## Change Log
Date | Author | Release | Reason for change
05.03.2024 | Ankur Pande | 0.1 | New Migration Test Scenario document
26.03.2024 | Ankur Pande | 0.2 | Uplifted comments by PPs. Please see Release Notes.
10.04.2024 | Ankur Pande | 0.3 | Uplifted comments by PPs and internal checks. Please see Release Notes for further information
30.04.2024 | Ankur Pande | 0.4 | Added ISD check and new steps for COS from updated BPD/BPM document

## Terminology
Terminology Used | Description | Type of Meter | Data Service | Description
BAU Process | This refers to a process within the MHHS arrangements as set out within the MHHS Core Design | Smart | SDSC | Smart Meter Data Service - Curent
CoA | Change of Agent |  | SDSI | Smart Meter Data Service - Incoming
CoS | Change of Supplier |  | SDSO | Smart Meter Data Service - Outgoing
CSS | Central Switching Service | Traditional | SDSC | Traditional Meter Data Service - Current
Data Cleanse Plan | The approach and activities required to improve and populate data prior to Migration start |  | SDSI | Traditional Meter Data Service - Incoming
DC | Data Collector |  | SDSO | Traditional Meter Data Service - Outgoing
DIP | Data Integration Platform | Advanced | ADSC | Advanced Meter Data Service - Current
DS | Data Service |  | ADSI | Advanced Meter Data Service - Incoming
Forward Migration | The process through which MPANs will move from Legacy arrangements to MHHS arrangements. |  | ADSO | Advanced Meter Data Service - Outgoing
Incoming / New MS | Incoming / New Metering Service | Unmetered | UMSDS | Unmetered Data Service
Incoming DS / New DS | Incoming Data Services
ISD | Industry Standing Data | Type of Meter | Metering Service | Description
LDSO | Licensed Distribution System Operator | Smart | SMSC | Smart Meter Metering Service - Current
MHHS | Market-Wide Half-Hourly Settlement |  | SMSI | Smart Meter Metering Service - Incoming
MHHS Arrangements | The new MHHS arrangements as set out in the MHHS Core Design Artefacts. |  | SMSO | Smart Meter Metering Service - Outgoing
Migration Design | The technical articulation of how MPANs will move from Legacy to new MHHS arrangements. | Traditional | SMSC | Traditional Meter Metering Service - Current
Migration Period | The period denoted by the Programme as occurring between the M11 and M15 milestones. |  | SMSI | Traditional Meter Metering Service - Incoming
MOP | Meter Operator |  | SMSO | Traditional Meter Metering Service - Outgoing
MPAN | Metering Point Administration Number | Advanced | AMSC | Advanced Meter Metering Service - Current
MS | Metering Service |  | AMSI | Advanced Meter Metering Service - Incoming
Outgoing MOP | Outgoing Meter Operator |  | AMSO | Advanced Meter Metering Service - Outgoing
Qualified Supplier | A Supplier recognised in ISD as both having passed the relevant System Integration Testing (SIT) requirements or BSC qualification requirements; and declared that their service is operational within the MHHS arrangements. | Unmetered | UMSO | Unmetered Metering Service
Registration Service | The service operated by LDSOs
REGS | Registration Services | Format | Description
Reverse Migration | The process through which MPANs will move from MHHS arrangements to Legacy arrangements. | Text in GREEN | NEW steps introduced for MIGRATION
Secondary MPAN | The MPAN, within a Related MPAN arrangement, for which a Forward Migration occurs when an IF-031 is received for a Primary MPAN. | Participants in RED | Out of scope participants - substituted by stubs or out of scope for testing
SUPC | Current Supplier | MS | Step in the "Change of Service - Metering Service" process
SUPI | Incoming Supplier | DS | Step in the "Change of Service - Data Service" process
SUPL | Linked Supplier | MS & DS | Common step for "Metering Service" and "Data Service" processes
SUPS | Sending Supplier
Switch | The process by which a new Supplier Registration supersedes an existing Supplier Registration, managed by the CSS.
XDSC | Data Service - Current
XDSP | Data Service – Proposed (denotes that multiple entries for same MAPN (but different DIP ID/Additional Info combinations) may exist for sniffer value)
XDSS | Data Service - Sending
XMIG | Migration Status (IF-036/IF-003)
XMSC | Metering Service – Current
XMSP | Metering Service – Proposed (denotes that multiple entries for same MAPN (but different DIP ID/Additional Info combinations) may exist for sniffer value )
XMSS | Metering Service - Sending
XMSU | Incumbent Metering Service (IF-035)
XMTR | Meter Type (IF-006)
XSEG | Segment (IF-044)
UMSO | Unmetered Metering Service
UMSDS | Unmetered Data Service

## SIT-M-FM-COS-RejApt Overview
Scenario ID | SIT-M-FM-COS-RejApt
Theme | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) - Rejected Appointment
Scenario Title | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) - Rejected Appointment
Description | This is a Forward Migration CoS Scenario - Appointment is rejected. Supplier choses to migrate an existing Legacy System MPAN to new MHHS compliant systems but the appointment is rejected. This document lists both DS and MS changes for each meter segment type. In the case of Traditional and Smart meter segments, SMSI and SDSI will be the PPs. In the case of Advanced Meters, AMSI and ADSI will be the PPs.
Functional Category | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) - Rejected Appointment
Functional Area 1 | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) - Rejected Appointment
Functional Area 2 | Existing MPAN, Change Agent successful with changes to Data Service and Metering Service
Creator | Ankur Pande
Priority | High
Scenario size | Large
Design Document Ref
Business Process | BP002, BP003, (+BP003A for Smart meters)
Pre-Requisites
Note
Test Case Variables | These test are specific to Prospective Appointments only as the process covers all functionality. (1) All Meter Types
Below is a list of all associated test cases to this scenario.
No. | Test Case Id | Test Case Title | Test Description | Meter Type | HH / NHH | Effective Date | Status
1 | SIT-M-FM-COS-RejApt-TC01 | SIT-M-FM-COS-RejApt-TC01 - All Meter Types | Under this scenario a MHHS Qualified Supplier chooses to migrate MPAN for all meter types MPAN from Legacy NHH settlements to MHHS arrangements but the appointment is rejected. This test is specific to Prospective Appointments only as it covers all functionality. | All | NHH | Next Day | Ready for review

## SIT-M-FM-COS-RejApt-TC01
Test Case Title | Key Journey Events | Test Step | Business Process | BP Step | Service Type | Test Steps | Test Description | Trigger Sender | Interface ID | Trigger Receipient | Traceability Requirement | Message Input Event Code | Evidence Required | Key Validation & Test Evidence
SIT-M-FM-CoS-NoObjection | Change of Supply - Start | 5 | BP001 | 60 | MS & DS | Initial Registration or Change of Supplier Required | SUPI sends Switch Request to CSS | SUPI | CSS01800 | CSS | N/A | N/A | Y | Evidence that SUPI generates a CSS01700; log screenshots in downstream systems.
|  | 10 | BP001 | 65 | MS & DS | MPAN Enquiry Web Service EES Interaction (if required) | CSS receives Switch Request from Incoming Supplier and responds to REGS | SUPI | CSS01800 | CSS | N/A | N/A | Y | Evidence that SUPI generates a CSS01700; log screenshots in downstream systems.
| COS Status at Pending | 15 | BP001 | 70 | MS & DS | COS status at Pending | CSS sends CSS2800 (pending Supplier request via CSS flow) to the REGS Registration Service receives pending Supplier request via CSS flow. | CSS | CSS2800 | REGS | MHHS-BR-RS-005 | N/A | Y | Evidence that CSS produces a CSS2800 which is consumed by REGS; log screenshots in downstream systems.
|  | 20 | BP001 | 75 | MS & DS | Provide Site Information to - Step 80 : DIP (using IF-002) - Step 185 : SUPI (D0217 / D0260) | REGS sends IF-002 to the DIP REGS sends D0217 / D0260 to SUPI | REGS | IF-002 D0217 / D0260 | DIP SUPI | MHHS-BR-RS-006 MHHS-Migration-CoS-RS-001 MHHS-Migration-CoS-RS-002 MHHS-Migration-CoS-RS-003 | N/A | y | (1) http 202 response from DIP. (2) Evidence that REGS produces a D0217/D0269 which are consumed by SUPI; log screenshots in downstream systems.
| DIP sends Pub-002 to SUPI | 25 | BP001 | 80 | MS & DS | Notification to New Supplier of Site Information | DIP receives MHHS-IF002 and sends PUB-002 to the new Supplier in order to obtain all relevant information to successfully set up the site in all systems and determine correct Service providers | DIP | PUB-002 | SUPI | DIP | [GainMPANInfo] | Y | Evidence that DIP produces a PUB-002 which is consumed by SUPI; log screenshots in downstream systems.
|  | 30 | BP001 | 85 | MS & DS | Receive Notification New Supplier Site Information | SUPI receives PUB-002 from REGS. | DIP | PUB-002 | SUPI | MHHS-BR-SU-001 | [GainMPANInfo] | Y | Evidence that DIP produces a PUB-002 which is consumed by SUPI; log screenshots in downstream systems.
| CSS sends COS Secured notification to SUPI | 35 | BP001 | 100 | MS & DS | CSS sends COS Active/COS Secured notification to SUPI | Suppliers will receive notification from CSS that COS has a secured status | CSS | CSS02370 | SUPI | MHHS-BR-SU-003 MHHS-BR-SU-048 | N/A | Y | Evidence that CSS produces a CSS Flow which is consumed by SUPI; log screenshots in downstream systems.
| ISD Check | 40 | BP001 |  | MS & DS | REGS confirms Supplier is MHHS qualified | REGS confirms identity of incoming Supplier is MHHS qualified
| CSS sends Loss Notification to SUPO | 45 | BP001 | 120 | MS & DS | CSS sends Loss Notification to SUPO | The Old supplier will receive notification once the Service providers have been de-appointed. This step is just for information which is why it is in grey. The de-appointment confirmation and activity will take place in BP002/BP003 | N/A | N/A | N/A | N/A | N/A | N
|  | 50 | BP001 | 125 | MS & DS | Control is transferred to BP003C - Read Transfer for Change of Data Service | This step is reflect that read/history transfer and any calculations for readings have been performed within BP003C. These are transferred to suppliers. | N/A | N/A | N/A | N/A | N/A | N
| CSS sends COS Secured notification to REGS | 55 | BP001 | 130 | MS & DS | CSS sends COS Active/COS Secured notification to REGS | The Registration Service will receive a COS secured notification from CSS. The Registration Service will send MHHS-IF-001 to confirm to parties the new Supplier information | CSS | CSS02860 | REGS | MHHS-BR-RS-007 MHHS-BR-RS-008 MHHS-BR-RS-094 MHHS-BR-RS-096 | N/A | Y | Evidence that CSS produces a CSS Flow which is consumed by REGS; log screenshots in downstream systems.
|  | 60 | BP001 | 135 | MS & DS | REGS sends new Supplier Details to DIP using an IF-001 | The DIP will receive MHHS-IF-001 from Registrations containing the new Supplier details | REGS | IF-001 | DIP | MHHS-BR-RS-008 | [ChangeOfSupplier] | y | http 202 response from DIP.
|  | 65 | BP001 | 150 | MS & DS | SIP publishes COS Details using PUB-001 to: - Step 155 : Central Settlements - Step 160 : LDSO - Step 165 : SUPI | The DIP will publish the new Supplier information via PUB-001 to the Supplier, LDSO and Central Settlements | DIP | PUB-001 | MDS LDSO SUPI EES | DIP | N/A | Y | Evidence that DIP produces a PUB-001 which is consumed by Central Settlements, LDSO, SUPI and EES; log screenshots in downstream systems.
| DIP sends Pub-001 to MDS | 70 | BP001 | 155 | MS & DS | MDS (Central Settlements) receives a PUB-001 from DIP with details of SUPI | MDS (Central Settlements) will receive the new Supplier details from the DIP. This must be updated in MDS so the appropriate settlement and charging can commence. | DIP | PUB-001 | MDS | Central settlements | [ChangeOfSupplier] | Y | Evidence that DIP produces a PUB-001 which is consumed by MDS (Central Settlements); log screenshots in downstream systems.
| DIP sends Pub-001 to LDSO | 75 | BP001 | 160 | MS & DS | LDSO receives a PUB-001 from DIP with details of SUPI | LDSO will receive the new Supplier details from the DIP | DIP | PUB-001 | LDSO | MHHS-BR-LD-001 MHHS-BR-LD-012 | [ChangeOfSupplier] | Y | Evidence that DIP produces a PUB-001 which is consumed by LDSO; log screenshots in downstream systems.
| DIP sends Pub-001 to SUPI | 80 | BP001 | 165 | MS & DS | SUPO SUPI receives a PUB-001 from DIP with details of SUPI | Outgoing Incoming Supplier will receive the new Supplier details from the DIP | DIP | PUB-001 | SUPI | MHHS-BR-SU-004 MHHS-BR-SU-049 | [ChangeOfSupplier] | Y | Evidence that DIP produces a PUB-001 which is consumed by SUPI; log screenshots in downstream systems.
| Send site tech details on Metering Service Request | 85 | BP001 | 169 | MS & DS | Request Site Tech Details from LDSO | Metering Services will issue a D0170 to the LDSO to request Metering Technical details on a new connection | Metering Service | D170 | LDSO | MHHS-BR-MS-037.2 .
|  | 90 | BP001 | 170 | MS & DS | Send Site Tech Details on Metering Service Request | The LDSO will receive a D0170 from Metering services requesting the site technical details and issue a D0215 with the information |  |  |  | MHHS-RS-LD-012.1
|  | 95 | BP001 | 175 | MS & DS | Receive Site Technical Details | Metering Services will receive a D0215 from the LDSO with the site technical details. | LDSO | D0215 | Metering Service | MHHS-RS-MS-037.1
| REGS sends D0217/D0260 to SUPI | 100 | BP001 | 185 | MS & DS | Receive Old Supplier Registration Details / Confirmation of the Registration of a Metering Point | The new Supplier receives the registration details of the old Supplier and confirms the registration of the Meter point. | REGS | D0217 / D0260 | SUPI |  | N/A | Y | Evidence that REGS produces a D0217/D0260 which is consumed by SUPI; log screenshots in downstream systems.
SIT-M-FM-COS-RejApt-TC01 | Determine Service Required | 115 | BP002 BP003 | 5 10 | MS & DS | Determine Metering Service Required | Supplier must identify the correct Market Segment. | N/A | N/A | N/A | MS - MHHS-BR-SU-005 DS - MHHS-BR-SU-019 | N/A | N | N/A
| Setting up Appointments | 120 | BP002 | 20 | MS | Send Initial MS Appointment Request | Supplier will send the correct appointment details for the appropriate Service provider | SUPC | IF-031 | DIP | MHHS-BR-SU-006 MHHS-BR-SU-007 MHHS-Migration-CoA(MS)-SUP-001 MHHS-Migration-CoA(MS)-SUP-004 | [MSApp] | Y | http 202 response from DIP
|  | 125 | BP002 | 30 | MS | Publish Initial MS Appointment Request | The DIP will receive the appointment details from Supplier and publish them to the Registration Service. | DIP | PUB-031 | REGS | MHHS-BR-RS-009 | [MSApp] | Y | Evidence that REGS processes the PUB-031 generated by DIP; log screenshots in downstream systems.
|  | 130 | BP003 | 20 | DS | Send Initial DS Appointment Request | Supplier will send the correct appointment details for the appropriate Service provider | SUPC | IF-031 | DIP | MHHS-BR-SU-020 MHHS-BR-SU-021 MHHS-Migration-CoA(DS)-SUP-002 MHHS-Migration-CoA(DS)-SUP-003 | [DSApp] | Y | http 202 response from DIP
|  | 135 | BP003 | 30 | DS | Publish Initial DS Appointment Request | The DIP will receive the appointment details from Supplier and publish them to the Registration Service. | DIP | PUB-031 | REGS | DIP | [DSApp] | Y | Evidence that REGS processes the PUB-031 generated by DIP; log screenshots in downstream systems.
| Validate Initial Appointment Request | 140 | BP002 | 40 | MS | Validate Initial MS Appointment Request Step 45 - All requests Step 60 - Valid Requests only | The REGS will receive the publication 'Supplier Service Appointment Request' from the DIP and validate the content of the message as per the Registration validation rules for Service providers | DIP | PUB-031 | REGS | MHHS-BR-RS-010 MHHS-Migration-CoA(MS)-RS-004 MHHS-Migration-CoA(MS)-RS-005 MHHS-Migration-Can-RS-005 MHHS-Migration-CoA(MS)-RS-007 MHHS-Migration-CoA(MS)-RS-009 MHHS-Migration-CoA(MS)-RS-011 MHHS-Migration-CoA(MS)-RS-013 MHHS-Migration-CoA(MS)-RS-019 | [MSApp] | Y | Evidence that REGS processes the PUB-031 generated by DIP; log screenshots in downstream systems.
|  | 145 | BP003 | 40 | DS | Validate Initial DS Appointment Request Step 45 - All requests Step 60 - Valid Requests only | The REGS will receive the publication 'Supplier Service Appointment Request' from the DIP and validate the content of the message as per the registration validation rules for Service providers | DIP | PUB-031 | REGS | MHHS-BR-RS-043 MHHS-BR-RS-044 MHHS-Migration-CoA(DS)-RS-004 MHHS-Migration-CoA(DS)-RS-005 MHHS-Migration-Can-RS-005 MHHS-Migration-CoA(DS)-RS-007 MHHS-Migration-CoA(DS)-RS-009 MHHS-Migration-CoA(DS)-RS-011 MHHS-Migration-CoA(DS)-RS-013 MHHS-Migration-CoA(DS)-RS-020 | [DSApp] | Y | Evidence that REGS processes the PUB-031 generated by DIP; log screenshots in downstream systems.
| All Appointment Requests | 150 | BP002 | 45 | MS | Issue Initial MS Appointment Request Response for ALL requests | The REGS will respond to the DIP for the 'Supplier Service Appointment Request' with the appropriate response to Accept appointment. | REGS | IF-032 | DIP | MHHS-BR-RS-011 MHHS-BR-RS-012 MHHS-Migration-CoA(MS)-RS-010 MHHS-Migration-CoA(MS)-RS-012 MHHS-Migration-CoA(MS)-RS-014 | [MSAppInitialResp] | Y | http 202 response from DIP
|  | 155 | BP002 | 50 | MS | Publish Initial MS Appointment Request Response | The DIP will publish the REGS response to the 'Supplier Service Appointment Request' | DIP | PUB-032 | SUPC | DIP | [MSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.
|  | 160 | BP002 | 55 | MS | Manage Initial MS Appointment Request Response | Supplier will receive response to the appointment request from the Registration Service and take the appropriate action dependant on outcome | DIP | PUB-032 | SUPC | MHHS-BR-SU-008 MHHS-BR-SU-009 | [MSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.
|  | 165 | BP003 | 45 | DS | Issue Initial DS Appointment Request for all requests | The REGS will respond to the DIP for the 'Supplier Service Appointment Request' with the appropriate response to Accept appointment. | REGS | IF-032 | DIP | MHHS-BR-RS-045 MHHS-BR-RS-046 MHHS-Migration-CoA(DS)-RS-010 MHHS-Migration-CoA(DS)-RS-012 MHHS-Migration-CoA(DS)-RS-014 | [DSAppInitialResp] | Y | http 202 response from DIP
|  | 170 | BP003 | 50 | DS | Publish Initial DS Appointment Request Response | The DIP will publish the REGS response to the 'Supplier Service Appointment Request' | DIP | PUB-032 | SUPC | DIP | [DSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.
|  | 175 | BP003 | 55 | DS | Manage Initial DS Appointment Request Response | Suppler will receive response to the appointment request from the Registration Service and take the appropriate action dependant on outcome | DIP | PUB-032 | SUPC | MHHS-BR-SU-022 MHHS-BR-SU-023 | [DSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.
| Valid Requests Only | 180 | BP002 | 60 | MS | Issue Request MS Proposed Appointment Validation | The REGS will send 'REGS Request for Service Appointment' to the correct service provider via the DIP | REGS | IF-033 | DIP | MHHS-BR-RS-014.1 MHHS-BR-RS-015 | [MSAppSPRequest] | Y | http 202 response from DIP
|  | 185 | BP002 | 65 | MS | Publish Proposed MS Appointment Validation Request | The DIP will publish the 'REGS Request for Service Appointment' to the Metering Service | DIP | PUB-033 | SMSI (Trad, Smart) AMSI (Adv) | DIP | [MSAppSPRequest] | Y | Evidence that Metering Service processes the PUB-033 generated by DIP; log screenshots in downstream systems.
|  | 190 | BP002 | 70 | MS | Manage MS Proposed Appointment Validation Request | Metering Service will receive an appointment from the Supplier via the REGS. Metering Service must process and validate the appointment request as per the validation rules. This is a Appointment Rejection Scenario - Therefore, the MS should REJECT the appointment. | DIP | PUB-033 | SMSI (Trad, Smart) AMSI (Adv) | MHHS-BR-MS-001 | [MSAppSPRequest] | Y | Evidence that Metering Service processes the PUB-033 generated by DIP; log screenshots in downstream systems.
|  | 195 | BP002 | 75 | MS | Respond to MS Proposed Appointment Request | If the appointment request is invalid the Metering Service will reject the appointment and apply the relevant rejection reason and send all responses back to the Registration Service | SMSI (Trad, Smart) AMSI (Adv) | IF-034 | DIP | MHHS-BR-MS-002 MHHS-BR-MS-003 | [MSAppSPResponse] | Y | http 202 response from DIP
|  | 200 | BP002 | 80 | MS | Publish Proposed MS Appointment Validation Response | The DIP will publish the responses from service providers | DIP | PUB-034 | REGS | DIP MHHS-Migration-CoA(MS)-SUP-005 | [MSAppSPResponse] | Y | Evidence that REGS processes the PUB-034 generated by DIP; log screenshots in downstream systems.
|  | 210 | BP003 | 60 | DS | Issue Request DS Proposed Appointment | The REGS will send 'REGS Request for Service Appointment' to the correct Service provider via the DIP | REGS | IF-033 | DIP | MHHS-BR-RS-049 MHHS-BR-RS-048.1 | [DSAppSPRequest] | Y | http 202 response from DIP
|  | 215 | BP003 | 65 | DS | Publish Proposed DS Appointment Validation Request | The DIP will publish the 'REGS Request for Service Appointment' to the Data Service | DIP | PUB-033 | SDSI (Smart, Trad) ADSI (Adv Meters) | DIP | [DSAppSPRequest] | Y | Evidence that Data Service processes the PUB-033 generated by DIP; log screenshots in downstream systems.
|  | 220 | BP003 | 220 | DS | Manage DS Appointment Request | Data Services will receive an appointment from the supplier via the REGS. Data services must process and validate the appointment request as per the validation rules. This is a Appointment Rejection Scenario - Therefore, the MS should REJECT the appointment. | N/A | N/A | N/A | MHHS-BR-DS-007 MHHS-BR-DS-008 MHHS-BR-DS-011 | N/A
|  | 225 | BP003 | 221 | DS | Respond to DS Appointment Request | The Data Service will reject the appointment and apply the relevant rejection reason and send all responses back to the Registration Service | SDSI (Smart, Trad) ADSI (Adv Meters) | IF-034 | DIP | MHHS-BR-DS-008 MHHS-BR-DS-011 | [DSAppSPResponse] | Y | http 202 response from DIP
| Additional step for DS for Accepted appointments | 230 | BP003 | 230 | DS | 3rd Party Appointment | Once the Data Service has accepted the appointment they must appoint the nominated 3rd parties as per the agreed contract and the agreed method. | N/A | N/A | N/A | MHHS-BR-DS-009 MHHS-BR-DS-010 | N/A
| All Outcomes | 235 | BP003 | 80 | DS | Publish Proposed DS Appointment Validation Response | The DIP will publish the responses from Data services | DIP | PUB-034 | REGS | DIP MHHS-Migration-CoA(DS)-SUP-004 | [DSAppSPResponse] | Y | Evidence that REGS processes the PUB-034 generated by DIP; log screenshots in downstream systems.
| For All Appointment Responses | 245 | BP002 | 87 | MS | Issue Appointment Rejection | The REGS will send out all responses it has received from the Metering Services back to Supplier via the DIP. | REGS | IF-035 | DIP | MHHS-BR-RS-018 | [MSAppRejected] | Y | http 202 response from DIP
|  | 250 | BP002 | 91 | MS | Publish Appointment Rejection | The DIP will publish the Metering Service response for the appointment to Supplier. | DIP | PUB-035 | SUPC SMSI (Trad, Smart) AMSI (Adv) | DIP | [MSAppRejected] | Y | Evidence that Supplier & Metering Services processes the PUB-035 generated by DIP; log screenshots in downstream systems.
|  | 255 | BP002 | 92 | MS | Manage Request Response for Rejected Appointment | Metering Services will receive PUB-035 confirming the REGS has received the Metering Services response to the appointment | DIP | PUB-035 | SMSI (Trad, Smart) AMSI (Adv) | MHHS-BR-MS-006.1 | [MSAppRejected] | Y | Evidence that Metering Service processes the PUB-035 generated by DIP; log screenshots in downstream systems.
|  | 260 | BP003 | 90 | DS | Publish Rejected Appointment Outcome Response | The DIP will send out all responses it has received from the Data Services back to Supplier | DIP | PUB-035 | SDSI (Smart, Trad) ADSI (Adv Meters) SUPC | DIP | [DSAppRejected] | Y | Evidence that Data Service & Supplier processes the PUB-035 generated by DIP; log screenshots in downstream systems.
|  | 275 | BP003 | 91 | DS | Manage DS Proposed Appointment Request Response | Data Services will receive PUB-035 confirming REGS received the Data Services response to the rejection of the appointment | DIP | PUB-035 | SDSI (Smart, Trad) ADSI (Adv Meters) | MHHS-BR-DS-012.1 | [DSAppRejected] | Y | Evidence that New Data Service processes the PUB-035 generated by DIP; log screenshots in downstream systems.
| Manage Prospective Appointment | 280 | BP002 | 95 | MS | Send Rejected Appointment Response | Supplier will receive appointment rejection for the Metering Service appointment request. | DIP | PUB-035 | SUPC | MHHS-BR-SU-010 MHHS-BR-SU-011 | [MSAppRejected] | Y | Evidence that Supplier processes the PUB-035 generated by DIP; log screenshots in downstream systems.
|  | 285 | BP003 | 95 | DS | Send Rejected Appointment Response | Supplier will receive appointment rejection for the Data Service appointment request. | DIP | PUB-035 | SUPC | MHHS-BR-SU-024 MHHS-BR-SU-025 | [DSAppRejected] | Y | Evidence that Supplier processes the PUB-035 generated by DIP; log screenshots in downstream systems.