## Change Log
Date | Author | Release | Reason for change
05.03.2024 | Ankur Pande | 0.1 | New Migration Test Scenario document
26.03.2024 | Ankur Pande | 0.2 | Uplifted comments by PPs. Please see Release Notes.
10.04.2024 | Ankur Pande | 0.3 | Uplifted comments by PPs and internal checks. Please see Release Notes for further information

## Terminology
Terminology Used | Description | Type of Meter | Data Service | Description
BAU Process | This refers to a process within the MHHS arrangements as set out within the MHHS Core Design | Smart | SDSC | Smart Meter Data Service - Curent
CoA | Change of Agent |  | SDSI | Smart Meter Data Service - Incoming
CoS | Change of Supplier |  | SDSO | Smart Meter Data Service - Outgoing
CSS | Central Switching Service | Traditional | SDSC | Traditional Meter Data Service - Current
Data Cleanse Plan | The approach and activities required to improve and populate data prior to Migration start |  | SDSI | Traditional Meter Data Service - Incoming
DC | Data Collector |  | SDSO | Traditional Meter Data Service - Outgoing
DIP | Data Integration Platform | Advanced | ADSC | Advanced Meter Data Service - Current
DS | Data Service |  | ADSI | Advanced Meter Data Service - Incoming
Forward Migration | The process through which MPANs will move from Legacy arrangements to MHHS arrangements. |  | ADSO | Advanced Meter Data Service - Outgoing
Incoming / New MS | Incoming / New Metering Service | Unmetered | UMSDS | Unmetered Data Service
Incoming DS / New DS | Incoming Data Services
ISD | Industry Standing Data | Type of Meter | Metering Service | Description
LDSO | Licensed Distribution System Operator | Smart | SMSC | Smart Meter Metering Service - Current
MHHS | Market-Wide Half-Hourly Settlement |  | SMSI | Smart Meter Metering Service - Incoming
MHHS Arrangements | The new MHHS arrangements as set out in the MHHS Core Design Artefacts. |  | SMSO | Smart Meter Metering Service - Outgoing
Migration Design | The technical articulation of how MPANs will move from Legacy to new MHHS arrangements. | Traditional | SMSC | Traditional Meter Metering Service - Current
Migration Period | The period denoted by the Programme as occurring between the M11 and M15 milestones. |  | SMSI | Traditional Meter Metering Service - Incoming
MOP | Meter Operator |  | SMSO | Traditional Meter Metering Service - Outgoing
MPAN | Metering Point Administration Number | Advanced | AMSC | Advanced Meter Metering Service - Current
MS | Metering Service |  | AMSI | Advanced Meter Metering Service - Incoming
Outgoing MOP | Outgoing Meter Operator |  | AMSO | Advanced Meter Metering Service - Outgoing
Qualified Supplier | A Supplier recognised in ISD as both having passed the relevant System Integration Testing (SIT) requirements or BSC qualification requirements; and declared that their service is operational within the MHHS arrangements. | Unmetered | UMSO | Unmetered Metering Service
Registration Service | The service operated by LDSOs
REGS | Registration Services | Format | Description
Reverse Migration | The process through which MPANs will move from MHHS arrangements to Legacy arrangements. | Text in GREEN | NEW steps introduced for MIGRATION
Secondary MPAN | The MPAN, within a Related MPAN arrangement, for which a Forward Migration occurs when an IF-031 is received for a Primary MPAN. | Participants in RED | Out of scope participants - substituted by stubs or out of scope for testing
SUPC | Current Supplier | MS | Step in the "Change of Service - Metering Service" process
SUPI | Incoming Supplier | DS | Step in the "Change of Service - Data Service" process
SUPL | Linked Supplier | MS & DS | Common step for "Metering Service" and "Data Service" processes
SUPS | Sending Supplier
Switch | The process by which a new Supplier Registration supersedes an existing Supplier Registration, managed by the CSS.
XDSC | Data Service - Current
XDSP | Data Service – Proposed (denotes that multiple entries for same MAPN (but different DIP ID/Additional Info combinations) may exist for sniffer value)
XDSS | Data Service - Sending
XMIG | Migration Status (IF-036/IF-003)
XMSC | Metering Service – Current
XMSP | Metering Service – Proposed (denotes that multiple entries for same MAPN (but different DIP ID/Additional Info combinations) may exist for sniffer value )
XMSS | Metering Service - Sending
XMSU | Incumbent Metering Service (IF-035)
XMTR | Meter Type (IF-006)
XSEG | Segment (IF-044)
UMSO | Unmetered Metering Service
UMSDS | Unmetered Data Service

## SIT-M-FM-COS-InvReq Overview
Scenario ID | SIT-M-FM-COS-InvReq
Theme | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) - Invalid Request
Scenario Title | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) - Invalid Request
Description | This is a Forward Migration CoS Scenario. Supplier choses to migrate an existing Legacy System MPAN to new MHHS compliant systems but the request is invalid. This document lists both DS and MS changes for each meter segment type.
Functional Category | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) - Invalid Request
Functional Area 1 | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) - Invalid Request
Functional Area 2 | Existing MPAN, Change of Agent is not successful because the appointments lapse
Creator | Ankur Pande
Priority | High
Scenario size | Large
Design Document Ref
Business Process | BP002, BP003, (+BP003A for Smart meters)
Pre-Requisites
Note
Test Case Variables | These test are specific to Prospective Appointments only as the process covers all functionality. (1) All Meter Types
Below is a list of all associated test cases to this scenario.
No. | Test Case Id | Test Case Title | Test Description | Meter Type | HH / NHH | Effective Date | Status
1 | SIT-M-FM-COS-InvReq-TC01 | SIT-M-FM-COS-InvReq-TC01 - All Meter Types | Under this scenario a MHHS Qualified Supplier chooses to migrate all meter type MPAN from Legacy NHH settlements to MHHS arrangements but the request is invalid This test is specific to Prospective Appointments only as it covers all functionality. | Traditional | NHH | Next Day | Ready for review

## SIT-M-FM-COS-InvReq-TC01
Test Case Title | Key Journey Events | Test Step | Business Process | BP Step | Service Type | Test Steps | Test Description | Trigger Sender | Interface ID | Trigger Receipient | Traceability Requirement | Message Input Event Code | Evidence Required | Key Validation & Test Evidence
SIT-M-FM-CoS-NoObjection | Change of Supply - Start | 5 | BP001 | 60 | MS & DS | Initial Registration or Change of Supplier Required | SUPI sends Switch Request to CSS | SUPI | CSS01800 | CSS | N/A | N/A | Y | Evidence that SUPI generates a CSS01700; log screenshots in downstream systems.
|  | 10 | BP001 | 65 | MS & DS | MPAN Enquiry Web Service Interaction (if required) | CSS receives Switch Request from Incoming Supplier and responds to REGS | SUPI | CSS01800 | CSS | N/A | N/A | Y | Evidence that SUPI generates a CSS01700; log screenshots in downstream systems.
| > CSS sends Loss Notification to SUPO | 20 | BP001 | 120 | MS & DS | CSS sends Loss Notification to SUPO | The Old supplier will receive notification once the Service providers have been de-appointed. This step is just for information which is why it is in grey. The de-appointment confirmation and activity will take place in BP002/BP003 | N/A | N/A | N/A | N/A | N/A | N
|  | 25 | BP001 | 125 | MS & DS | Control is transferred to BP003C - Read Transfer for Change of Data Service | This step is reflect that read/history transfer and any calculations for readings have been performed within BP003C. These are transferred to suppliers. | N/A | N/A | N/A | N/A | N/A | N
| > CSS sends COS Secured notification to SUPI | 30 | BP001 | 100 | MS & DS | CSS sends COS Active/COS Secured notification to SUPI | Suppliers will receive notification from CSS that COS has a secured status | CSS | CSS02370 | SUPI | MHHS-BR-SU-003 MHHS-BR-SU-048 | N/A | Y | Evidence that CSS produces a CSS Flow which is consumed by SUPI; log screenshots in downstream systems.
| ISD Check | 33 | BP001 |  | MS & DS | REGS confirms Supplier is MHHS qualified | REGS confirms identity of incoming Supplier is MHHS qualified
| > CSS sends COS Secured notification to REGS | 35 | BP001 | 130 | MS & DS | CSS sends COS Active/COS Secured notification to REGS | The Registration Service will receive a COS secured notification from CSS. The Registration Service will send MHHS-IF-001 to confirm to parties the new Supplier information | CSS | CSS02860 | REGS | MHHS-BR-RS-007 MHHS-BR-RS-008 MHHS-BR-RS-094 MHHS-BR-RS-096 | N/A | Y | Evidence that CSS produces a CSS Flow which is consumed by REGS; log screenshots in downstream systems.
|  | 40 | BP001 | 135 | MS & DS | REGS sends new Supplier Details to DIP using an IF-001 | The DIP will receive MHHS-IF-001 from Registrations containing the new Supplier details | REGS | IF-001 | DIP | MHHS-BR-RS-008 | [ChangeOfSupplier] | y | http 202 response from DIP.
|  | 45 | BP001 | 150 | MS & DS | SIP publishes COS Details using PUB-001 to: - Step 155 : Central Settlements - Step 160 : LDSO - Step 165 : SUPI | The DIP will publish the new Supplier information via PUB-001 to the Supplier, LDSO and Central Settlements | DIP | PUB-001 | MDS LDSO SUPI EES | DIP | N/A | Y | Evidence that DIP produces a PUB-001 which is consumed by Central Settlements, LDSO, SUPI and EES; log screenshots in downstream systems.
| >> DIP sends Pub-001 to MDS | 50 | BP001 | 155 | MS & DS | MDS (Central Settlements) receives a PUB-001 from DIP with details of SUPI | MDS (Central Settlements) will receive the new Supplier details from the DIP. This must be updated in MDS so the appropriate settlement and charging can commence. | DIP | PUB-001 | MDS | Central settlements | [ChangeOfSupplier] | Y | Evidence that DIP produces a PUB-001 which is consumed by MDS (Central Settlements); log screenshots in downstream systems.
| >> DIP sends Pub-001 to LDSO | 55 | BP001 | 160 | MS & DS | LDSO receives a PUB-001 from DIP with details of SUPI | LDSO will receive the new Supplier details from the DIP | DIP | PUB-001 | LDSO | MHHS-BR-LD-001 MHHS-BR-LD-012 | [ChangeOfSupplier] | Y | Evidence that DIP produces a PUB-001 which is consumed by LDSO; log screenshots in downstream systems.
| >> DIP sends Pub-001 to SUPI | 60 | BP001 | 165 | MS & DS | SUPO receives a PUB-001 from DIP with details of SUPI | Outgoing Supplier will receive the new Supplier details from the DIP | DIP | PUB-001 | SUPI | MHHS-BR-SU-004 MHHS-BR-SU-049 | [ChangeOfSupplier] | Y | Evidence that DIP produces a PUB-001 which is consumed by SUPI; log screenshots in downstream systems.
| > COS Status at Pending | 70 | BP001 | 70 | MS & DS | COS status at Pending | CSS sends CSS2800 (pending Supplier request via CSS flow) to the REGS Registration Service receives pending Supplier request via CSS flow. | CSS | CSS2800 | REGS | MHHS-BR-RS-005 | N/A | Y | Evidence that CSS produces a CSS2800 which is consumed by REGS; log screenshots in downstream systems.
|  | 75 | BP001 | 75 | MS & DS | Provide Site Information to - Step 80 : DIP (using IF-002) - Step 185 : SUPI (D0217 / D0260) | REGS sends IF-002 to the DIP REGS sends D0217 / D0260 to SUPI | REGS | IF-002 D0217 / D0260 | DIP SUPI | MHHS-BR-RS-006 MHHS-Migration-CoS-RS-001 MHHS-Migration-CoS-RS-002 MHHS-Migration-CoS-RS-003 | N/A | y | (1) http 202 response from DIP. (2) Evidence that REGS produces a D0217/D0269 which are consumed by SUPI; log screenshots in downstream systems.
| >> DIP sends Pub-002 to SUPI | 85 | BP001 | 80 | MS & DS | Notification to New Supplier of Site Information | DIP receives MHHS-IF002 and sends PUB-002 to the new Supplier in order to obtain all relevant information to successfully set up the site in all systems and determine correct Service providers | DIP | PUB-002 | SUPI | DIP | [GainMPANInfo] | Y | Evidence that DIP produces a PUB-002 which is consumed by SUPI; log screenshots in downstream systems.
|  | 90 | BP001 | 85 | MS & DS | Receive Notification New Supplier Site Information | SUPI receives PUB-002 from REGS. | DIP | PUB-002 | SUPI | MHHS-BR-SU-001 | [GainMPANInfo] | Y | Evidence that DIP produces a PUB-002 which is consumed by SUPI; log screenshots in downstream systems.
| >> REGS sends D0217/D0260 to SUPI | 95 | BP001 | 185 | MS & DS | Receive Old Supplier Registration Details / Confirmation of the Registration of a Metering Point | The new Supplier receives the registration details of the old Supplier and confirms the registration of the Meter point. | REGS | D0217 / D0260 | SUPI |  | N/A | Y | Evidence that REGS produces a D0217/D0260 which is consumed by SUPI; log screenshots in downstream systems.
SIT-M-FM-COS-LAPSED-TC01 | Determine Service Required | 115 | BP002 BP003 | 5 10 | MS & DS | Determine Metering Service Required | Supplier must identify the correct Market Segment. | N/A | N/A | N/A | MS - MHHS-BR-SU-005 DS - MHHS-BR-SU-019 | N/A | N | N/A
| Setting up Appointments | 120 | BP002 | 20 | MS | Send Initial MS Appointment Request | Supplier will send the correct appointment details for the appropriate Service provider | SUPC | IF-031 | DIP | MHHS-BR-SU-006 MHHS-BR-SU-007 MHHS-Migration-CoA(MS)-SUP-001 MHHS-Migration-CoA(MS)-SUP-004 | [MSApp] | Y | http 202 response from DIP
|  | 125 | BP002 | 30 | MS | Publish Initial MS Appointment Request | The DIP will receive the appointment details from Supplier and publish them to the Registration Service. | DIP | PUB-031 | REGS | MHHS-BR-RS-009 | [MSApp] | Y | Evidence that REGS processes the PUB-031 generated by DIP; log screenshots in downstream systems.
|  | 130 | BP003 | 20 | DS | Send Initial DS Appointment Request | Supplier will send the correct appointment details for the appropriate Service provider | SUPC | IF-031 | DIP | MHHS-BR-SU-020 MHHS-BR-SU-021 MHHS-Migration-CoA(DS)-SUP-002 MHHS-Migration-CoA(DS)-SUP-003 | [DSApp] | Y | http 202 response from DIP
|  | 135 | BP003 | 30 | DS | Publish Initial DS Appointment Request | The DIP will receive the appointment details from Supplier and publish them to the Registration Service. | DIP | PUB-031 | REGS | DIP | [DSApp] | Y | Evidence that REGS processes the PUB-031 generated by DIP; log screenshots in downstream systems.
| Validate Initial Appointment Request | 140 | BP002 | 40 | MS | Validate Initial MS Appointment Request Step 45 - All requests Step 60 - Valid Requests only | The REGS will receive the publication 'Supplier Service Appointment Request' from the DIP and validate the content of the message as per the Registration validation rules for Service providers | DIP | PUB-031 | REGS | MHHS-BR-RS-010 MHHS-Migration-CoA(MS)-RS-004 MHHS-Migration-CoA(MS)-RS-005 MHHS-Migration-Can-RS-005 MHHS-Migration-CoA(MS)-RS-007 MHHS-Migration-CoA(MS)-RS-009 MHHS-Migration-CoA(MS)-RS-011 MHHS-Migration-CoA(MS)-RS-013 MHHS-Migration-CoA(MS)-RS-019 | [MSApp] | Y | Evidence that REGS processes the PUB-031 generated by DIP; log screenshots in downstream systems.
|  | 145 | BP003 | 40 | DS | Validate Initial DS Appointment Request Step 45 - All requests Step 60 - Valid Requests only | The REGS will receive the publication 'Supplier Service Appointment Request' from the DIP and validate the content of the message as per the registration validation rules for Service providers | DIP | PUB-031 | REGS | MHHS-BR-RS-043 MHHS-BR-RS-044 MHHS-Migration-CoA(DS)-RS-004 MHHS-Migration-CoA(DS)-RS-005 MHHS-Migration-Can-RS-005 MHHS-Migration-CoA(DS)-RS-007 MHHS-Migration-CoA(DS)-RS-009 MHHS-Migration-CoA(DS)-RS-011 MHHS-Migration-CoA(DS)-RS-013 MHHS-Migration-CoA(DS)-RS-020 | [DSApp] | Y | Evidence that REGS processes the PUB-031 generated by DIP; log screenshots in downstream systems.
| All Appointment Requests | 150 | BP002 | 45 | MS | Issue Initial MS Appointment Request Response for ALL requests | The REGS will accept receive the 'Supplier Service Appointment Request' with Rejection response | REGS | IF-032 | DIP | MHHS-BR-RS-011 MHHS-BR-RS-012 MHHS-Migration-CoA(MS)-RS-010 MHHS-Migration-CoA(MS)-RS-012 MHHS-Migration-CoA(MS)-RS-014 | [MSAppInitialResp] | Y | http 202 response from DIP
|  | 155 | BP002 | 50 | MS | Publish Initial MS Appointment Request Response | The DIP will publish the REGS Rejection response to the 'Supplier Service Appointment Request' | DIP | PUB-032 | SUPC | DIP | [MSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.
|  | 160 | BP002 | 55 | MS | Manage Initial MS Appointment Request Response | Supplier will receive Rejection response to the appointment request from the REGS | DIP | PUB-032 | SUPC | MHHS-BR-SU-008 MHHS-BR-SU-009 | [MSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.
|  | 165 | BP003 | 45 | DS | Issue Initial DS Appointment Request for all requests | The REGS will accept receive the 'Supplier Service Appointment Request' with Rejection response | REGS | IF-032 | DIP | MHHS-BR-RS-045 MHHS-BR-RS-046 MHHS-Migration-CoA(DS)-RS-010 MHHS-Migration-CoA(DS)-RS-012 MHHS-Migration-CoA(DS)-RS-014 | [DSAppInitialResp] | Y | http 202 response from DIP
|  | 170 | BP003 | 50 | DS | Publish Initial DS Appointment Request Response | The DIP will publish the REGS Rejection response to the 'Supplier Service Appointment Request' | DIP | PUB-032 | SUPC | DIP | [DSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.
|  | 175 | BP003 | 55 | DS | Manage Initial DS Appointment Request Response | Supplier will receive Rejection response to the appointment request from the REGS | DIP | PUB-032 | SUPC | MHHS-BR-SU-022 MHHS-BR-SU-023 | [DSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.