## Change Log
Date | Author | Release | Reason for change
2024-05-28 | MHHS NFT | 0.1 | Initial version
2024-06-21 | MHHS NFT | 0.2 | Updates post industry review

## SITNFT-T2-100 Disconnect OV
Scenario ID | SITNFT-T2-100
Scenario Title | Disconnection initiated by LDSO or Customer
Theme | Metering Changes
Description | In emergency situations, the LDSO or Customer can initiate a Disconnection. the following scenarios are to be covered: 1) Customer Initiated 2) LDSO Initiated - Metered 3) LDSO Initiated - No Meter/Supplier on Site 4) LDSO initiated - Unmetered Confirm Disconnection is completed successfully and Metering Services and Data Services are de-appointed. Ensure supplier successfully intakes IF-037 and IF-009 with EES successfully intaking IF-050.
Functional Category | Metering Changes
Functional Area 1 | Disconnection
Functional Area 2 | Disconnection successful
Creator | MHHS NFT
Priority | High
Scenario size | Medium
Design Document Ref
Business Process | BP007, BP002, BP003, BP008, BP009
Pre-Requisites
Boundaries | Processing ends when Meter Point is de-energised, disconnected and Services De-Appointed and meter removed
Test Case Variables | (1) smart, single MPAN, same-day (2) traditional, single MPAN, same-day (3) advanced, single MPAN (No Meter), same-day (4) unmetered, single MPAN, same-day
Mapped Requirements
Exception Codes | NA
Below is a list of all associated test cases to this scenario.
No. | Test Case Id | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 | SITNFT-T2-100-010-Smart | SITNFT-T2-100-010-Smart | Smart Single MPAN, same-day Customer Initiated Disconnection (as per DES138 data specification) | Smart Meter | Single MPAN | same-day
2 | SITNFT-T2-100-020-Trad | SITNFT-T2-100-020-Trad | Traditional Single MPAN with meter, same-day LDSO Initiated Disconnection (as per DES138 data specification) where the Related MPAN has been un-related | Traditional Meter | Single MPAN | same-day
3 | SITNFT-T2-100-030-Adv | SITNFT-T2-100-030-Adv | Advanced Single MPAN with no meter, same-day LDSO Initiated Disconnection (as per DES138 data specification) | Advanced Meter | Single MPAN | same-day
4 | SITNFT-T2-100-040-UM | SITNFT-T2-100-040-UM | Unmetered Single MPAN , same-day LDSO Initiated Disconnection (as per DES138 data specification) | Unmetered | Single MPAN | same-day
Back to List of
Test Scenarios

## SITNFT-T2-100-010-Smart
No. |  | Test Case Id |  |  |  |  | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 |  | SITNFT-T2-100-010-Smart |  |  |  |  | SITNFT-T2-100-010-Smart | Smart Single MPAN, same-day Customer Initiated Disconnection (as per DES138 data specification) | Smart Meter | Single | same-day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0840 - Customer Initiated Disconnection (Smart) | De-energisation - Start | 1 | BP008 | 10 | MHHS-BR-SU-060 | SUPC | D0134 | N/A | SMSC | SUPC sends D0134 to the SMSC |  | Y
|  | 2 | BP008 | 15 | MHHS-BR-LD-022 | SUPC | D0134 | N/A | SMSC | Smart Metering Service receives D0134 (Request Energisation Status Change). |  | Y
IF-041 Interface between SMSC Participant and DIP is disable/configured to return error
|  | 3 | BP008 | 30 35 | MHHS-BR-MS-043 MHHS-BR-MS-044 | SMSC | IF-041 | N/A | DIP | SMSC sends IF-041 to DIP - Capture cumulative reads | http 202 response to DIP | Y
Evidence of IF-041 Queuing/Buffering
IF-041 Interface between SMSI Participant and DIP is enabled/configured to return process as normal
|  | 4 | BP008 | 36 | MHHS-BR-MS-043 MHHS-BR-MS-044 | DIP | PUB-041 | N/A | SUPC, LDSO & SDSC | DIP sends PUB-041 to SUPC, LDSO & SDSC |  | N
|  | 5 | BP008 | 170 | MHHS-BR-SU-063 | DIP | PUB-041 | [ReadingEnergisationChg] | SUPC | Supplier (Currently appointed) receives PUB-041 from DIP for a Smart change of Energisation | Supplier receives PUB-041 ReadingEnergisationChg, confirms Meter Reading prior to energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 6 | BP008 | 171 | MHHS-BR-LD-025 | DIP | PUB-041 | [ReadingEnergisationChg] | LDSO | LDSO receives PUB-041 from DIP for a Smart change of Energisation | LDSO receives PUB-041 ReadingEnergisationChg, confirms Meter Reading prior to energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 7 | BP008 | 150 | MHHS-BR-DS-111 | DIP | PUB-041 | [ReadingEnergisationChg] | SDSC | Smart Data Service receives PUB-041 from DIP for a Smart change of Energisation | Data Service receives PUB-041 ReadingEnergisationChg, confirms Meter Reading prior to energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-007 Interface between SMSC Participant and DIP is disable/configured to return error
|  | 8 | BP008 | 45 80 | MHHS-BR-MS-045.1 MHHS-BR-MS-049 | SMSC | IF-007 | [EnergisationStatusChange] | DIP | SMSC sends IF-007 to the DIP. | http 202 response to DIP | Y
Evidence of IF-007 Queuing/Buffering
IF-007 Interface between SMSI Participant and DIP is enabled/configured to return process as normal
|  | 9 | BP008 | 90 | MHHS-BR-MS-049 | DIP | PUB-007 | [EnergisationStatusChange] | REGS | DIP sends PUB-007 [EnergisationStatusChange] to REGS |  | N
|  | 10 | BP008 | 105 110 | MHHS-BR-RS-104 MHHS-BR-RS-105 | DIP | PUB-007 | [EnergisationStatusChange] | REGS | REGS receives PUB-007 [EnergisationStatusChange] from DIP | REGS receives PUB-007 EnergisationStatusChange, confirms request for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-008 Interface between Registration Participant and DIP is disable/configured to return error
|  | 11 | BP008 | 115 | MHHS-BR-RS-107 | REGS | IF-008 | [EnergisationStatusChange] | DIP | REGS sends IF-008 to DIP | http 202 response to DIP | Y
Evidence of IF-008 Queuing/Buffering
IF-008 Interface between Registration Participant and DIP is enabled/configured to return process as normal
|  | 12 | BP008 | 125 |  | DIP | PUB-008 | [EnergisationStatusChange] | SMSC, SUPC, LDSO, SDSC, MDS, EES | DIP sends PUB-008 [EnergisationStatusChange] to SMSC, SUPC, LDSO, SDSC, MDS, EES |  | N
|  | 13 | BP008 | 117 | MHHS-BR-RS-109 | DIP | PUB-008 | [EnergisationStatusChange] | SMSC | SMSC - Metering Service (Currently Appointed) receives PUB-008 | Meter Service receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 14 | BP008 | 175 | MHHS-BR-SU-064 | DIP | PUB-008 | [EnergisationStatusChange] | SUPC | Supplier receives PUB-008. | Supplier receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 15 | BP008 | 165 | MHHS-BR-LD-024 | DIP | PUB-008 | [EnergisationStatusChange] | LDSO | LDSO receives PUB-008. | LDSO receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 16 | BP008 | 155 | MHHS-BR-DS-106 | DIP | PUB-008 | [EnergisationStatusChange] | SDSC | SDS (Current) receives PUB-008. | Data Service receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 17 | BP008 | 160 | MDS | DIP | PUB-008 | [EnergisationStatusChange] | MDS | MDS receives PUB-008. | MDS receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| De-energisation - End | 18 | BP008 | 156 | MHHS-BR-EES-016.3 | DIP | PUB-008 | [EnergisationStatusChange] | EES | EES receives PUB-008. | EES receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Change of Metering - MS accepts request for meter removal | 19 | BP009 | 20 | MHHS-BR-SU-066 | SUPC | D0142 | N/A | SMSC | Supplier issues out D0142 to Metering service requesting Meter removal works to be taken out |  | Y
|  | 20 | BP009 | 30 40 | MHHS-BR-MS-051 MHHS-BR-MS-056 | SMSC | D0142 | N/A | N/A | Metering Service (Currently Appointed) receives D0142 via the DTN or the Service Provider Portal accepts and Metering will complete the required metering works requested by Supplier and update their systems to reflect the changes made. |  | Y
|  | 21 | BP009 | 60 | MHHS-BR-MS-061 | SMSC | IF-041 | [ReadingRemv] | DIP | SMSC sends IF-041 to DIP | http 202 response from DIP | Y
|  | 22 | BP009 | 60 | MHHS-BR-MS-061 | DIP | PUB-041 | [ReadingRemv] | SUPC | DIP sends PUB-041 to Supplier, LDSO and Smart Data Service |  | N
|  | 23 | BP009 | 220 215 | MHHS-BR-SU-072 MHHS-BR-SU-071 | DIP | PUB-041 | [ReadingRemv] | SUPC | Supplier receives PUB-041 from DIP | Supplier receives PUB-041 Meter Removal Read and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 24 | BP009 | 190 | MHHS-BR-LD-029 | DIP | PUB-041 | [ReadingRemv] | LDSO | LDSO receives PUB-041 from DIP | LDSO receives PUB-041 Meter Removal Read and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 25 | BP009 | 180 | MHHS-BR-DS-118 | DIP | PUB-041 | [ReadingRemv] | SDSO | Data Service (Outgoing) receives PUB-041 from DIP | Data Service (Outgoing) receives PUB-041 Meter Removal Read and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-005 Interface between SMSC and DIP is disable/configured to return error
|  | 26 | BP009 | 55 | MHHS-BR-MS-058 MHHS-BR-MS-058.3 | SMSC | IF-005 | [MeterRemoval] | DIP | SMSC sends IF-005 to DIP | http 202 response from DIP | Y
Evidence of IF-005 Queuing/Buffering
IF-005 Interface between SMSC Participant and DIP is enabled/configured to return process as normal
|  | 27 | BP009 | 55 | MHHS-BR-MS-058 MHHS-BR-MS-058.3 | DIP | PUB-005 | [MeterRemoval] | REGS | DIP sends PUB-005 to the REGS |  | N
|  | 28 | BP009 | 95 100 125 | MHHS-BR-RS-108 MHHS-BR-RS-108.1 MHHS-BR-RS-109 | DIP | PUB-005 | [MeterRemoval] | REGS | REGS receives PUB-005 and updates Metering and new registration data passes validation rules will update their systems with the new metering details and update all relevant systems. | REGS receives PUB-005 Updating Meter Removal and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-006 Interface between Registration and DIP is disable/configured to return error
|  | 29 | BP009 | 195 | MHHS-BR-LD-030 | REGS | IF-006 | [MeterRemoval] | DIP | REGS sends IF-006 to DIP | http 202 response from DIP | Y
Evidence of IF-006 Queuing/Buffering
IF-006 Interface between Registration Participant and DIP is enabled/configured to return process as normal
|  | 30 | BP009 | 140 | MHHS-BR-RS-111 | DIP | PUB-006 | [MeterRemoval] | SUPC, LDSO, EES, SMSC & SDSO | DIP sends PUB-006 to the SUPC, LDSO, EES, SMSC & SDSO. |  | N
|  | 31 | BP009 | 200 | MHHS-BR-SU-069 | DIP | PUB-006 | [MeterRemoval] | SUPC | Supplier receives registration update through PUB-006 | Supplier receives PUB-006 Notifying Meter Technical information of the back of Meter Removal and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 32 | BP009 | 195 | MHHS-BR-LD-030 | DIP | PUB-006 | [MeterRemoval] | LDSO | LDSO receives registration update through PUB-006 | LDSO receives PUB-006 Notifying Meter Technical information of the back of Meter Removal and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 33 | BP009 | 186 | MHHS-BR-EES-016.3 | DIP | PUB-006 | [MeterRemoval] | SDSC | Data Service receives registration update through PUB-006 | Data Service receives PUB-006 Notifying Meter Technical information of the back of Meter Removal and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 34 | BP009 | 160 170 | MHHS-BR-MS-073.1 MHHS-BR-MS-059 | DIP | PUB-006 | [MeterRemoval] | EES | EES receives registration update through PUB-006 | EES receives PUB-006 Notifying Meter Technical information of the back of Meter Removal and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Change of Metering - MS completes removal of the Meter | 35 | BP009 | 185 | MHHS-BR-DS-117 | DIP | PUB-006 | [MeterRemoval] | SMSC | Metering Service receives registration update through PUB-006 | Metering Service receives PUB-006 Notifying Meter Technical information of the back of Meter Removal and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| LDSO Disconnects Meter Point | 36 | BP007 | 65 | MHHS-BR-LD-013 MHHS-BR-LD-014 MHHS-BR-LD-016 MHHS-BR-LD-017 MHHS-BR-LD-018 | LDSO | Internal DB03 |  | REGS | LDSO disconnects Meter Point and sends an Internal DB03 to the Registration Service | Hypothetically at this stage the customer would contact the LDSO to disconnect meter point through normal BAU practice | Y
|  | 37 | BP007 | 70 | MHHS-BR-RS-097 | LDSO | Internal DB03 |  | REGS | REGS receives the Internal DB03 | REGS receives Internal DB03 and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-009 Interface between Registration Participant and DIP is disable/configured to return error
| RS sends out LDSO Disconnection Notifications | 38 | BP007 | 70 | MHHS-BR-RS-098 | REGS | IF-009 | [MPANDisconnection] | DIP | REGS sends IF-009 to DIP | http 202 response from DIP | Y
Evidence of IF-009 Queuing/Buffering
IF-009 Interface between Registration Participant and DIP is enabled/configured to return process as normal
|  | 39 | BP007 | 85 |  | DIP | PUB-009 | [MPANDisconnection] | SUPC, LDSO, EES | DIP sends PUB-009 to SUP (Current), LDSO and EES to confirm the Meter Point has been disconnected |  | N
|  | 40 | BP007 | 95 | MHHS-BR-SU-056 MHHS-BR-SU-057 | DIP | PUB-009 | [MPANDisconnection] | SUPC | SUP (Current) receives PUB-009. | Supplier (Current) receives PUB-009 with details of the Meter Point Disconnection and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 41 | BP007 | 86 | MHHS-BR-LD-020 | DIP | PUB-009 | [MPANDisconnection] | LDSO | LDSO receives PUB-009. | LDSO receives PUB-009 with details of the Meter Point Disconnection and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 42 | BP007 | 87 | MHHS-BR-EES-016.3 | DIP | PUB-009 | [MPANDisconnection] | EES | EES receives PUB-009. | EES receives PUB-009 with details of the Meter Point Disconnection and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-050 Interface between Registration Participant and DIP is disable/configured to return error
| RS sends out EES MPAN Status Change Update | 43 | BP007 | 70 | MHHS-BR-RS-099 | REGS | IF-050 | [MPStatusChange] | DIP | REGS sends IF-050 to DIP | http 202 response from DIP | Y
Evidence of IF-050 Queuing/Buffering
IF-050 Interface between Registration Participant and DIP is enabled/configured to return process as normal
|  | 44 | BP007 | 126 |  | DIP | PUB-050 | [MPStatusChange] | EES | DIP sends PUB-050 to EES to confirm the MPAN status change |  | N
|  | 45 | BP007 | 127 |  | DIP | PUB-050 | [MPStatusChange] | EES | EES receives PUB-050. | EES receives PUB-050 with details of the MPAN Status Change and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS sends out CSS Simulated MPAN Status Change Update | 46 | BP007 | 70 | MHHS-BR-RS-099 | REGS | CSS Simulated 00300 | N/A | CSS Simulated | REGS sends CSS Simulated 00300 to CSS Simulated |  | Y
|  | 47 | BP007 | 115 | CSS Simulated | REGS | CSS Simulated 00300 | N/A | CSS Simulated | CSS Simulated receives CSS Simulated 00300 and Terminates RMP |  | Y
| Deactivation Formal Request | 48 | BP007 | 96 | MHHS-BR-SU-057 | SUPC | CSS Simulated 01900 | N/A | CSS Simulated | SUP (Current) sends Registration Deactivation Request CSS Simulated 01900 to CSS Simulated |  | Y
|  | 49 | BP007 | 120 | CSS Simulated | SUPC | CSS Simulated 01900 | N/A | CSS Simulated | CSS Simulated receives CSS Simulated 01900 and performs Registration Deactivation |  | Y
| CSS Simulated Registration Deactivation | 50 | BP007 | 121 | CSS Simulated | CSS Simulated | CSS Simulated 02860 | N/A | REGS | CSS Simulated performs Registration Deactivation and sends CSS Simulated 02860 to REGS |  | Y
|  | 51 | BP007 | 121 | CSS Simulated | CSS Simulated | CSS Simulated 02370 | N/A | SUPC | CSS Simulated Sends CSS Simulated 02370 to Supplier |  | Y
|  | 52 | BP007 | 160 | MHHS-BR-SU-058 | CSS Simulated | CSS Simulated 02370 | N/A | SUPC | Supplier receives CSS Simulated 02370 confirmation of registration deactivation for an MPAN |  | Y
|  | 53 | BP007 | 125 | MHHS-BR-RS-100 MHHS-BR-RS-101 | CSS Simulated | CSS Simulated 02860 | N/A | REGS | REGS receives CSS Simulated 02860 and updates Registration | REGS receives CSS Simulated 02860 Registration Update and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 54 | BP007 | 155 | MHHS-BR-RS-102 MHHS-BR-RS-103 MHHS-BR-RS-102.1 | CSS Simulated | CSS Simulated 02860 | N/A | REGS | On receipt of the CSS Simulated deactivation notification the Registration Service will send out the de-appointment notification to all service providers | REGS receives CSS Simulated 02860 Registration Update and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS sends out CSS Simulated DeRegistration Notification | 55 | BP007 | 125 | MHHS-BR-RS-101 MHHS-BR-RS-102.1 | REGS | IF-009 | [CSS Simulated DeRegistration] | DIP | REGS sends IF-009 to DIP | http 202 response from DIP | Y
|  | 56 | BP007 | 130 |  | DIP | PUB-009 | [CSS Simulated DeRegistration] | SUPC, LDSO, MDS and EES | DIP sends PUB-009 to SUPC, LDSO, MDS and EES to confirm the CSS Simulated De-Registration |  | N
|  | 57 | BP007 | 137 |  | DIP | PUB-009 | [CSS Simulated DeRegistration] | SUPC | SUPC receives PUB-009. | Supplier (Current) receives PUB-009 with details of the CSS Simulated De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 58 | BP007 | 136 | MHHS-BR-LD-020.1 | DIP | PUB-009 | [CSS Simulated DeRegistration] | LDSO | LDSO receives PUB-009. | LDSO receives PUB-009 with details of the CSS Simulated De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 59 | BP007 | 135 | Central Settlements | DIP | PUB-009 | [CSS Simulated DeRegistration] | MDS | MDS receives PUB-009. | MDS receives PUB-009 with details of the CSS Simulated De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 60 | BP007 | 131 | MHHS-BR-EES-016.3 | DIP | PUB-009 | [CSS Simulated DeRegistration] | EES | EES receives PUB-009. | EES receives PUB-009 with details of the CSS Simulated De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-037 Interface between Registration Participant and DIP is disable/configured to return error
| De-appoint Current Metering Service | 61 | BP007 | 155 | MHHS-BR-RS-102 | REGS | IF-037 | [MSDeApp] | DIP | REGS sends IF-037 to DIP | http 202 response from DIP | Y
Evidence of IF-037 Queuing/Buffering
IF-037 Interface between Registration Participant and DIP is enabled/configured to return process as normal
|  | 62 | BP007 | 145 |  | DIP | PUB-037 | [MSDeApp] | SMSC, SUPC, LDSO & EES | DIP sends PUB-037 De-Appoints Current Metering Service with a De-Appointment Reason Code = "DEREG" (RMP Terminated by CSS Simulated ) to Metering Service (Current), Supplier(Outgoing), LDSO & EES |  | N
|  | 63 | BP007 | 150 | MHHS-BR-MS-040 | DIP | PUB-037 | [MSDeApp] | SMSC | Metering Service (Current) receives PUB-037 confirming MS De-appointment | Metering Service (Current) receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 64 | BP007 | 157 | MHHS-BR-SU-059 | DIP | PUB-037 | [MSDeApp] | SUPC | Outgoing Supplier receives PUB-037 confirming MS De-appointment | Supplier (Current) receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 65 | BP007 | 156 | MHHS-BR-LD-021 | DIP | PUB-037 | [MSDeApp] | LDSO | LDSO receives PUB-037 confirming MS De-appointment | LDSO receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 66 | BP007 |  | MHHS-BR-EES-016.3 | DIP | PUB-037 | [MSDeApp] | EES | EES receives PUB-037 confirming MS De-appointment | EES receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| De-appoint Current Data Service | 67 | BP007 | 155 | MHHS-BR-RS-102 | REGS | IF-037 | [DSDeApp] | DIP | REGS sends IF-037 to DIP | http 202 response from DIP | Y
|  | 68 | BP007 | 145 |  | DIP | PUB-037 | [DSDeApp] | SDSC, SUPC, LDSO, EES and MDS | DIP sends PUB-037 - De-Appoints Current Data Service with a De-Appointment Reason Code = "DEREG" (RMP Terminated by CSS Simulated ) to SDSC, SUPC, LDSO, EES and MDS |  | N
|  | 69 | BP007 | 140 | MHHS-BR-DS-104 MHHS-BR-DS-105 | DIP | PUB-037 | [DSDeApp] | SDSC | Smart Data Service (Outgoing) receives PUB-037 | Smart Data Services Outgoing receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 70 | BP007 | 157 | MHHS-BR-SU-059 | DIP | PUB-037 | [DSDeApp] | SUPC | Supplier (Outgoing) receives PUB-037 | Supplier (Current) receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 71 | BP007 | 156 | MHHS-BR-LD-021 | DIP | PUB-037 | [DSDeApp] | LDSO | LDSO receives PUB-037. | LDSO receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 72 | BP007 |  | MHHS-BR-EES-016.3 | DIP | PUB-037 | [DSDeApp] | EES | EES receives PUB-037. | EES receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 73 | BP007 |  | DES138 | DIP | PUB-037 | [DSDeApp] | MDS | MDS receives PUB-037. | MDS receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y

## SITNFT-T2-100-020-Trad
No. |  | Test Case Id |  |  |  |  | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
2 |  | SITNFT-T2-100-020-Trad |  |  |  |  | SITNFT-T2-100-020-Trad | Traditional Single MPAN with meter, same-day LDSO Initiated Disconnection (as per DES138 data specification) where the Related MPAN has been un-related | Traditional Meter | Single | same-day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0840 - LDSO Initiated Disconnection - Metered Sites (Traditional) | De-energisation - Start | 1 | BP008 | 10 | MHHS-BR-SU-060 | SUPC | D0134 | N/A | SMSC | SUPC sends D0134 to the SMSC |  | Y
|  | 2 | BP008 | 15 | MHHS-BR-LD-022 | SUPC | D0134 | N/A | SMSC | Smart Metering Service receives D0134 (Request Energisation Status Change). |  | Y
|  | 3 | BP008 | 50 | MHHS-BR-MS-046 | SMSC | D010 | N/A | SDSC | SMSC sends D010 to the SDSC |  | Y
|  | 4 | BP008 | 145 | MHHS-BR-DS-108 MHHS-BR-DS-109 MHHS-BR-DS-110 MHHS-BR-DS-112 | SMSC | D010 | N/A | SDSC | SDSC receives D010 from the MSSC |  | Y
|  | 5 | BP008 | 145 | MHHS-BR-DS-108 MHHS-BR-DS-109 MHHS-BR-DS-110 MHHS-BR-DS-112 | SDSC | D010 | N/A | SUPC | SDSC sends D010 to the SUPC and LDSO |  | Y
|  | 6 | BP008 | 180 | MHHS-BR-SU-065 | SDSC | D010 | N/A | SUPC | SUPC receives D010 from the SDSC |  | Y
|  | 7 | BP008 | 172 | MHHS-BR-LD-026 | SDSC | D010 | N/A | LDSO | LDSO receives D010 from the SDSC |  | Y
IF-007 Interface between SMSC Participant and DIP is disable/configured to return error
|  | 8 | BP008 | 45 80 | MHHS-BR-MS-045.1 MHHS-BR-MS-049 | SMSC | IF-007 | [EnergisationStatusChange] | DIP | SMSC sends IF-007 to the DIP. | http 202 response to DIP | Y
Evidence of IF-007 Queuing/Buffering
IF-007 Interface between SMSI Participant and DIP is enabled/configured to return process as normal
|  | 9 | BP008 | 90 | MHHS-BR-MS-049 | DIP | PUB-007 | [EnergisationStatusChange] | REGS | DIP sends PUB-007 [EnergisationStatusChange] to REGS |  | N
|  | 10 | BP008 | 105 110 | MHHS-BR-RS-104 MHHS-BR-RS-105 | DIP | PUB-007 | [EnergisationStatusChange] | REGS | REGS receives PUB-007 [EnergisationStatusChange] from DIP | REGS receives PUB-007 EnergisationStatusChange, confirms request for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-008 Interface between Registration Participant and DIP is disable/configured to return error
|  | 11 | BP008 | 115 | MHHS-BR-RS-107 | REGS | IF-008 | [EnergisationStatusChange] | DIP | REGS sends IF-008 to DIP | http 202 response to DIP | Y
Evidence of IF-008 Queuing/Buffering
IF-008 Interface between Registration Participant and DIP is enabled/configured to return process as normal
|  | 12 | BP008 | 125 |  | DIP | PUB-008 | [EnergisationStatusChange] | SMSC, SUPC, LDSO, SDSC, MDS, EES | DIP sends PUB-008 [EnergisationStatusChange] to SMSC, SUPC, LDSO, SDSC, MDS, EES |  | N
|  | 13 | BP008 | 117 | MHHS-BR-RS-109 | DIP | PUB-008 | [EnergisationStatusChange] | SMSC | SMSC - Metering Service (Currently Appointed) receives PUB-008 | Meter Service receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 14 | BP008 | 175 | MHHS-BR-SU-064 | DIP | PUB-008 | [EnergisationStatusChange] | SUPC | Supplier receives PUB-008. | Supplier receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 15 | BP008 | 165 | MHHS-BR-LD-024 | DIP | PUB-008 | [EnergisationStatusChange] | LDSO | LDSO receives PUB-008. | LDSO receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 16 | BP008 | 155 | MHHS-BR-DS-106 | DIP | PUB-008 | [EnergisationStatusChange] | SDSC | SDS (Current) receives PUB-008. | Data Service receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 17 | BP008 | 160 | MDS | DIP | PUB-008 | [EnergisationStatusChange] | MDS | MDS receives PUB-008. | MDS receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| De-energisation - End | 18 | BP008 | 156 | MHHS-BR-EES-016.3 | DIP | PUB-008 | [EnergisationStatusChange] | EES | EES receives PUB-008. | EES receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| LDSO Initiated Disconnection | 19 | BP007 | 32 | MHHS-BR-LD-015 | LDSO | BAU | BAU | LDSO | LDSO may need to disconnect sites in emergency scenarios. Where an LDSO has initiated a disconnection in cases of emergency they must where possible update the Metering Service of the meter removal |  | Y
| LDSO Disconnects Meter Point | 20 | BP007 | 40 | MHHS-BR-LD-015 MHHS-BR-LD-018 | LDSO | Internal DB03 |  | REGS | The LDSO physically disconnects the connection to the property and updates the Registration Service |  | Y
|  | 21 | BP007 | 70 | MHHS-BR-RS-097 | LDSO | Internal DB03 |  | REGS | REGS receives the Internal DB03 | REGS receives Internal DB03 and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-009 Interface between Registration Participant and DIP is disable/configured to return error
| RS sends out LDSO Disconnection Notifications | 22 | BP007 | 70 | MHHS-BR-RS-098 | REGS | IF-009 | [MPANDisconnection] | DIP | REGS sends IF-009 to DIP | http 202 response from DIP | Y
Evidence of IF-009 Queuing/Buffering
IF-009 Interface between Registration Participant and DIP is enabled/configured to return process as normal
|  | 23 | BP007 | 85 |  | DIP | PUB-009 | [MPANDisconnection] | SUPC, LDSO, EES | DIP sends PUB-009 to SUP (Current), LDSO and EES to confirm the Meter Point has been disconnected |  | N
|  | 24 | BP007 | 95 | MHHS-BR-SU-056 MHHS-BR-SU-057 | DIP | PUB-009 | [MPANDisconnection] | SUPC | SUP (Current) receives PUB-009. | Supplier (Current) receives PUB-009 with details of the Meter Point Disconnection and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 25 | BP007 | 86 | MHHS-BR-LD-020 | DIP | PUB-009 | [MPANDisconnection] | LDSO | LDSO receives PUB-009. | LDSO receives PUB-009 with details of the Meter Point Disconnection and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 26 | BP007 | 87 | MHHS-BR-EES-016.3 | DIP | PUB-009 | [MPANDisconnection] | EES | EES receives PUB-009. | EES receives PUB-009 with details of the Meter Point Disconnection and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-050 Interface between Registration Participant and DIP is disable/configured to return error
| RS sends out EES MPAN Status Change Update | 27 | BP007 | 70 | MHHS-BR-RS-099 | REGS | IF-050 | [MPStatusChange] | DIP | REGS sends IF-050 to DIP | http 202 response from DIP | Y
Evidence of IF-050 Queuing/Buffering
IF-050 Interface between Registration Participant and DIP is enabled/configured to return process as normal
|  | 28 | BP007 | 126 |  | DIP | PUB-050 | [MPStatusChange] | EES | DIP sends PUB-050 to EES to confirm the MPAN status change |  | N
|  | 29 | BP007 | 127 |  | DIP | PUB-050 | [MPStatusChange] | EES | EES receives PUB-050. | EES receives PUB-050 with details of the MPAN Status Change and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS sends out CSS Simulated MPAN Status Change Update | 30 | BP007 | 70 | MHHS-BR-RS-099 | REGS | CSS Simulated 00300 | N/A | CSS Simulated | REGS sends CSS Simulated 00300 to CSS Simulated |  | Y
|  | 31 | BP007 | 115 | CSS Simulated | REGS | CSS Simulated 00300 | N/A | CSS Simulated | CSS Simulated receives CSS Simulated 00300 and Terminates RMP |  | Y
| Deactivation Formal Request | 32 | BP007 | 96 | MHHS-BR-SU-057 | SUPC | CSS Simulated 01900 | N/A | CSS Simulated | SUP (Current) sends Registration Deactivation Request CSS Simulated 01900 to CSS Simulated |  | Y
|  | 33 | BP007 | 120 | CSS Simulated | SUPC | CSS Simulated 01900 | N/A | CSS Simulated | CSS Simulated receives CSS Simulated 01900 and performs Registration Deactivation |  | Y
| CSS Simulated Registration Deactivation | 34 | BP007 | 121 | CSS Simulated | CSS Simulated | CSS Simulated 02860 | N/A | REGS | CSS Simulated performs Registration Deactivation and sends CSS Simulated 02860 to REGS |  | Y
|  | 35 | BP007 | 125 | MHHS-BR-RS-100 MHHS-BR-RS-101 | CSS Simulated | CSS Simulated 02860 | N/A | REGS | REGS receives CSS Simulated 02860 and updates Registration | REGS receives CSS Simulated 02860 Registration Update and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 36 | BP007 | 155 | MHHS-BR-RS-102 MHHS-BR-RS-103 MHHS-BR-RS-102.1 | CSS Simulated | CSS Simulated 02860 | N/A | REGS | On receipt of the CSS Simulated deactivation notification the Registration Service will send out the de-appointment notification to all service providers | REGS receives CSS Simulated 02860 Registration Update and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS sends out CSS Simulated DeRegistration Notification | 37 | BP007 | 125 | MHHS-BR-RS-101 MHHS-BR-RS-102.1 | REGS | IF-009 | [CSS Simulated DeRegistration] | DIP | REGS sends IF-009 to DIP | http 202 response from DIP | Y
|  | 38 | BP007 | 130 | MHHS-BR-RS-101 | DIP | PUB-009 | [CSS Simulated DeRegistration] | SUPC, LDSO, MDS and EES | DIP sends PUB-009 to SUPC, LDSO, Central Settlements and EES to confirm the CSS Simulated De-Registration |  | N
|  | 39 | BP007 | 137 |  | DIP | PUB-009 | [CSS Simulated DeRegistration] | SUPC | SUPC receives PUB-009. | Supplier (Current) receives PUB-009 with details of the CSS Simulated De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 40 | BP007 | 136 | MHHS-BR-LD-020.1 | DIP | PUB-009 | [CSS Simulated DeRegistration] | LDSO | LDSO receives PUB-009. | LDSO receives PUB-009 with details of the CSS Simulated De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 41 | BP007 | 135 | MDS | DIP | PUB-009 | [CSS Simulated DeRegistration] | MDS | MDS receives PUB-009. | MDS receives PUB-009 with details of the CSS Simulated De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 42 | BP007 | 131 | MHHS-BR-EES-016.3 | DIP | PUB-009 | [CSS Simulated DeRegistration] | EES | EES receives PUB-009. | EES receives PUB-009 with details of the CSS Simulated De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-037 Interface between Registration Participant and DIP is disable/configured to return error
| De-appoint Current Metering Service | 43 | BP007 | 155 | MHHS-BR-RS-102 | REGS | IF-037 | [MSDeApp] | DIP | REGS sends IF-037 to DIP | http 202 response from DIP | Y
Evidence of IF-037 Queuing/Buffering
IF-037 Interface between Registration Participant and DIP is enabled/configured to return process as normal
|  | 44 | BP007 | 145 |  | DIP | PUB-037 | [MSDeApp] | SMSC, SUPC, LDSO & EES | DIP sends PUB-037 De-Appoints Current Metering Service with a De-Appointment Reason Code = "DEREG" (RMP Terminated by CSS Simulated ) to Metering Service (Current), Supplier(Outgoing), LDSO & EES |  | N
|  | 45 | BP007 | 150 | MHHS-BR-MS-040 | DIP | PUB-037 | [MSDeApp] | SMSC | Metering Service (Current) receives PUB-037 confirming MS De-appointment | Metering Service (Current) receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 46 | BP007 | 157 | MHHS-BR-SU-059 | DIP | PUB-037 | [MSDeApp] | SUPC | Outgoing Supplier receives PUB-037 confirming MS De-appointment | Supplier (Current) receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 47 | BP007 | 156 | MHHS-BR-LD-021 | DIP | PUB-037 | [MSDeApp] | LDSO | LDSO receives PUB-037 confirming MS De-appointment | LDSO receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 48 | BP007 |  | MHHS-BR-EES-016.3 | DIP | PUB-037 | [MSDeApp] | EES | EES receives PUB-037 confirming MS De-appointment | EES receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| De-appoint Current Data Service | 49 | BP007 | 155 | MHHS-BR-RS-102 | REGS | IF-037 | [DSDeApp] | DIP | REGS sends IF-037 to DIP | http 202 response from DIP | Y
|  | 50 | BP007 | 145 |  | DIP | PUB-037 | [DSDeApp] | SDSC, SUPC, LDSO, EES and MDS | DIP sends PUB-037 - De-Appoints Current Data Service with a De-Appointment Reason Code = "DEREG" (RMP Terminated by CSS Simulated ) to SDSC, SUPC, LDSO, EES and MDS |  | N
|  | 51 | BP007 | 140 | MHHS-BR-DS-104 MHHS-BR-DS-105 | DIP | PUB-037 | [DSDeApp] | SDSC | Smart Data Service (Outgoing) receives PUB-037 | Smart Data Services Outgoing receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 52 | BP007 | 157 | MHHS-BR-SU-059 | DIP | PUB-037 | [DSDeApp] | SUPC | Supplier (Outgoing) receives PUB-037 | Supplier (Current) receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 53 | BP007 | 156 | MHHS-BR-LD-021 | DIP | PUB-037 | [DSDeApp] | LDSO | LDSO receives PUB-037. | LDSO receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 54 | BP007 |  | MHHS-BR-EES-016.3 | DIP | PUB-037 | [DSDeApp] | EES | EES receives PUB-037. | EES receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 55 | BP007 |  | DES138 | DIP | PUB-037 | [DSDeApp] | MDS | MDS receives PUB-037. | MDS receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Change of Metering - MS accepts request for meter removal | 56 | BP009 | 20 | MHHS-BR-SU-066 | SUPC | D0142 | N/A | SMSC | Supplier issues out D0142 to Metering service requesting Meter removal works to be taken out |  | Y
|  | 57 | BP009 | 30 40 | MHHS-BR-MS-051 MHHS-BR-MS-056 | SMSC | D0142 | N/A | N/A | Metering Service (Currently Appointed) receives D0142 via the DTN or the Service Provider Portal accepts and Metering will complete the required metering works requested by Supplier and update their systems to reflect the changes made. |  | Y
|  | 58 | BP008 | 50 | MHHS-BR-MS-046 | SMSC | D010 | N/A | SDSO | SMSC sends D010 to the SDSC |  | Y
|  | 59 | BP008 | 145 | MHHS-BR-DS-108 MHHS-BR-DS-109 MHHS-BR-DS-110 MHHS-BR-DS-112 | SMSC | D010 | N/A | SDSO | SDSO receives D010 from the MSSC |  | Y
|  | 60 | BP008 | 145 | MHHS-BR-DS-108 MHHS-BR-DS-109 MHHS-BR-DS-110 MHHS-BR-DS-112 | SDSO | D010 | N/A | SUPC | SDSO sends D010 to the SUPC and LDSO |  | Y
|  | 61 | BP008 | 180 | MHHS-BR-SU-065 | SDSO | D010 | N/A | SUPC | SUPC receives D010 from the SDSC |  | Y
|  | 62 | BP008 | 172 | MHHS-BR-LD-026 | SDSO | D010 | N/A | LDSO | LDSO receives D010 from the SDSC |  | Y
IF-005 Interface between SMSC and DIP is disable/configured to return error
|  | 63 | BP009 | 55 | MHHS-BR-MS-058 MHHS-BR-MS-058.3 | SMSC | IF-005 | [MeterRemoval] | DIP | SMSC sends IF-005 to DIP | http 202 response from DIP | Y
Evidence of IF-005 Queuing/Buffering
IF-005 Interface between SMSC Participant and DIP is enabled/configured to return process as normal
|  | 64 | BP009 | 55 | MHHS-BR-MS-058 MHHS-BR-MS-058.3 | DIP | PUB-005 | [MeterRemoval] | REGS | DIP sends PUB-005 to the REGS |  | N
|  | 65 | BP009 | 95 100 125 | MHHS-BR-RS-108 MHHS-BR-RS-108.1 MHHS-BR-RS-109 | DIP | PUB-005 | [MeterRemoval] | REGS | REGS receives PUB-005 and updates Metering and new registration data passes validation rules will update their systems with the new metering details and update all relevant systems. | REGS receives PUB-005 Updating Meter Removal and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-006 Interface between Registration and DIP is disable/configured to return error
|  | 66 | BP009 | 195 | MHHS-BR-LD-030 | REGS | IF-006 | [MeterRemoval] | DIP | REGS sends IF-006 to DIP | http 202 response from DIP | Y
Evidence of IF-006 Queuing/Buffering
IF-006 Interface between Registration Participant and DIP is enabled/configured to return process as normal
|  | 67 | BP009 | 140 | MHHS-BR-RS-111 | DIP | PUB-006 | [MeterRemoval] | SUPC, LDSO, EES, SMSC & SDSO | DIP sends PUB-006 to the SUPC, LDSO, EES, SMSC & SDSO. |  | N
|  | 68 | BP009 | 200 | MHHS-BR-SU-069 | DIP | PUB-006 | [MeterRemoval] | SUPC | Supplier receives registration update through PUB-006 | Supplier receives PUB-006 Notifying Meter Technical information of the back of Meter Removal and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 69 | BP009 | 195 | MHHS-BR-LD-030 | DIP | PUB-006 | [MeterRemoval] | LDSO | LDSO receives registration update through PUB-006 | LDSO receives PUB-006 Notifying Meter Technical information of the back of Meter Removal and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 70 | BP009 | 186 | MHHS-BR-EES-016.3 | DIP | PUB-006 | [MeterRemoval] | SDSO | Data Service (Outgoing) receives registration update through PUB-006 | Data Service (Outgoing) receives PUB-006 Notifying Meter Technical information of the back of Meter Removal and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 71 | BP009 | 160 170 | MHHS-BR-MS-073.1 MHHS-BR-MS-059 | DIP | PUB-006 | [MeterRemoval] | EES | EES receives registration update through PUB-006 | EES receives PUB-006 Notifying Meter Technical information of the back of Meter Removal and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Change of Metering - MS completes removal of the Meter | 72 | BP009 | 185 | MHHS-BR-DS-117 | DIP | PUB-006 | [MeterRemoval] | SMSC | Metering Service receives registration update through PUB-006 | Metering Service receives PUB-006 Notifying Meter Technical information of the back of Meter Removal and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITNFT-T2-100-030-Adv
No. |  | Test Case Id |  |  |  |  | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
3 |  | SITNFT-T2-100-030-Adv |  |  |  |  | SITNFT-T2-100-030-Adv | Advanced Single MPAN with no meter, same-day LDSO Initiated Disconnection (as per DES138 data specification) | Advanced Meter | Single | same-day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0840 - LDSO Initiated Disconnection - No Meter/Supplier Onsite (Advanced) | De-energisation - Start | 1 | BP008 | 10 | MHHS-BR-SU-060 | SUPC | D0134 | N/A | LDSO | Supplier Sends D0134 requesting change of energisation |  | Y
|  | 2 | BP008 | 15 | MHHS-BR-LD-022 | SUPC | D0134 | N/A | LDSO | LDSO receives D0134 from Supplier |  | Y
|  | 3 | BP008 | 20 | MHHS-BR-LD-023 | LDSO | D0139 | N/A | AMSC | LDSO Issues D0139 to Advanced Metering Service |  | Y
|  | 4 | BP008 | 30 | MHHS-BR-MS-042 | LDSO | D0139 | N/A | AMSC | Advanced Metering Service receives D0139 from LDSO |  | Y
IF-041 Interface between AMSC Participant and DIP is disable/configured to return error
|  | 5 | BP008 | 30 35 | MHHS-BR-MS-043 MHHS-BR-MS-044 | AMSC | IF-041 | N/A | DIP | AMSC sends IF-041 to DIP - Capture cumulative reads | http 202 response to DIP | Y
Evidence of IF-041 Queuing/Buffering
IF-041 Interface between AMSC Participant and DIP is enabled/configured to return process as normal
IF-007 Interface between AMSC Participant and DIP is disable/configured to return error
|  | 6 | BP008 | 80 | MHHS-BR-MS-049 | AMSC | IF-007 | [EnergisationStatusChange] | DIP | Metering Service Advanced sends IF-007 to DIP | http 202 response to DIP | Y
Evidence of IF-007 Queuing/Buffering
IF-007 Interface between AMSC Participant and DIP is enabled/configured to return process as normal
|  | 7 | BP008 | 90 |  | DIP | PUB-007 | [EnergisationStatusChange] | REGS | DIP sends PUB-007 to REGS |  | N
|  | 8 | BP008 | 105 110 | MHHS-BR-RS-104 MHHS-BR-RS-105 | DIP | PUB-007 | [EnergisationStatusChange] | REGS | Registration service receives update of energisation status from PUB- 007 | REGS receives PUB-007 EnergisationStatusChange, confirms request for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-008 Interface between Registration Participant and DIP is disable/configured to return error
|  | 9 | BP008 | 115 | MHHS-BR-RS-107 | REGS | IF-008 | [EnergisationStatusChange] | DIP | REGS sends IF-008 to DIP | http 202 response to DIP | Y
Evidence of IF-008 Queuing/Buffering
IF-008 Interface between Registration Participant and DIP is enabled/configured to return process as normal
|  | 10 | BP008 | 125 |  | DIP | PUB-008 | [EnergisationStatusChange] | AMSC | DIP sends PUB-008 to Metering Service Advanced, Supplier, LDSO, Advanced Data Service ,MDS & EES |  | N
|  | 11 | BP008 | 140 | MHHS-BR-MS-050 | DIP | PUB-008 | [EnergisationStatusChange] | AMSC | Metering Service receives PUB-008 | Meter Service receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 12 | BP008 | 175 | MHHS-BR-SU-064 | DIP | PUB-008 | [EnergisationStatusChange] | SUPC | Supplier receives PUB-008. | Supplier receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 13 | BP008 | 165 | MHHS-BR-LD-024 | DIP | PUB-008 | [EnergisationStatusChange] | LDSO | LDSO receives PUB-008. | LDSO receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 14 | BP008 | 155 | MHHS-BR-DS-106 | DIP | PUB-008 | [EnergisationStatusChange] | ADSC | Advanced Data Service receives PUB-008. | Data Service receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 15 | BP008 | 160 | central settlements | DIP | PUB-008 | [EnergisationStatusChange] | MDS | MDS receives PUB-008 | MDS receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| De-energisation - End | 16 | BP008 | 156 | MHHS-BR-EES-016.3 | DIP | PUB-008 | [EnergisationStatusChange] | EES | EES receives PUB-008. | EES receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| LDSO Initiated Disconnection | 17 | BP007 | 35 | MHHS-BR-LD-015 | LDSO | BAU | BAU | LDSO | Where the LDSO have had to disconnect the MPAN due to emergency and there is no meter present. Other scenarios may include MPAN being created in error and no Supplier is active. |  | Y
| LDSO Disconnects Meter Point | 18 | BP007 | 40 | MHHS-BR-LD-015 MHHS-BR-LD-018 | LDSO | Internal DB03 |  | REGS | The LDSO physically disconnects the connection to the property and updates the Registration Service |  | Y
|  | 19 | BP007 | 70 | MHHS-BR-RS-097 | LDSO | Internal DB03 |  | REGS | REGS receives the Internal DB03 | REGS receives Internal DB03 and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-009 Interface between Registration Participant and DIP is disable/configured to return error
| RS sends out LDSO Disconnection Notifications | 20 | BP007 | 70 | MHHS-BR-RS-098 | REGS | IF-009 | [MPANDisconnection] | DIP | REGS sends IF-009 to DIP | http 202 response from DIP | Y
Evidence of IF-009 Queuing/Buffering
IF-009 Interface between Registration Participant and DIP is enabled/configured to return process as normal
|  | 21 | BP007 | 85 |  | DIP | PUB-009 | [MPANDisconnection] | SUPC, LDSO, EES | DIP sends PUB-009 to SUP (Current), LDSO and EES to confirm the Meter Point has been disconnected |  | N
|  | 22 | BP007 | 95 | MHHS-BR-SU-056 MHHS-BR-SU-057 | DIP | PUB-009 | [MPANDisconnection] | SUPC | SUP (Current) receives PUB-009. | Supplier (Current) receives PUB-009 with details of the Meter Point Disconnection and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 23 | BP007 | 86 | MHHS-BR-LD-020 | DIP | PUB-009 | [MPANDisconnection] | LDSO | LDSO receives PUB-009. | LDSO receives PUB-009 with details of the Meter Point Disconnection and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 24 | BP007 | 87 | MHHS-BR-EES-016.3 | DIP | PUB-009 | [MPANDisconnection] | EES | EES receives PUB-009. | EES receives PUB-009 with details of the Meter Point Disconnection and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-050 Interface between Registration Participant and DIP is disable/configured to return error
| RS sends out EES MPAN Status Change Update | 25 | BP007 | 70 | MHHS-BR-RS-099 | REGS | IF-050 | [MPStatusChange] | DIP | REGS sends IF-050 to DIP | http 202 response from DIP | Y
Evidence of IF-050 Queuing/Buffering
IF-050 Interface between Registration Participant and DIP is enabled/configured to return process as normal
|  | 26 | BP007 | 126 |  | DIP | PUB-050 | [MPStatusChange] | EES | DIP sends PUB-050 to EES to confirm the MPAN status change |  | N
|  | 27 | BP007 | 127 |  | DIP | PUB-050 | [MPStatusChange] | EES | EES receives PUB-050. | EES receives PUB-050 with details of the MPAN Status Change and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS sends out CSS Simulated MPAN Status Change Update | 28 | BP007 | 70 | MHHS-BR-RS-099 | REGS | CSS Simulated 00300 | N/A | CSS Simulated | REGS sends CSS Simulated 00300 to CSS Simulated |  | Y
|  | 29 | BP007 | 115 | CSS Simulated | REGS | CSS Simulated 00300 | N/A | CSS Simulated | CSS Simulated receives CSS Simulated 00300 and Terminates RMP |  | Y
| Deactivation Formal Request | 30 | BP007 | 96 | MHHS-BR-SU-057 | SUPC | CSS Simulated 01900 | N/A | CSS Simulated | SUP (Current) sends Registration Deactivation Request CSS Simulated 01900 to CSS Simulated |  | Y
|  | 31 | BP007 | 120 | CSS Simulated | SUPC | CSS Simulated 01900 | N/A | CSS Simulated | CSS Simulated receives CSS Simulated 01900 and performs Registration Deactivation |  | Y
| CSS Simulated Registration Deactivation | 32 | BP007 | 121 | CSS Simulated | CSS Simulated | CSS Simulated 02860 | N/A | REGS | CSS Simulated performs Registration Deactivation and sends CSS Simulated 02860 to REGS |  | Y
|  | 33 | BP007 | 125 | MHHS-BR-RS-100 MHHS-BR-RS-101 | CSS Simulated | CSS Simulated 02860 | N/A | REGS | REGS receives CSS Simulated 02860 and updates Registration | REGS receives CSS Simulated 02860 Registration Update and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 34 | BP007 | 155 | MHHS-BR-RS-102 MHHS-BR-RS-103 MHHS-BR-RS-102.1 | CSS Simulated | CSS Simulated 02860 | N/A | REGS | On receipt of the CSS Simulated deactivation notification the Registration Service will send out the de-appointment notification to all service providers | REGS receives CSS Simulated 02860 Registration Update and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS sends out CSS Simulated DeRegistration Notification | 35 | BP007 | 125 | MHHS-BR-RS-101 MHHS-BR-RS-102.1 | REGS | IF-009 | [CSS Simulated DeRegistration] | DIP | REGS sends IF-009 to DIP | http 202 response from DIP | Y
|  | 36 | BP007 | 130 |  | DIP | PUB-009 | [CSS Simulated DeRegistration] | SUPC, LDSO, MDS and EES | REGS sends PUB-009 to SUPC, LDSO, MDS and EES to confirm the CSS Simulated De-Registration |  | N
|  | 37 | BP007 | 137 |  | DIP | PUB-009 | [CSS Simulated DeRegistration] | SUPC | SUPC receives PUB-009. | Supplier (Current) receives PUB-009 with details of the CSS Simulated De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 38 | BP007 | 136 | MHHS-BR-LD-020.1 | DIP | PUB-009 | [CSS Simulated DeRegistration] | LDSO | LDSO receives PUB-009. | LDSO receives PUB-009 with details of the CSS Simulated De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 39 | BP007 | 135 | MDS | DIP | PUB-009 | [CSS Simulated DeRegistration] | MDS | MDS receives PUB-009. | MDS receives PUB-009 with details of the CSS Simulated De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 40 | BP007 | 131 | MHHS-BR-EES-016.3 | DIP | PUB-009 | [CSS Simulated DeRegistration] | EES | EES receives PUB-009. | EES receives PUB-009 with details of the CSS Simulated De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-037 Interface between Registration Participant and DIP is disable/configured to return error
| De-appoint Current Metering Service | 41 | BP007 | 155 | MHHS-BR-RS-102 | REGS | IF-037 | [MSDeApp] | DIP | REGS sends IF-037 to DIP | http 202 response from DIP | Y
Evidence of IF-037 Queuing/Buffering
IF-037 Interface between Registration Participant and DIP is enabled/configured to return process as normal
|  | 42 | BP007 | 145 |  | DIP | PUB-037 | [MSDeApp] | AMSC, SUPC, LDSO & EES | DIP sends PUB-037 De-Appoints Current Metering Service with a De-Appointment Reason Code = "DEREG" (RMP Terminated by CSS Simulated ) to Metering Service (Current), Supplier(Outgoing), LDSO & EES |  | N
|  | 43 | BP007 | 150 | MHHS-BR-MS-040 | DIP | PUB-037 | [MSDeApp] | AMSC | Metering Service (Current) receives PUB-037 confirming MS De-appointment | Metering Service (Current) receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 44 | BP007 | 157 | MHHS-BR-SU-059 | DIP | PUB-037 | [MSDeApp] | SUPC | Outgoing Supplier receives PUB-037 confirming MS De-appointment | Supplier (Current) receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 45 | BP007 | 156 | MHHS-BR-LD-021 | DIP | PUB-037 | [MSDeApp] | LDSO | LDSO receives PUB-037 confirming MS De-appointment | LDSO receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 46 | BP007 |  | MHHS-BR-EES-016.3 | DIP | PUB-037 | [MSDeApp] | EES | EES receives PUB-037 confirming MS De-appointment | EES receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| De-appoint Current Data Service | 47 | BP007 | 155 | MHHS-BR-RS-102 | REGS | IF-037 | [DSDeApp] | DIP | REGS sends IF-037 to DIP | http 202 response from DIP | Y
|  | 48 | BP007 | 145 |  | DIP | PUB-037 | [DSDeApp] | ADSC, SUPC, LDSO, EES and MDS | DIP sends PUB-037 - De-Appoints Current Data Service with a De-Appointment Reason Code = "DEREG" (RMP Terminated by CSS Simulated ) to ADSC, SUPC, LDSO, EES and MDS |  | N
|  | 49 | BP007 | 140 | MHHS-BR-DS-104 MHHS-BR-DS-105 | DIP | PUB-037 | [DSDeApp] | ADSC | Smart Data Service (Outgoing) receives PUB-037 | Smart Data Services Outgoing receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 50 | BP007 | 157 | MHHS-BR-SU-059 | DIP | PUB-037 | [DSDeApp] | SUPC | Supplier (Outgoing) receives PUB-037 | Supplier (Current) receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 51 | BP007 | 156 | MHHS-BR-LD-021 | DIP | PUB-037 | [DSDeApp] | LDSO | LDSO receives PUB-037. | LDSO receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 52 | BP007 |  | MHHS-BR-EES-016.3 | DIP | PUB-037 | [DSDeApp] | EES | EES receives PUB-037. | EES receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 53 | BP007 |  | DES138 | DIP | PUB-037 | [DSDeApp] | MDS | MDS receives PUB-037. | MDS receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y

## SITNFT-T2-100-040-UM
No. |  | Test Case Id |  |  |  |  | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
4 |  | SITNFT-T2-100-040-UM |  |  |  |  | SITNFT-T2-100-040-UM | Unmetered Single MPAN , same-day LDSO Initiated Disconnection (as per DES138 data specification) | Unmetered | Single | same-day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
IF-007 Interface between UMSO Participant and DIP is disable/configured to return error
SITFTS-0840 - LDSO Initiated Disconnection - Unmetered Supplies | De-energisation - Start | 1 | BP008 | 65 70 80 | MHHS-BR-MS-047 MHHS-BR-MS-048 MHHS-BR-MS-049 | UMSO | IF-007 | [EnergisationStatusChange] | DIP | UMSO sends IF-007 to DIP | http 202 response to DIP | Y
Evidence of IF-007 Queuing/Buffering
IF-007 Interface between UMSO Participant and DIP is enabled/configured to return process as normal
|  | 2 | BP008 | 90 |  | DIP | PUB-007 | [EnergisationStatusChange] | REGS | DIP sends PUB-007 to REGS |  | N
|  | 3 | BP008 | 105 110 | MHHS-BR-RS-104 MHHS-BR-RS-105 | DIP | PUB-007 | [EnergisationStatusChange] | REGS | Registration service receives update of energisation status from PUB- 007 | REGS receives PUB-007 EnergisationStatusChange, confirms request for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-008 Interface between Registration Participant and DIP is disable/configured to return error
|  | 4 | BP008 | 115 | MHHS-BR-RS-107 | REGS | IF-008 | [EnergisationStatusChange] | DIP | REGS sends IF-008 to DIP | http 202 response to DIP | Y
Evidence of IF-008 Queuing/Buffering
IF-008 Interface between Registration Participant and DIP is enabled/configured to return process as normal
|  | 5 | BP008 | 125 |  | DIP | PUB-008 | [EnergisationStatusChange] | UMSO, SUPC, LDSO, UMSDS, MDS & EES | DIP sends PUB-008 to UMSO, Supplier, LDSO, Unmetered Data Service, MDS & EES |  | N
|  | 6 | BP008 | 140 | MHHS-BR-MS-050 | DIP | PUB-008 | [EnergisationStatusChange] | UMSO | UMSO receives PUB-008 | Meter Service receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 7 | BP008 | 175 | MHHS-BR-SU-064 | DIP | PUB-008 | [EnergisationStatusChange] | SUPC | Supplier receives PUB-008. | Supplier receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 8 | BP008 | 165 | MHHS-BR-LD-024 | DIP | PUB-008 | [EnergisationStatusChange] | LDSO | LDSO receives PUB-008. | LDSO receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 9 | BP008 | 155 | MHHS-BR-DS-106 | DIP | PUB-008 | [EnergisationStatusChange] | UMSDS | Unmetered Data Service receives PUB-008. | Data Service receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 10 | BP008 | 160 | central settlements | DIP | PUB-008 | [EnergisationStatusChange] | MDS | MDS receives PUB-008 | MDS receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| De-energisation - End | 11 | BP008 | 156 | MHHS-BR-EES-016.3 | DIP | PUB-008 | [EnergisationStatusChange] | EES | EES receives PUB-008. | EES receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| LDSO Initiated Disconnection | 12 | BP007 | 30 | MHHS-BR-LD-013 MHHS-BR-LD-014 | UMSO | BAU | BAU | LDSO | LDSO may also receive a request from UMSO where they have been asked to disconnect. Where the LDSO have had a request to disconnect they will inform the UMSO of this. This will be done via an agreed communication method |  | Y
| UMSO Receives Notification of Disconnection | 13 | BP007 | 50 | MHHS-BR-MS-038 | LDSO | Email or other Agreed Mechanism | Email or other Agreed Mechanism | UMSO | UMSO receives request for disconnection. | UMSO receives Disconnection Request and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| LDSO Initiated Disconnection | 14 | BP007 | 30 | MHHS-BR-LD-013 MHHS-BR-LD-014 | UMSO | Email or other Agreed Mechanism | Email or other Agreed Mechanism | LDSO | LDSO receives confirmation from UMSO that the Disconnection Request has been received. | LDSO receives confirmation that the Disconnection Request has been received and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| LDSO Disconnects Meter Point | 15 | BP007 | 40 | MHHS-BR-LD-015 MHHS-BR-LD-018 | LDSO | Internal DB03 |  | REGS | The LDSO physically disconnects the connection to the property and updates the Registration Service |  | Y
|  | 16 | BP007 | 70 | MHHS-BR-RS-097 | LDSO | Internal DB03 |  | REGS | REGS receives the Internal DB03 | REGS receives Internal DB03 and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-009 Interface between Registration Participant and DIP is disable/configured to return error
| RS sends out LDSO Disconnection Notifications | 17 | BP007 | 70 | MHHS-BR-RS-098 | REGS | IF-009 | [MPANDisconnection] | DIP | REGS sends IF-009 to DIP | http 202 response from DIP | Y
Evidence of IF-009 Queuing/Buffering
IF-009 Interface between Registration Participant and DIP is enabled/configured to return process as normal
|  | 18 | BP007 | 85 |  | DIP | PUB-009 | [MPANDisconnection] | SUPC, LDSO, EES | DIP sends PUB-009 to SUP (Current), LDSO and EES to confirm the Meter Point has been disconnected |  | N
|  | 19 | BP007 | 95 | MHHS-BR-SU-056 MHHS-BR-SU-057 | DIP | PUB-009 | [MPANDisconnection] | SUPC | SUP (Current) receives PUB-009. | Supplier (Current) receives PUB-009 with details of the Meter Point Disconnection and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 20 | BP007 | 86 | MHHS-BR-LD-020 | DIP | PUB-009 | [MPANDisconnection] | LDSO | LDSO receives PUB-009. | LDSO receives PUB-009 with details of the Meter Point Disconnection and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 21 | BP007 | 87 | MHHS-BR-EES-016.3 | DIP | PUB-009 | [MPANDisconnection] | EES | EES receives PUB-009. | EES receives PUB-009 with details of the Meter Point Disconnection and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-050 Interface between Registration Participant and DIP is disable/configured to return error
| RS sends out EES MPAN Status Change Update | 22 | BP007 | 70 | MHHS-BR-RS-099 | REGS | IF-050 | [MPStatusChange] | DIP | REGS sends IF-050 to DIP | http 202 response from DIP | Y
Evidence of IF-050 Queuing/Buffering
IF-050 Interface between Registration Participant and DIP is enabled/configured to return process as normal
|  | 23 | BP007 | 126 |  | DIP | PUB-050 | [MPStatusChange] | EES | DIP sends PUB-050 to EES to confirm the MP status change |  | N
|  | 24 | BP007 | 127 |  | DIP | PUB-050 | [MPStatusChange] | EES | EES receives PUB-050. | EES receives PUB-050 with details of the MP Status Change and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS sends out CSS Simulated MPAN Status Change Update | 25 | BP007 | 70 | MHHS-BR-RS-099 | REGS | CSS Simulated 0700 | N/A | CSS Simulated | REGS sends CSS Simulated 0700 to CSS Simulated |  | Y
|  | 26 | BP007 | 115 | CSS Simulated | REGS | CSS Simulated 0700 | N/A | CSS Simulated | CSS Simulated receives CS0700 and Terminates RMP |  | Y
| Deactivation Formal Request | 27 | BP007 | 96 | MHHS-BR-SU-057 | SUPC | CSS Simulated 01900 | N/A | CSS Simulated | SUP (Current) sends Registration Deactivation Request CSS Simulated 01900 to CSS Simulated |  | Y
|  | 28 | BP007 | 120 | CSS Simulated | SUPC | CSS Simulated 01900 | N/A | CSS Simulated | CSS Simulated receives CSS Simulated 01900 and performs Registration Deactivation |  | Y
| CSS Simulated Registration Deactivation | 29 | BP007 | 121 | CSS Simulated | CSS Simulated | CSS Simulated 02860 | N/A | REGS | CSS Simulated performs Registration Deactivation and sends CSS Simulated 02860 to REGS |  | Y
|  | 30 | BP007 | 125 | MHHS-BR-RS-100 MHHS-BR-RS-101 | CSS Simulated | CSS Simulated 02860 | N/A | REGS | REGS receives CSS Simulated 02860 and updates Registration | REGS receives CSS Simulated 02860 Registration Update and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 31 | BP007 | 155 | MHHS-BR-RS-102 MHHS-BR-RS-103 MHHS-BR-RS-102.1 | CSS Simulated | CSS Simulated 02860 | N/A | REGS | On receipt of the CSS Simulated deactivation notification the Registration Service will send out the de-appointment notification to all service providers | REGS receives CSS Simulated 02860 Registration Update and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS sends out CSS Simulated DeRegistration Notification | 32 | BP007 | 125 | MHHS-BR-RS-101 MHHS-BR-RS-102.1 | REGS | IF-009 | [CSS Simulated DeRegistration] | DIP | REGS sends IF-009 to DIP | http 202 response from DIP | Y
|  | 33 | BP007 | 130 |  | DIP | PUB-009 | [CSS Simulated DeRegistration] | SUPC, LDSO, MDS and EES | DIP sends PUB-009 to SUPC, LDSO, MDS and EES to confirm the CSS Simulated De-Registration |  | N
|  | 34 | BP007 | 137 |  | DIP | PUB-009 | [CSS Simulated DeRegistration] | SUPC | SUPC receives PUB-009. | Supplier (Current) receives PUB-009 with details of the CSS Simulated De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 35 | BP007 | 136 | MHHS-BR-LD-020.1 | DIP | PUB-009 | [CSS Simulated DeRegistration] | LDSO | LDSO receives PUB-009. | LDSO receives PUB-009 with details of the CSS Simulated De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 36 | BP007 | 135 | MDS | DIP | PUB-009 | [CSS Simulated DeRegistration] | MDS | MDS receives PUB-009. | MDS receives PUB-009 with details of the CSS Simulated De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 37 | BP007 | 131 | MHHS-BR-EES-016.3 | DIP | PUB-009 | [CSS Simulated DeRegistration] | EES | EES receives PUB-009. | EES receives PUB-009 with details of the CSS Simulated De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-037 Interface between Registration Participant and DIP is disable/configured to return error
| De-appoint Current Metering Service | 38 | BP007 | 155 | MHHS-BR-RS-102 | REGS | IF-037 | [MSDeApp] | DIP | REGS sends IF-037 to DIP | http 202 response from DIP | Y
Evidence of IF-037 Queuing/Buffering
IF-037 Interface between Registration Participant and DIP is enabled/configured to return process as normal
|  | 39 | BP007 | 145 |  | DIP | PUB-037 | [MSDeApp] | UMSO, SUPC, LDSO & EES | DIP sends PUB-037 De-Appoints Current Metering Service with a De-Appointment Reason Code = "DEREG" (RMP Terminated by CSS Simulated ) to Metering Service (Current), Supplier(Outgoing), LDSO & EES |  | N
|  | 40 | BP007 | 150 | MHHS-BR-MS-040 | DIP | PUB-037 | [MSDeApp] | UMSO | Metering Service (Current) receives PUB-037 confirming MS De-appointment | Metering Service (Current) receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 41 | BP007 | 157 | MHHS-BR-SU-059 | DIP | PUB-037 | [MSDeApp] | SUPC | Outgoing Supplier receives PUB-037 confirming MS De-appointment | Supplier (Current) receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 42 | BP007 | 156 | MHHS-BR-LD-021 | DIP | PUB-037 | [MSDeApp] | LDSO | LDSO receives PUB-037 confirming MS De-appointment | LDSO receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 43 | BP007 |  | MHHS-BR-EES-016.3 | DIP | PUB-037 | [MSDeApp] | EES | EES receives PUB-037 confirming MS De-appointment | EES receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| De-appoint Current Data Service | 44 | BP007 | 155 | MHHS-BR-RS-102 | REGS | IF-037 | [DSDeApp] | DIP | REGS sends IF-037 to DIP | http 202 response from DIP | Y
|  | 45 | BP007 | 145 |  | DIP | PUB-037 | [DSDeApp] | UMSDS, SUPC, LDSO, EES and MDS | DIP sends PUB-037 - De-Appoints Current Data Service with a De-Appointment Reason Code = "DEREG" (RMP Terminated by CSS Simulated ) to UMSDS, SUPC, LDSO, EES and MDS |  | N
|  | 46 | BP007 | 140 | MHHS-BR-DS-104 MHHS-BR-DS-105 | DIP | PUB-037 | [DSDeApp] | UMSDS | UMSDS (Outgoing) receives PUB-037 | Unmetered Data Service Outgoing receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 47 | BP007 | 157 | MHHS-BR-SU-059 | DIP | PUB-037 | [DSDeApp] | SUPC | Supplier (Outgoing) receives PUB-037 | Supplier (Current) receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 48 | BP007 | 156 | MHHS-BR-LD-021 | DIP | PUB-037 | [DSDeApp] | LDSO | LDSO receives PUB-037. | LDSO receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 49 | BP007 |  | MHHS-BR-EES-016.3 | DIP | PUB-037 | [DSDeApp] | EES | EES receives PUB-037. | EES receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 50 | BP007 |  | DES138 | DIP | PUB-037 | [DSDeApp] | MDS | MDS receives PUB-037. | MDS receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y