## Sheet1
Organisation: | Various |  | MHHS-DEL1307 Consolidated Comments Log (This Artefact)
Constituency: | Various
Date: | 2023-06-29 |  | Comments on artefact 'MHHS-DEL1258 SIT Component Integration Testing Approach & Plan (v0.2)'
Anonymised: | Where requested
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete |  |  |  | Programme to complete once consultation window has closed.
Ref | Reviewer | Page | Section | Comment | Accept/Reject or Action | Response | Status
1 | St Clements | Page: 15 | Section: 7.1.3 | Will DIP and ISD include both MPIDs and roles? | Clarification Action | Working assumption is yes. | Closed - Clarification Response (Document Not Updated)
2 | St Clements | Page: 18 | Section: 7.2.1 | SIT participants will be expected to keep ADO updated in real time as execution is carried out. - what amount of time delay is acceptable assuming ADO is manually updated? | Clarification Action | We require participants to execute and capture evidence at the point the test is executed and this standard will be maintained, monitored and assured - we will discuss this in more detail with you bi-laterally. | Closed - Clarification Response (Document Not Updated)
3 | St Clements | Page: 10 | Section: 5.1 | Further to previous comments, will there be a clear distinction within the test cases between the testing conducted for 1II and 2 ? | Clarification Action | At present we don't have a mechanism to differentiate between these groups of scenarios / cases, however this is being looked at. We will feedback bi-laterally on this. | Closed - Clarification Response (Document Not Updated)
4 | IMServ | Page: | Section: | Could the boxes above, Organisation, Constituency and Date (cells C7, C8 and C9) not be a white font on a white background please | Clarification Action | Noted and passed on to the PPC team. | Closed - Clarification Response (Document Not Updated)
5 | IMServ | Page: | Section: 7.2.1 | It is unrealistic to say'SIT participants will be expected to keep ADO updated in real time as execution is carried out', often some time is required to evaluate results, it would be better to say close to real time | Clarification Action | We require participants to execute and capture evidence at the point the test is executed and this standard will be maintained, monitored and assured - we will discuss this in more detail with you bi-laterally. | Closed - Clarification Response (Document Not Updated)
6 | IMServ | Page: | Section: 7.2.8 | This should be 5 working days | Accepted | In section 7.2.8 the statement '...will be required to provide an individual Test Completion Report within 5 days of completing their tests...' has been amended to 5 working days for clarification. | Closed - Document Updated
7 | IMServ | Page: | Section: | This review period was not 5 full working days at it was not issued until 14:11 on Friday 30/06/23 with a closing date for review of Thursday 6th July | No Action | Noted. | Closed - No Update Required
8 | IMServ | Page: | Section: 7.2.1.1 | ability to take on ISD this seems to have been changed to "download" everywhere else in the document so for consistency should be updated here too? | Accepted | In section 7.2.1.1 the reference PPs' ability to 'take on ISD' has been amended to 'download ISD' in order to be consistent with the rest of the document. | Closed - Document Updated
9 | IMServ | Page: | Section: 7.2.2 | MPANs records should this be "MPAN records" ? | Accepted | In section 7.2.2 the reference to 'MPANs records' has been changed to 'MPAN records'. | Closed - Document Updated
10 | IMServ | Page: | Section: 7.2.4 and 7.2.6 | test "scripts" seem to have been changed to "cases" elsewhere in the doc. so for consistency should be updated here too? | Accepted | 2 references to test 'scripts' have been changed to 'cases' for consistency with the rest of the document. | Closed - Document Updated
11 | Power Data Associates | Page: 13 | Section: 6.1 | As per our comms in January and subsequent email exchange this year (meeting 19 May, last email from Kevin Davis on 1 June), where given it is known by the Testing Team that the CIT Testing scenarios are inaccurate/incomplete - and is not reflective of the baselined Design - an amendment should be made to reference and recognise this within this SIT CIT Test Data Approach & Plan document, and not to just directly call out and link to the scenarios - as to avoid confusion with participants thinking they are a final/correct version. | Clarification Action | Each referenced formal MHHS deliverable (the SIT CIT Scenarios the one that is referenced here) has a consultation and change management process which is managed centrally. We have completed the uplift of the CIT scenarios in line with Interim release 1 and are in the process of updating them in line with the recently published Interim release 2. We will keep participants informed on release dates of these in SITWG group meetings and have also written out to you directly on this point. | Closed - Clarification Response (Document Not Updated) | Kevin
12 | Power Data Associates | Page: 14 | Section:7.1.1 | As per our comms in January and subsequent email exchange this year (meeting 19 May, last email from Kevin Davis on 1 June), where given it is known by the Testing Team that the CIT Testing scenarios are inaccurate/incomplete - and is not reflective of the baselined Design - an amendment should be made to reference and recognise this within this SIT CIT Test Data Approach & Plan document, and not to just directly call out and link to the scenarios - as to avoid confusion with participants thinking they are a final/correct version. | Clarification Action | As above | Closed - Clarification Response (Document Not Updated) | Kevin
13 | Power Data Associates | Page: 14 | Section: 7.1.1 | """[REF-12] ‘MHHSP-DES138-Interface Catalogue’The Interface Catalogue has been one of the primary inputs for defining the Component Integration Test Scenarios and Cases."" As already commented on, but therefore not sure this is an accurate statement to use, given the email of 19 May from Kate advising the Interface Catalogue was not checked in relation to developing the Test scenarios. " | Clarification Action | The interface catalogue is the key input to key input to the CIT scenarios creation so apologies for any previous miscommunication. The CIT scenarios version issued for review was based on v5.0 and had been overtaken by a design update (Interim Release 1). To avoid this issue, and associated confusion, recurring, we are holding off the reissue until we complete the update to Interim Release 2 (5.2.1), which is the baseline for entry to CIT, please refer to SITWG for further status updates. | Closed - Clarification Response (Document Not Updated) | Kevin
14 | Power Data Associates | Page: 21 | Section: 7.2.9.1 | Where you've indicated a completion report will be anonymised as appropriate, i.e. identified by market role rather than organisation. Why? Two views here - for some roles it will remaine either obvious, or reasonably obvious who the participant is, given the small numbers (sometimes singular) of each market role in SIT. But also - why is this being anonymised? I appreicate technical details of someones solution wouldn't be shared, but isn't it imperative for the ability for SIT to be completed from the Programme perspective that each participant succeeds - and especially where Placing Reliance is being used it would be important for the participant to be seen and known? | Clarification Action | We have erred on the side of caution here, however we plan to put this to FTIG PPs to see if there are any objections to PP level test and defect metric transparency with industry (i.e. via the governance framework). | Closed - Clarification Response (Document Not Updated)
15 | E.ON Energy Services | Page: 22 | Section: 7.2.8 | Individual Test Completion Report needs to be provided within 5 days of completing their tests. Can it be clarified that its 5 working days. | Duplicate (No Action) | This has been amended in v0.4. See comment ref 6 response. | Closed (Duplicate)
16 | Helix | Page: | Section:7.2 | CIT/ SIT progressive integration - System service is in scope are DIP, LSS and MDS. Remove Settlement Operation. Other system is ISD from where only data will be downloaded by other participants from the data catalogue and no direct DIP and ISD testing or access is required. | Accepted | Settlement Operations has been removed from v0.4. | Closed - Document Updated
17 | Helix | Page: | Section: 7.2.1.1 | Need discussion on this for CIT as this is manual testing and evidence capturing | No Action | Noted, we will discuss this with you bilaterally. | Closed - No Update Required
18 | Helix | Page: | Section: 7.2.5 | Release and configuration management process is in discussion as we do not agree with the defect SLA and sev 2 and 3 release schedule | No Action | This is noted, but is out of scope of this document. Discussion on this topic will be continued bilaterally and relates to the Release and Configuration Management Approach and Plan and Defect Management Plan. | Closed - No Update Required
19 | Helix | Page: | Section:7.1.6 | PIT Exit - Our ability to do anything more than certificate testing against DIP simulator is subject to alignment of interface specification with the DIP and sufficient time. | No Action | This is noted, further discussion on this topic will be continued bilaterally in relation to your PIT Approach and Plan. | Closed - No Update Required
20 | Helix | Page: | Section:8 | SIT CIT progressive Integration - please remove VAS and Settlement Operation | Accepted | VAS was removed in version 0.3 as per comment received. Settlement Operations has been also now been removed from v0.4. | Closed - Document Updated
21 | Smart DCC | Page: 23 | Section: 8.1 | The CIT Data Approach is showing the last interval 22nd December. What is CI Test Execution up to Feb 24 covering? | Clarification Action | I assume you are referring to section 9 Test Data Schedule within the Test Data Approach and Plan. This is a timeline which depicts test data readiness activities ahead of each interval. That plan is targeting completion of data prep tasks by 22nd Dec, however interval 6 execution commences Jan 29th as per the timeline within CIT Approach and Plan deliverable. | Closed - Clarification Response (Document Not Updated)
22 | Smart DCC | Page: 25 | Section: 8.2 | There doesn't seem to be inclusion of TRT to CIT? I'd expect TRT 1-2 in line with PIT for CIT then TRT 3 post PIT governance? | Clarification Action | As the DCC doesn't connect directly with the DIP we have deemed it out of scope for CIT. All DCC and PP DCC UEPT readiness activities are aligned to SIT Functional Test. | Closed - Clarification Response (Document Not Updated)
23 | Smart DCC | Page: General | Section: General | Will progress reports be provided to TMAG and other groups on a regular basis including defect information? | Clarification Action | Correct. DCC are an MHHS participant and so will be in receipt of reports published within the programme governance framework. | Closed - Clarification Response (Document Not Updated)
24 |  | Page: | Section:
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117