## Northern Powergrid
Organisation: | Northern Powergrid
Constituency: | DNO
Date: | 2024-03-21 | MHHS-DEL2415 Environments Approach & Plan Comments Log
Anonymised:
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete |  |  |  | Programme to complete once consultation window has closed.
Ref | Reviewer | Page | Section | Comment | Accept/Reject or Action | Response | Status
1 | Northern Powergrid | 38 | 9.6 Non-SIT LDSO Qualification Testing | It is mentioned in this section that "No requirement to test CSS to Network Operations functionality as this is tested in MHHS SIT Functional testing." CSS is connected to MPRS application of LDSO and not Network Operation. It is misleading. | Accept | Amended | Closed
2 | Northern Powergrid | 38 | 9.6 Non-SIT LDSO Qualification Testing | As per the 'QA&P Annex 1 - Non-SIT LDSO MHHS QT Approach & Plan' document the 'Generation of the REP-900 [E-Bill] and REP-901 [Aggregated DUoS Charges]' has been included. In this case, Please confirm if we need to stand-up a DUoS Billing test environment for the entire duration of NON-SIT LDSO phase to support the Non-SIT LDSO environment? |  | I have clarified with the Qualification Test Team and have been informed that non-SIT LDSOs will be required to stand up a DUoS Billing test environment. | No change required to the Environments Approach & Plan document. The document defines what Central Parties are required to provide, not the individual architecture of individual PPs - PPs should know what test environment architecture they need to stand-up in order for them to test to the test scenario / test case scope.
3 | Northern Powergrid | 45, 46 | 11.2 MHHS Environments Timeline 11.1 High Level MHHS Test POAP | The Non- SIT LDSO testing phase end date is different in both the figures -Figure 22 - High Level MHHS Test POAP : end date is 20-Jan-25 - Figure 23 - MHHS Environments Timeline: end date is 17-Jan-25 It is a typo and needs to be aligned - we believe it should be 20-Jan-25. | Accept |  | Diagrams updated

## Elexon
Organisation: | ELEXON - Helix Programme
Constituency:
Date: | 2024-03-18 | MHHS-DEL2145_Environment_Approach__Plan_v2.12 ELEXON-Helix Review Comments Log
Anonymised:
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete |  |  |  | Programme to complete once consultation window has closed.
Ref | Reviewer | Page | Section | Comment | Accept/Reject or Action | Response | Status
1 | ELEXON - Helix Programme | 14 | 7.1.1 | Which Helix application components are required in SIT B to cover Settlement Testing scenarios ? Section 8.2 table states Settlement Operations but does not state the application components, can we have further details of the Settlement Operation application components? | No change to document | Helix to stand-up those components that they require in order to be able to execute the test cases | Clarification provided
2 | ELEXON - Helix Programme | 14 | 7.1.1 | Assumption is cycle 2 functional release drop is proposed for SIT B environment for "Settlement Testing" Phase? can you please confirm | Clarification - no change to document | IR7 will be deplaoyed into SIT-A for Cycle 2 on 27th May and into SIT-B on 3rd June. | Clarification provided
3 | ELEXON - Helix Programme | 14 | 7.1.1 | Which Helix application components will be required for Non-SIT LDSO test phase in the UIT Environment? | Clarification - no change to document | None. Neither Helix nor a Helix test harness will be required for non-SIT LDSO Qualification testing. Any reports that are required to support testing will be stubbed. | Clarification provided
4 | ELEXON - Helix Programme | 19 | 8.1 | Section 8.1 states: The environment requirements for SIT B (SIT non-Functional) have yet to be defined in detail, and will be included in future iterations of this document. - Is there are a definite timeline by when the "Settlement Testing" application component requirements for SIT B will be defined and shared? | Clarification - no change to document | This is ongoing at the present time. The Programme wants to conclude ASAP in order to provide PPs with sufficient time to stand-up environments. | Clarification provided
5 | ELEXON - Helix Programme | 29 | 9.4.3 | Section 9.4.3 states: "For the avoidance of doubt, it should be assumed that if a D-Flow is new or changed it should be tested in MHHS SIT, either Functional or non-Functional." Can we please have confirmation in which environment will the DTN flows be tested? Will it be in the SIT A or SIT B? or both | Clarification - no change to document | Both, depending on the testing activity. SIT-A is the environment for SIT Functional testing (with the exception of Settlement Testing which is to be executed in SIT-B). Settlement Testing is a functional test phase but requires a 'clean' environment, hence the use of SIT-B. If any D-Flows are referenced in Settlement Test Cases then they will be exercised in SIT-B. | Clarification provided
6 | ELEXON - Helix Programme | 45 | 11.1 | Figure 22 does not state the timeline for Settlement Testing Phase. Conflicts with the Environment Timeline figure shown in 11.2 | Clarification - no change to document | Figure 22 provides a high level view of the test phases. Settlement Testing is a component of SIT-Functional Testing, Theme 8. It is not explicitly referenced, nor are the other 7 functional themes. Figure 23 states in which test environments the different test phases are taking place. | Clarification provided
7 | ELEXON - Helix Programme | 48 | 11.3.1.3 | Can we have the DIP environment confirmed to interface with our SIT B environment ? Do we interface with the same DIP environment currently setup for SIT A? | Clarification - no change to document | There will be a DIP environment for SIT-A and a separate DIP environment for SIT-B. There is an MHHS Programme & Avanade meeting on 27th March to discuss how PPs will connect to SIT-B - i.e. new certificates or existing certificates. Either way webhooks will need to be registered. | Clarification provided
8 | ELEXON - Helix Programme | 48 | 11.4 | Section 11.4 states: "Consequently integrated end to end test environment connectivity is required to CSS and the DTN. Programme Participants are responsible for registering their CSS webhooks and for configuring the DTN." Helix does not interface with CSS directly, therefore assumption is Helix environment will not require to register with CSS webhooks. | Clarification - no change to document | Correct. There is no requirement for Helix to register CSS webhooks. | Clarification provided
9 | ELEXON - Helix Programme | 14 | 7.1.1 | Assumption is cycle 2 functional release drop is proposed for SIT B environment for "Settlement Testing" Phase? Does this mean the new IR7 changes and the cycle2-settlement reports would be tested in SITB? and what about Cycle3 testing, will it be carried in SITA or SITB? SITA will continue with Theme1 to 7,9 and migration testing activities? please confirm. | Clarification - no change to document | It is only Settlement testing that is being executed in SIT-B. Migration Testing and all other Functional SIT will be executed in SIT-A. At present Settlement Testing is only envisaged to be executed in Cycle 2. | Clarification provided
10 | ELEXON - Helix Programme | 45 | 11.1 | In the environment table, SITB doesn't include SIT functional testing which contradicts the section 7.1.1 | Clarification - no change to document | Do you mean Figure 22? Figure 22 is a logical representation of when the different test phases are being executed, taking an environment agnostic point of view. Section 7.1.1 states that Functional Settlement Testing will be executed in SIT-B. It makes sense to make that statement to avoid comments that state that Table 1 in section 7.1.1 and Figure 23 aren't aligned. Figure 23 is a logical representation | Clarification provided
11 | ELEXON - Helix Programme | 10 | 10.1 | How will the DIP onboarding cater for both SIT-A and SIT-B? | Clarification - no change to document | There will be separate DIP instances, different end points. Discussions are ongoing between the MHHS Programme and Avanade in order to baseline the connection method. When baselined this will be communicated to PPs at the earliest opportunity. Most likely via EWG and / or FTIG. | Clarification provided
12 | ELEXON - Helix Programme | 49 | 11.5 | Re: SIT-B required from April 1st 2024 Will there be any preliminary testing carried out once the environment is ready prior to SIT Functional Cycle 2 formally starting on June 10th? (If yes, what will be carried out and when?) | Clarification - no change to document | At FTIG on Friday 22nd March Lee presented a POAP for Settlement Testing, stating when PPs are expected to have their environments on-line, when smoke testing will take place. These are further stated in the April EWG slides. April EWG scheduled for 2nd April. | Clarification provided
13 | ELEXON - Helix Programme | 49 | 11.5 | Re: SIT-B required from April 1st 2024 Will project participants need access to this environment to access any test data which isn't produced by themselves ahead of June 10th? (e.g. ISD data) (If yes what is the expected due date?) | Clarification - no change to document | Data requirements are in the process of being reviewed and will be communicated to PPs at the earliest opportunity. | Clarification provided
14 | ELEXON - Helix Programme | 49 | 11.5 | Re: SIT-B required from April 1st 2024 Can MHHSP share a schedule outlining activities that will occur between the setup of the environment and the actual start date of testing on June 10th? | Clarification - no change to document | At FTIG on Friday 22nd March Lee presented a POAP for Settlement Testing, stating when PPs are expected to have their environments on-line, when smoke testing will take place. These are further stated in the April EWG slides. April EWG scheduled for 2nd April. | Clarification provided