## Utilita
Organisation: | Utilita
Constituency: | Supplier & Meter Service
Date: | 2024-04-05 | MHHS-DEL2459 SIT Operational Test Approach and Plan Comments Log
Anonymised: | No
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete |  |  |  | Programme to complete once consultation window has closed.
Ref | Reviewer | Page | Section | Comment | Accept/Reject or Action | Response | Status
1 | Kev Roper | 18 | 7.1.4.1 | Participant SIT Operational Test Readiness Report This section suggests that PPs are responsible for the delivery of the items in section 7.2 yet 7.2 confirms the SI is producing them. Section 9.2.1 also shows PPs are only Informed for those activities | Accept | Section 7.1.4.1 reference to 7.2 was incorrect it has been changed to 7.1.4. Section 9.2 shows the Participant being responsible for the Participant Test Readiness Report and the SI responsible for the SI Test Readiness Report. | closed
2 | Kev Roper | 18 | 7.1.4.1 | Participant SIT Operational Test Readiness Report Assuming I've understood Ref 1 correctly what are you expecting PPs to report on? | Accept | Reporting against section 7.1.4, as above the reference was incorrect and should not have been pointing to 7.2 | Closed
3 | Kev Roper | 10 to 13 | 5 | Its unclear if this test phase applies solely to the Central Parties or if other PPs (i.e. Supplier, Meter Service etc) are also involved Could a matrix be provided showing which of the In Section items ins section 5.2 onwards applies to which Role? I cant read this and be sure which of those areas we might be involved in as either a Supplier or Metering Service. For example I believe we would not be involved in Section 5.6 "Demonstrate LDSO operability with MPRS" though that seemed to be contradicted by Lee Cox on the SITWG held 04/04 | Accept | A matrix has been added showing roles expected to involved | Closed
4 | Kev Roper | 13 & 13 | Security CR044 Business Requirements Out of Scope | Some document sections aren't numbered. I.e. Security, CR044 and Business requirements on page 12 and Out of Scope on page 13 | A | Updated | Closed
6 | Mike Pawluk | General | General | Overlap with Non-Functional Testing. A lot of the areas covered in this documents were / are already covered bt the NFT NFR Categorisation Document. Based on the NFR Categorisation OAT tests had already been defined. Should these test and (in general) is Operation Testing being pulled out and separated from Non-Functional Testing? |  | Operations Testing and Non-Functional Testing have always been seperate activities, as there will be elements of overlap between Operational Testing and NFT we are working closely together to ensure no overlap or gaps between the phases

## Elexon
Organisation: | Elexon
Constituency:
Date: | 2024-04-08 | MHHS-DEL2459 SIT Operational Test Approach and Plan Comments Log
Anonymised:
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete |  |  |  | Programme to complete once consultation window has closed.
Ref | Reviewer | Page | Section | Comment | Accept/Reject or Action | Response | Status
1 | Santosh Vasudevan | 11 | 5.1 In Scope | By DIP offboarding, we assume you mean offboarding of an industry party and not Elexon. It would not make sense for a central party such as Elexon to get offboarded. | A | We will not be looking to offboard Elexon as part of this process
2 | Santosh Vasudevan | 11 | 5.1 In scope | Please could you change "Functional Business requirements" to "Operational requirements" or similar as the scope of this testing is limited to operational aspects that may not have been covered by other test phases. | A | This has been changed to Business Requirements as requirements are split by Business and Non-Functional. We are only looking at a sub set of the Business Requirements for Operational Testing
3 | Santosh Vasudevan | 11 | 5.1 Inscope | Security : Helix will be conducting our own Pentration Testing using a Third party, will that suffice? |  | We would look to assure the results from your testing as part of Operational Testing
4 | Santosh Vasudevan | 11 | 5.2 Operation Process | Reporting : Helix monitoring systems is designed for the Production, only when we officially go live in Prod is when the Monitoring Systems will work. How would you expect the assurance to be carried out? |  | We would look to assure the Monitoring system Design if Monitoring is not available within the Test environment
5 | Riccardo Lampini | 10 | 5.1 | Dates for DIP onboarding - this testing was to be conducted starting from January 25 and not October 24. Please could you confirm the approach, timeline and reason for the change? |  | DIP onboarding forms part of Operational Testing which commences in Oct 2024. DIP Onboarding is within theme 2. The execution order / scheduling is not yet defined.
6 |  | 10 | 5.2 | There is no defined or agreed process for DIP Offboarding. When do we get visibility of that? |  | We are currently waiting for the planned delivery date for the Offboarding process
7 |  |  | General | Is the scope of testing limited to the target state or does it cover the transition period as well? |  | We will be testing against target state
8 | Ian Giles | 11 | 5.4 | The timeline for service management testing - we discussed that this will be later than October. Please could you confirm that still be the case and the approximate timelines. We may not be fully ready with a fully operational and tested tool by October. |  | We will be looking at the scheduling for the themes of which Service Mngt is in Theme 3 as next steps.
9 | Ian Giles | 11 | 5.4 | Is the readiness of our support partner's connectivity with the service management tool crucial as part of this? What would the triage process look like? Does all of that need to be documented and ready? |  | We expect an instance of the Service Management tool to be in place that can be used to support Operational Testing taking place in SIT B Expectations are the technical components that make up your Service Management Solution will be built and available with supporting processes documented and available SIT operational will not be testing the Operational Readiness of People, so do not expect you to have support teams fully stood up for the purpose of this SIT Test Stage, however resource will be required to test the processes Your Service Management Tool, , will need to be built, configured and available to test. We are setting out that we will test any areas of the Service Management Platform that has new customisations/configurations built for MHHS
10 |  | 11 | 5.5 | Third bullet - please clarify if this related to the technical functioning of the system and/or business operational functioning? |  | This is related to operational processes for any error handling / fault management. We will not be testing each interface from a functional perspective as this has already been proven in other phases
11 |  | 11 | 5.5 | Second bullet - please could you clarify this further with another example. The MDS example does not provide enough clarity. |  | After further analysis and discussion this has been removed as it will be covered under NFT scope
12 |  | 12 | 5.6 | This section is for LDSO's scope of testing. Has any testing related to submission of LLFs been covered under functional or any other testing? That might need to be included here if not. |  | This testing is aimed at providing confidence that LDSO's (BUUK and SSEN only) can operate MPRS in their own traget infrastructure. SIT Functional SITFTS-ST0035 covers LLF
13 |  | 12 | CR044 | This CR is yet to be discussed and details approved and therefore is out of the scope for this SIT Operational test. It will need to go through the change management process referred to in this document. |  | The Test Approach and Plan already has allowance for the current status of this CR section 5.1. This CR therefore is not confirmed to be in scope until the change process concludes identifying it is a candidate for SIT operational Testing
14 |  | 13 | Business Requirements | Please could you share the 60 requirements that you refer here for us to understand where the gaps might be. |  | Table added showing BR's after further analysis there are 46 BRs identified for Operational Testing scope
15 |  | 22 | 7.10 Documentation Issue | Sixth bullet "Documentation Issue" - Please could you clarify what type of documentation are you referring here. |  | This is where the Test team identify issues against Design documents
16 | Theo Tsatsos | 14 | 6.1 Environments | We have concerns that the co-existence of functional and non-functional operating within the same environment could result it: -red-herring defects -general latency -conflicting priorities in terms of defect fixing and release management Please could describe what is the approach to avoid this and whether we need any additional environment/s to mitigate these risks or change the timeline |  | SIT NF and SIT Operational Testing have co-existed in the same Test environment since CR022 was concluded, as such this is not a new challenge. As SIT NF and SIT Operational Test Scenario and Test Cases are developed so will a deconflicting test schedule across SIT B also be developed ahead of Test Exceution and will be shared / socialised with Industry as appropriate. The Programme does not intend on investigating additional Test Environemnts to deconflict. No change propsed to this document.
17 | Theo Tsatsos | 31 | 10.1 | What are the three themes and milestone IDs that have been referred to. [Now understood as part of SITWG presentation.] |  | No update required. Dates for each theme included in section 10.1
18 | Mahesh Gogtay / John Abbott | 18 | 7.1.4 | What is the purpose of PIT documentation and tests here? The environment and systems would have been already tested by other test phases happening concurrently. We do not believe drafting additional PIT documentation and running those achieves anything. |  | Helix platforms to support portions of SIT operational Testing e.g. Service Managament will not have been tested in previous phases. Therefore evidence will be required from PIT testing in areas such as this. Equally if Platforms required for SIT operational have been tested previously then PIT approach and plans can state and credit that, documenting no further testing is required

## REECo
Organisation: | RECCo
Constituency: | Central Party / Code Body
Date: | 09.04.2024 | MHHS-DEL2459 SIT Operational Test Approach and Plan Comments Log
Anonymised:
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete |  |  |  | Programme to complete once consultation window has closed.
Ref | Reviewer | Page | Section | Comment | Accept/Reject or Action | Response | Status
| Jonny Moore | 8 | 3.5.2 | There are a number of statements throughout the document that operational processes, BCDR processes etc are not yet available. The availability of these documented processes should be captured as a dependency and tracked through the operational testing delivery plan | A | Dependency wording updated
| Jonny Moore | 10 | 5.1 | CR045 'SSD Correction Tool' should also be mentioned as in scope should it be approved |  | The implementation approach and associated timeline is due for decison at May's PSG. Following that decision the Programme will look to accomodate into the Test Programme where appropriate.
| Jonny Moore | 10 | 5.1 | Should either CR044 or CR045 not be approved in time for SIT Operational, testing of work around processes for correcting mismatches or data errors should be included as part of the SIT Operational scope. |  | Should in-flight and not yet approved CRs that are expected to form part of the Operational Testing scope not be approved within the timeframe. We will assess the impact and any workarounds
| Jonny Moore | 10 | 5.1 | Given it's importance within industry architecture. We would have expected the end to end SOLR process to form part of SIT Operational testing. In particular updates within the DIP and ISD should be tested. |  | SOLR process is not changing as part of MHHS and therefore not considered as in scope for Operational Testing
| Jonny Moore | 10 | 5.1 | We would suggest that the transfer of MPIDs / DIP IDs between participants as part of a Trade Sale should also form part of the DIP Operational Testing. |  | Trade Sale is not changing as part of MHHS and therefore not considered as in scope for Operational Testing
| Andrew Wallace | 16 | 7.1.1 | As a general principle, Code Bodies require clarity on the SIT Operational Test Scenarios and Test Cases for parties that need to MHHS Qualify to feed into the development of the Qualification materials, in particular the QAD which is expected to be finalised at end Aug 24. We therefore welcome the MHHS Programme approach to develop the SIT Operational Test Scenarios and Test Cases in batches, with some of these being finalised in July. We request that MHHS Programme cover all SIT Operational Test Scenarios and Test Cases that impact parties that need to MHHS Qualify in July with other testing that impact Central Parties being covered in August. We have set out below our understanding of which areas should be covered in July but, as recognised in section 5, the full scope of the operational design has not yet completed and our views may change once the full scope is better understood. |  | Acknowledged, no updates to the document
|  |  |  | Comments on Batch 1: - We agree that LDSO Operability with MPRS, and Business Requirements are required for July. |  | No change to document required
| Andrew Wallace | 16 | 7.1.1 | Comments on Batch 2: - DIP Onboarding / Offboarding and Security are not expected to be required for the development of Qualification documents, so could move to August for approval. - We agree with the proposal to approve the CR044 solution test scenarios and cases in July. - As noted above, we think that CR45 should also be within scope and, given the impact for parties that need to MHHS Qualify, any test scenarios and test cases should be agreed in July. |  | Revised POAP added to section 7.1.1 as discussed and agreed with Code Bodies applied to the document
| Andrew Wallace | 16 | 7.1.1 | Comments on Batch 3: - We consider that the scope of BCDR should include LDSOs (Registration Services) and on that basis we would expect the tests cases to be in Batch 1 or 2 and agreed in July. - Our understanding is that Service Management design is still in development. Where there are interoperability and capacity requirements for Registration Services e.g. in relation to the Agent Appointment process, we would expect this to be in Batch 1 or 2 and agreed for July. - We are not clear about the use of the term 'Operational Processes' as in section 5.2 as this covers a wide range of issues including Service Management and BCDR (Batch 3) and DIP Onboarding (Batch 2). As such, we are not able to determine if there impacts for parties that need to be MHHS Qualified (such that Test Scenarios and Cases should be agreed in July). |  | As discussed in Code Bodies weekly call BCDR is confined to new central parties MPRS in this context is not a Central party and on the assumption LDSO's already bound to existing BCDR obligations SIT operational will not cover BCDR of SSEN and BUUK With regards to Service Mngt again as discussed will be retained in Theme 3 Operational processes are not yet authored and therefore conclusive assesments against impact to PPs qualification cannot be determined in this document.
| Andrew Wallace | 16 | 7.1.1 | We could not see that Operational Choreography had been allocated to a Batch. Is this because all elements are covered by Non-Functional Testing? To the expent that there are any SIT Operational Scenarios and Test Cases for parties that need to MHHS Qualify, these should be agreed in July. |  | Operational Choreography has been included in Theme 2, there will be limited testing in Operational Testing for the Op Choreography as the majority of this is covered by NFT

## Imserv
Organisation: | IMServ Europe
Constituency: | Independent Supplier Agent
Date: | 28/03/24 | MHHS-DEL2459 SIT Operational Test Approach and Plan Comments Log
Anonymised: | No
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete |  |  |  | Programme to complete once consultation window has closed.
Ref | Reviewer | Page | Section | Comment | Accept/Reject or Action | Response | Status
| RF | 10 | 5.2 | DIP Onboarding/Offboarding requirements - would the evidence that we've already done this for accessing the DIP for CIT/SIT, not be sufficient in providing evidence of our ability to achieve this? Rather than repeating the activity with a 'pseudo' person/role? |  | Operational Testing will test the DIP Onboarding/offborading process E2E. This will not be for each party and at this point do not expect this to impact you
| RF | 11 | 5.5 | If we are to provide a focus on Interfaces where manual work is required - it may need to be considered that for certain Interfaces different participants (even in the same role) may have designed different approaches in their systems to manage these. |  | Acknowledged
| RF | 11 | 5.5 | Additionally, where Interfaces require manual work, and we have a number of these already - there are tests in SIT Functional that involve these interfaces, and so evidence that will have been given in that testing stage will already demonstrate their use. Can this evidence simply be referenced to avoid retesting, or copied back into the evidence for this SIT Operational stage? |  | Acknowledged and interfaces in this category will be assessed during scenario creation and if applicable and already proven in SIT Functional we can look to use this as evidence an example is a correction PUB-031

## UKPN
Organisation: | UK Power Networks
Constituency:
Date: | 2024-04-09 | MHHS-DEL2459 SIT Operational Test Approach and Plan Comments Log
Anonymised:
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete |  |  |  | Programme to complete once consultation window has closed.
Ref | Reviewer | Page | Section | Comment | Accept/Reject or Action | Response | Status
1 | Murshid | 12 | 5.6 | What is the IR version against which the MPRS has to be baselined and deployed in LDSOs infrastructure to demonstrate LDSO operability. If there is a specific IR version, update it in this section | A | MPRS instance to be aligned to IR8 which will be the version utitlised for Operational Testing, This will be for SSEN and BUUK specifically no other LDSO | Closed
2 | Murshid |  | General | No particular sections document the risks, dependencies ,assumptions and issues |  | Assumptions and depndencies are listed in section 3.5.1 and 3.5.2.
3 | Murshid | 26 | 8 Test schedule | Is there a risk captured for SIT non functional and operational test overlapping each other |  | There is an existing risk to cover the SIT NF and SIT Operational congestion challenge R556 which was created in July 2023