## Consolidated Comments Log
Organisation: | Various
Constituency:
Date: | 2023-07-04 | MHHS-DEL1371 Systems Integration Testing (SIT) Component Integration Testing (CIT) Test Data Approach & Plan Assurance Comments Log
Anonymised:
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete |  |  |  | Programme to complete once assurance window has closed.
Ref | Reviewer | Page | Section | Comment | Accept/Reject or Action | Response | Status
1 | Participants #1 | 22 | 8 Test Data Anonymisation | MPAN can't be shared in communication but as part of evidence capture it may be required. Can it be clarified with respect to evidence capture in ADO. | Section 8.1 Added including instructions to obfuscate MPANs on Test Reports | Thanks for highlighting the item. I aligned with the Testing team and included instructions on obfuscation of MPAN unique number in the reports and test evidences. | Recommended to close
2 | Smart DCC | 20 | 7.2.6 | During SIT, any PP - I'd expect this to state During CIT as this is a CIT Test Plan/Approach | Updated section 8 to state SIT (removed "Functional") | The annonymisation applies to CIT, Functional and all other SIT phases. | Recommended to close
3 | Smart DCC | General | General | If there is a defect raised, will data be reusable against a MPAN(s) if already utilised by the the PP or will database tables need to be cleared and retried? | No document updates | We do not recommend the databases to be cleared. - If the MPAN is is a state that the participant can retry the test using the same data, it okay to reuse. Otherwise, the participant should use a new MPAN attending the conditions of the Test Scenario. | Recommended to close
4 | Smart DCC | General | General | What is the entry and exit criteria for CIT? Who is confirming this test stage is a success and how is this measured? | No document updates | Forwared the query to Dominic - Test Plans | Recommended to close for this document review
5 | Smart DCC | 22 and 23 | 9 - Test Schedule | PP check data integrity Dec 18 - 22, This is normally holiday season is the 22nd the end date of CIT? Also each schedule of checking data/integrity, there doesn't seem to be time to fix issues? Is this expected to overlap for the different intervals? Is there any reporting expected out of this for approvals? Is this accounted for? | No document updates | Hi Nickie, the Test Data preparation finishes 4 weeks before the start of the respective CIT Interval. So, if the holidays season impacts the activity, we have margin to address it. Time to fix issues: Between transmission of any augmented data and the deadline to have the test data checked and ready, we are planning roughly 3 weeks. It should be enough. The participant also will have the interval between the Data Cut 19th August and start of the Test Data Prep to set-up test environment and load its test data. We do not have a requirements for reports for this data integrity check. Happy to discuss further during the bilateral calls | Recommended to discuss in bilat
6 | Participants #2 | 20 | 7.11 Test Data Preparation - Interval 6 – UMSDS, EES | As per the section "EES is expected to receive and load a full refresh of data provided by the relevant MPRS systems instances under testing, before testing commences" We have a few questions related to this topic 1. Would it be a one time activity? 2. Would programme need to have a connectivity setup between EES and MPRS prior to testing? 3. If the above is required, who is responsible for ensuring these interface applications are interlinked prior to testing? | Section 7.11 updated: As per alignment with RECCo and Testing team, the EES will take a backup instead of using the MPRS refresh mechanisms. | Thanks for the call out: 1- As per aligment calls with St Clements and RECCo, the MPRS full refresh won't be used for CIT. RECCo will take a backup and update any augmented data as required. 2 - For CIT it won't be required. However, for SIT Functional subsequent phases, the connectivity between EES and MPRS will be required. 3 - The EWG (Environment and Configuration Working Group - Simon Berry) is responsible for the connectivity and interfaces preparation for testing. | Recommended to close for this document review
7 | Participants #2 | 14 | 7.7 Test Data Preparation – Intervals 2 and 6 – MPRS | Who would be responsible for the manufacture of test data? We presume, programme SI will provide the test data to participants. | No updates required to the document | The SI will manufacture the missing/augmented Test Data to be loaded to the participants systems. Eg: Connection Type. Specifically for the Data Items the participant already has from their Data Cut, the SI does not need to manufacture or re-send them. The participant should load them from their Data Cut. Happy to furthr discuss it in bilateral calls | Recommended to close for this document review
8 | Participants #2 | 21 | 8 Test Data Anonymisation | Can we add a point under Assumption section that all the processes are same for both Domestic and Non-Domestic ? | Updated Section 8 | Good catch. Updated to include the note | Recommended to close
9 | Participants #2 | 21 | 8 Test Data Anonymisation | Will the programme participants be asked to provide the Non-Domestic consumption data as part of their SIT data cut? | No updates required to the document | No consumption data required in the data cut. The PP's won't need to provide any real consumption data. Consumption data will be generated/manufactured. Some participants may want to use. | Recommended to close
10 | Participants #3 | 8 | 6.1 | "During CIT, tests will also be required to show the DIP routing of, and participants systems’ correct intake of the Industry Standing Data (ISD).". I understood following the first set of comments, that you were now not requiring us to show our systems intaking the ISD during CIT? This statement seems to contradict this? | Section 6.1 updated to: "During CIT, tests will also be required to show the DIP routing of, and participants systems’ ability to download the Industry Standing Data (ISD)." | Updated Richard. During CIT, the PPs only need to prove they can download the content of the ISD, but do not need to process it. | Recommended to close
11 | Participants #3 | 11 | 7.6 | "The recipient participants do not need to process the ISD as part of CIT Tests.". This is now contradictory to the statement used as referened in our comment about section 6.1 above. | Updated the section 6.1 | Updated the section 6.1 | Recommended to close
12 | Participants #3 | 17 | Table 8 | As per our comms in January and subsequent email exchange this year (meeting 19 May, last email from Kevin Davis on 1 June), where given it is known by the Testing Team that the CIT Testing scenarios are inaccurate/incomplete - and is not reflective of the baselined Design. Just to clarify again therefore, this Table 8 in this guide for UMSO is incomplete with regards the messages the UMSO would send and receive via the DIP. It only shows the UMSO sending an IF-007. But misses the IF/PUBs for IF-008, IF-018, IF-026, IF-033, IF-034, IF-036, IF-037, IF-038, IF-039 and IF-047. There is no written detail in this section at all about the messgaes the UMSO will be a recipient for - UMSO and Network Operations are not the same role - the UMSO is a Metering Service. | Updated table 8. | Hi Richard, as we discussed, we do not capture the PUBs received for CIT Test Data Plan, since you won't need to demonstrate the processing of those during CIT test scenarios. | Recommended to close
13 | Participants #3 | 17 | Table 9 | As per our comms in January and subsequent email exchange this year (meeting 19 May, last email from Kevin Davis on 1 June), where given it is known by the Testing Team that the CIT Testing scenarios are inaccurate/incomplete - and is not reflective of the baselined Design. Just to clarify again therefore, this Table 9 in this guide for UMSDS is incomplete with regards the messages the UMSDS would send and receive via the DIP. It only shows the UMSDS sending an IF-021 and IF-034. But misses the IF/PUBs for IF-008, IF-013, IF-014, IF-018, IF-022, IF-026, IF-033, IF-034, IF-036, IF-037, IF-038, IF-039 and IF-047. Additionally, this document shows the UMSDS on the IF-021 providing Reactive Data - Reactive Data isn't used the Unmetered roles, and so is incorrect on that front too - the Design does not call out that Reactive Data would be sent, so this is an issue for these Test scenarios, and a further inaccuarcy of these Test Scenarios. | Updated table 9. | Hi Richard. Same, we need to capture the sending messages only. Thanks for your support clarifying it. | Recommended to close
14 | IMServ | 21 | 8 | Replace 'MPAN Number' with 'MPAN' since the 'N' in MPAN is the abbrevated form of 'Number' | Section 8 updated to remove "number" | Thanks. Updated! | Recommended to close
15 | IMServ | 7 | 5.1 | In MHHS-DEL-1258 the Testing Approach Plan you have updated "ability to take on ISD" to "download ISD", for cosistency between the two documents should the terminology be the same? This is genreal comment whereby if a change/update it made to one document and there is a related document that will be impacted by said change the related document should also be updated. | Updated section 5.1 | Thanks. You're right I updated 2 more reference to "intake" ISD. | Recommended to close
16 | Participants #4 | 21 | 8 Test Data Anonymisation | "The programme will provide a table to all participants with Unique Ref ID for the allocated MPANs to be used in communication. For example: - MPAN: 20 0001 5001 165 - Ref ID (For communications and reports): dfa4aba971c132ae07014206e6abb1c6" The use of a completely random MPAN id like this will cause confusion. Within Faster switching, we used a sensible id which would be discussed in meetings and easily written dow - eg EE1 for EMEB data or EN1 for NORW data A more simple id will make communication much easier | No document changes required. | Hi Anna, I added only as an example the obfuscation using a hash function. I'm happy to use the approach you participants find easier to communicate. We can discuss in the next bilateral calls to agree in the annonymisation function or logic to be used. I will need to provide a table to all participants with the "real MPAN ¦ Obfuscated MPAN". | Recommended to close for this document review
17 | Participants #4 | 10 13 | Figure 2 - CIT intervals 7.6 Test Data Preparation - Interval 1 | Interval 1 still includes VAS, but this is now out of scope. | Figure 2 and Section 7.6 Updated | Updated accordingly | Recommended to close.
18 | Participants #4 | 14 | 7.7 Test Data Preparation – Intervals 2 and 6 – MPRS | The data will not necessarily prepped to this - a lot of the data is included within the CIT scenario data | No document changes required. | Agree. As we've been discussing, for CIT the relevant data is: - MPAN - Routing data (MPID, DIPID) - EventCode - Relevant Data specified by Test Scenario All the other data does not need to be accurate. | Recommended to close for this document review
19 | Participants #4 | 22 | 9 Test Data Schedule | With regards to my previous comment:- "Check & Transmit Data to SI within a week of data cut will be challenging depending on the process to generate the data cut, especially if the data cut has to be loaded from the SIT DNO/iDNO into St Clements and the data cut taken at St Clements. The loading of the data into the St Clements environments is time consuming The requirement and effort of the processing of extracting the data is not known and has not been specified. This work has not been included in our planning (raised at FTIG as D014) " This issue is not around the loading of data back into MPRS, but the data extract from MPRS to send to SI. This is not a problem if the SI extract the data from EES as expected, but if taken from MPRS and data needs to be sent to SI, 5 days is not enough time to stand up 2 x environments, load the data, extract the data and send it to SI. | No document changes required. | Hi Anna. I confirm we are planning around get the test data needed from the EES data cut. We still have the programme risk R552 active and the D014. Since for SIT Functional in Q2 2024 I'm not 100% sure the EES data will contain all data needed, I can not close those items. | Recommended to close for this document review