## Change Log
Date | Author | Version | Change Detail
2024-02-09 | Kevin Davis | 1.0 | Discussion draft to inform Cohort, as well as central services, discussions.

## Execution Order by Cohort
Theme | Scenario File | Initiator Role | Primary Roles | Secondary Roles | Central Services | #TCs | #Steps (avg/TC) | #Parties | Category | Within Theme Priority | Cohort Internal (I), or Cross-Cohort ( C) | Smart | Adv | Trad | Unm | Linked, Related, Imp/Exp | Complications/Blockers | Co-A (UM) L(Co-C) | Co-C | Co-B L(Co-E) | Co-E | Co-D L(Co-F) | Co-F | Co-G (UM) L(Co-H) | Co-H | Co-I L (Co-J) | Co-J (UM)
INTERNAL TO COHORT
1 - New Connections | MHHS-DEL1757 SITFTS-0050 New Connection | LDSO | REGS, SUPC | EES, SUPC, SMSI, SDSI, MDS, SUPL, SMSC, SDSC, DCC, MDR, AMSI, ADSI, AMSC, ADSC, UMSDS, UMSO, CSS | CSS, MDR, REGS, EES, Helix (MDS) | 4 | 114 | 18 | P | 1 | I | Yi+e | Y | Y | Y |  | IF-50 | 36 | 34 | 26 | 26 | 26 | 26 | 29 | 27 | 7 | 9
1 - New Connections | MHHS-DEL1758 SITFTS 0060 New Connection MS DS Delay | LDSO | REGS | LDSO, EES, SMSI, SMSC, SDSI, SDSC, MDS, DCC, UMSDS, LSS, MDR, CSS | CSS, MDR, REGS, EES, Helix (MDS, LSS) | 2 | 138 | 14 | EC | 2 | I | Y |  |  | Y |  | IF-50 | 37 | 35 | 27 | 27 | 27 | 27 | 30 | 28 | 8 | 10
1 - New Connections | MHHS-DEL1759 SITFTS-0090 New Connection MS Change Re-Submit | LDSO | REGS, SMSI, AMSI, UMSO | EES, SUPL, MDS, SDSI, UDSI, ADSI, UMSDS, CSS | CSS, REGS, EES, Helix (MDS) | 4 | 55 | 13 | EC | 3 | I | Yi+e | Y | Y | Y |  | IF-50 | 38 | 36 | 28 | 28 | 28 | 28 | 31 | 29 | 9 | 11
2 - Change of Registration | MHHS-DEL1772 SITFTS-1000 REG UPD Linked | SUPC | LDSO, REGS | SMSC, SDSC, EES, AMSC, ADSC, SUPC | REGS, EES | 3 | 11 | 8 | P | 1 | I | YL | YL |  |  | Y | Link, Rel, Imp/Exp - IR7
2 - Change of Registration | MHHS-DEL1763 SITFTS-0930 REG UPD Consent Granularity | SUPC | REGS | SDSC, ADSC, SUPC | REGS | 2 | 7 | 4 | P | 1 | I | Y | Y |  |  |  |  | 25 | 23 | 8 | 8 | 1 | 1 | 18 | 14 | 10 | 12
2 - Change of Registration | MHHS-DEL1764 SITFTS-0940 REG UPD Domestic Premise Indicator | SUPC | REGS | LDSO, SMSC, SDSC, MDS, AMSC, ADSC, SUPC, CSS | CSS, REGS | 2 | 9 | 8 | P | 1 | I | Y | Y |  |  |  |  | 26 | 24 | 9 | 9 | 2 | 2 | 19 | 15 | 11 | 13
2 - Change of Registration | MHHS-DEL1765 SITFTS-0950 REG UPD DUOS Tariff ID | LDSO | REGS | MDS, SMSC, SDSC, EES, SUPC, AMSC, ADSC, LDSO | REGS, EES | 2 | 9 | 9 | P | 1 | I | Y | Y |  |  |  |  | 27 | 25 | 10 | 10 | 3 | 3 | 20 | 16 | 12 | 14
2 - Change of Registration | MHHS-DEL1762 SITFTS-0920 REG UPD MPL Address GSP Group ID | SUPC, LDSO, UMSO | REGS | SUPC, SMSC, SDSC, MDS, EES, LDSO, AMSC, ADSC, UMSO, UMSDS, CSS | CSS, REGS, EES | 5 | 10 | 11 | P | 2 | I | Y | Y | Y | Y |  |  | 28 | 26 | 11 | 11 | 4 | 4 | 21 | 17 | 13 | 15
2 - Change of Registration | MHHS-DEL1766 SITFTS-0960 REG UPD Related | SUPC | REGS | SMSC, SDSC, MDS, EES, LDSO, AMSC, ADSC, SUPC, CSS | CSS, REGS, EES | 2 | 13 | 9 | P | 2 | I | Yrel | Yrel |  |  | Y | Link, Rel, Imp/Exp - IR7
2 - Change of Registration | MHHS-DEL1768 SITFTS-0970 REG UPD Energy Direction | SUPC | REGS | LDSO, SMSC, SDSC, EES, MDS, AMSC, ADSC, SUPC, CSS | CSS, REGS, EES | 2 | 12 | 9 | P | 3 | I | Yi | Ye |  |  | Y | Link, Rel, Imp/Exp - IR7
2 - Change of Registration | MHHS-DEL1769 SITFTS-0980 REG UPD Metered Indicator | SUPC | REGS | LDSO, SMSC, SDSC, EES, AMSC, ADSC, SUPC, CSS | CSS, REGS, EES | 3 | 11 | 8 | P | 3 | I | Y | Y | Y |  |  |  | 29 | 27 | 12 | 12 | 5 | 5 | 22 | 16 | 14 | 16
2 - Change of Registration | MHHS-DEL1770 SITFTS-0990 REG UPD SMSO | LDSO | REGS | SMSC, SDSC, EES, SUPC, LDSO | REGS, EES | 3 | 9 | 5 | P | 3 | I | Y | [5 empty] | 30 | 28 | 13 | 13 | 6 | 6 | 23 | 17 | 15 | 17
2 - Change of Registration | MHHS-DEL1771 SITFTS-0995 REG UPD IHD | SUPC | REGS | EES, SUPC | REGS, EES | 2 | 6 | 3 | P | 3 | I | Y | [5 empty] | 31 | 29 | 14 | 14 | 7 | 7 | 24 | 18 | 16 | 18
2 - Change of Registration | MHHS-DEL1774 SITFTS-1010 REG UPD Legacy Info | SUPC | REGS | SMSC, SDSC, LSS, EES, LDSO, SUPC | REGS, EES | 4 | 11 | 7 | P | 3 | I | Y |  | Y |  |  |  | 32 | 30 | 15 | 15 | 8 | 8 | 25 | 19 | 17 | 19
2 - Change of Registration | MHHS-DEL1775 SITFTS-1020 REG DCC Enrolment | DCC | REGS | SDSC, EES, SUPC | REGS, EES | 2 | 6 | 5 | P | 3 | I | Y | [5 empty] | 33 | 31 | 16 | 16 | 9 | 9 | 26 | 20 | 18 | 20
2 - Change of Registration | MHHS-DEL1806 SITFTS-0100 REG Change Cust Appt MS | SMSI, AMSI, UMSO | REGS | EES, SMSI, AMSI, SUPC | REGS, EES | 4 | 9 | 6 | P | 4 | I | Y | Yi+e | Yrel | Y |  |  | 34 | 32 | 17 | 17 | 10 | 10 | 27 | 21 | 19 | 21
2 - Change of Registration | MHHS-DEL1805 SITFTS-0180 REG Change Cust Appt DS | SDSI, ADSI, UMSDS | REGS | SUPC, EES, SDSI, ADSI, UMSDS | REGS, EES | 3 | 8 | 6 | P | 4 | I | Y | Y |  | Y |  |  | 35 | 33 | 18 | 18 | 11 | 11 | 28 | 22 | 20 | 22
2 - Change of Registration | MHHS-DEL1767 SITFTS-0965 REG UPD Related Rejection | SUPC | REGS | SUPC | REGS | 1 | 6 | 2 | N | 4 | I | Yrel |  |  |  | Y | Link, Rel, Imp/Exp - IR7
2 - Change of Registration | MHHS-DEL1773 SITFTS-1005 REG UPD Linked Rejection | SUPC | LDSO | SUPC | REGS | 1 | 6 | 2 | N | 4 | I | YL |  |  |  | Y | Link, Rel, Imp/Exp - IR7
6 - Metering Changes | MHHS-DEL1887 SITFTS-0280 MET Energisation Change | SUPC | SMSC, AMSC, UMSO, REGS | MDS, EES, LDSO, SDSC, ADSC, UMSDS, SUPC | REGS, EES | 6 | 19 | 11 | P | 1 | I | Y | Y | Y | Y |  |  | 17 | 15 | 29 | 29 | 29 | 29 | 1 | 1 | 21 | 23
6 - Metering Changes | MHHS-DEL1894 SITFTS-0900 MET Change of Meter | SUPC | SMSC, REGS, AMSC, | LDSO, SDSC, EES, ADSC, SUPC | REGS, EES | 6 | 27 | 9 | P | 1 | I | Y | Y | Y |  |  |  | 18 | 16 | 30 | 30 | 30 | 30 | 2 | 2 | 22 | 24
6 - Metering Changes | MHHS-DEL1889 SITFTS-0840 MET DISCONNECT | LDSO | REGS | SUPC, EES, MDS, SMSC, SDSC, AMSC, ADSC, LDSO, CSS | REGS, EES, CSS, Helix (MDS) | 4 | 38 | 9 | P | 2 | I | Y | Y | Y | Y |  | IF-50 | 19 | 17 | 31 | 31 | 31 | 31 | 3 | 3 | 23 | 25
6 - Metering Changes | MHHS-DEL1888 SITFTS-0360 MET Energisation Change Fails | SUPC | SMSC REGS, LDSO, AMSC | SDSC, SUPC | REGS | 4 | 11 | 5 | N | 5 | I | Y | Y | Y |  |  |  | 20 | 18 | 32 | 32 | 32 | 32 | 4 | 4 | 24 | 26
6 - Metering Changes | MHHS-DEL1893 SITFTS-0890 MET Historic Updates incl Rejections | SMSC | REGS, AMSC, SMSC | LDSO, EES, SUPC | REGS, EES | 6 | 9 | 6 | P | 5 | I | Y | Y | Y |  |  |  | 21 | 19 | 33 | 33 | 33 | 33 | 5 | 5 | 25 | 27
6 - Metering Changes | MHHS-DEL1913 SITFTS-0905 MET Changes REGS rejection | SUPC | AMSC, REGS, SMSC | SDSC, LDSO, ADSC, SUPC | REGS | 6 | 15 | 8 | EC | 5 | I | Y | Y | Y |  |  |  | 22 | 20 | 34 | 34 | 34 | 34 | 6 | 6 | 26 | 28
6 - Metering Changes | MHHS-DEL1891 SITFTS-0850 MET DISCONNECT Related and Linked | SUPC | SMSC, REGS, LDSO, AMSC | SDSC, EES, MDS, ADSC, SUPC, CSS | REGS, EES, CSS, Helix (MDS) | 3 | 83 | 11 | EC | 6 | I | Yrel | Yrel | Yrel |  | Y | Link, Rel, Imp/Exp - IR7
6 - Metering Changes | MHHS-DEL1914 SITFTS-0910 MET Change of MAP | SMSC, AMSC | SMSC, AMSC, REG | LDSO, EES, SDSC, ADSC | REGS, EES | 2 | 11 | 9 | P | 6 | I |  | Y | Y |  |  |  | 23 | 21 | 35 | 35 | 35 | 35 | 7 | 7 | 27 | 29
6 - Metering Changes | MHHS-DEL1915 SITFTS-0915 MET Change of MAP update unsuccessful | SMSC | SMSC, REGS | SUPC | REGS | 1 | 8 | 3 | EC | 6 | I |  |  | Y |  |  |  | 24 | 22 | 36 | 36 | 36 | 36 | 8 | 8 | 28 | 30
7 - Consumption | MHHS-DEL1981 SITFTS-1110 CONS Amendment Accepted | SUPC | SUPC, SDSC, ADSC | LSS, MDS, LDSO | Helix (MDS, LSS) | 2 | 15 | 6 | P | 1 | I |  | Y | Y |  |  |  | 1 | 1 | 7 | 7 | 12 | 12 | 9 | 9 | 5 | 5
7 - Consumption | MHHS-DEL1970 SITFTS-0290 CONS Estimate Trad Meters Multi Rates | SDSC | SDSC, LSS | SUPC | Helix (LSS) | 4 | 8 | 1 | P | 2 | I |  |  | Yi+e |  | Y | Link, Rel, Imp/Exp - IR7 | [8 empty] | 4 | 4
7 - Consumption | MHHS-DEL1972 SITFTS-0300 CONS ADS Meter Advance Reconciliation | ADSC | ADSC |  |  | 2 | 6 | 1 | N | 2 | I |  | Yi+e |  |  |  | Link, Rel, Imp/Exp - IR7 | [8 empty] | 4 | 4
7 - Consumption | MHHS-DEL1980 SITFTS-1100 CONS Amendment Rejection | SUPC | SUPC, SDSC, ADSC | LSS, MDS, LDSO, | Helix (MDS, LSS) | 2 | 18 | 6 | N | 2 | I |  | Y | Y |  |  |  | 2 | 2 | 6 | 6 | 13 | 13 | 10 | 10 | 1 | 1
7 - Consumption | MHHS-DEL1971 SITFTS-0295 CONS SDS Estimation | SDSC,SUPC | LSS | LDSO | Helix (LSS) | 16 | 12 | 2 | P | 3 | I | Yi+e |  | Yi+e |  | Y | Link, Rel, Imp/Exp - IR7
7 - Consumption | MHHS-DEL1974 SITFTS-0310 CONS ADS Export Estimation | ADSC | ADSC, LSS |  | Helix (LSS) | 14 | 6 | 1 | P | 3 | I |  | Ye |  |  | Y | Link, Rel, Imp/Exp - IR7
7 - Consumption | MHHS-DEL1976 SITFTS-0320 CONS UMDS Estimation | UMSO, UMSDS | UMSDS, UMSO, LSS |  | Helix (LSS) | 5 | 9 | 2 | P | 3 | I |  |  |  | Y |  |  | 3 | [5 empty] | 11 |  |  | 2
7 - Consumption | MHHS-DEL1978 SITFTS-1080 CONS Amendment Criteria Not Met | SUPC | SUPC |  |  | 2 | 3 | 1 | N | 3 | I | Y | Y |  |  |  |  | 4 | 3 | 1 | 1 | 14 | 14 | 12 | 11 | 2 | 3
7 - Consumption | MHHS-DEL1941 SITFTS-0330 CONS Unmetered Invalid | UMSO | UMSDS, UMSO |  |  | 2 | 5 | 2 | EC | 4 | I |  |  |  | Y |  |  | 5 | [5 empty] | 13 |  |  | 4
7 - Consumption | MHHS-DEL1973 SITFTS-0305 CONS ADS Import Estimation | ADSC, SUPC | LSS |  | Helix (LSS) | 16 | 11 | 1 | P | 5 | I |  | Yi |  |  | Y | Link, Rel, Imp/Exp - IR7
7 - Consumption | MHHS-DEL1975 SITFTS-0315 CONS ADS Opt Out estimation | SUPC, ADSC | ADSC, LSS | LDSO | Helix (LSS) | 10 | 11 | 4 | EC | 6 | I |  | Yi+e |  |  | Y | Link, Rel, Imp/Exp - IR7
7 - Consumption | MHHS-DEL1942 SITFTS-0530 LSS IF-021 Rejected | SDSC, ADSC | SDSC, ADSC, LSS | LDSO, SUPC | Helix (LSS) | 2 | 8 | 5 | N | 6 | I | Y | Y |  |  |  |  | 6 | 4 | 2 | 2 | 15 | 15 | 14 | 12 | 3 | 5
7 - Consumption | MHHS-DEL1977 SITFTS-1070 CONS Amendment Override Readings Accepted | SUPC | SUPC | SDSC, ADSC, LDSO |  | 2 | 6 | 3 | N | 7 | I |  | Y | Y |  |  |  | 7 | 5 | 3 | 3 | 16 | 16 | 15 | 13 | 4 | 6
7 - Consumption | MHHS-DEL1979 SITFTS-1090 CONS Amendment Invalid Data | SUPC | SDSC, ADSC, SUPC |  |  | 2 | 7 | 3 | N | 8 | I |  | Y | Y |  |  |  | 8 | 6 | 4 | 4 | 17 | 17 | 16 | 14 | 5 | 7
7 - Consumption | MHHS-DEL1943 SITFTS-1095 CONS Amendment dispute | SUPC | SUPC | ADSC |  | 2 | 6 | 2 | EC | 9 | I | Y | Y |  |  |  |  | 9 | 7 | 5 | 5 | 18 | 18 | 17 | 15 | 6 | 8
7 - Consumption | MHHS-DEL1939 SITFTS-0260 CONS SETTLE Smart with gaps | MDR | DCC, SUPC, REGS | SDSC | MDR, DCC | 3 | 14 | 4 | N | 10 | I | [5 empty] | Physical Meters - Cycle 2
7 - Consumption | MHHS-DEL1940 SITFTS-0270 CONS Invalid | MDR, ADSC | DCC, MDR | SDSC, SUPC, AMSC | MDR, DCC | 2 | 6 | 4 | N | 10 | I | [5 empty] | Physical Meters - Cycle 2
9 - ISD | MHHS-DEL1930 SITFTS-0370 BSCCO ISD Data Changes | Helix (BSCCo) | ISD |  | Helix (BSCCo) | 2 | 3 | 2 | P | 1 | I | [6 empty] | 10 | 8 | 19 | 19 | 19 | 19 | 29 | 23 | 29 | 31
9 - ISD | MHHS-DEL1934 SITFTS-0425 ISD Data Human form Readable | MSA, ADS, SDS, MSS, UMSO, UMSDS, REGS, SUP, LDSO, EES | MSA, ADS, SDS, MSS, UMSO, UMSDS, REGS, SUP, LDSO, EES |  | Helix (BSCCo), REGS, EES | 1 | 1 | 10 | P | 1 | I | [6 empty] | 11 | 9 | 20 | 20 | 20 | 20 | 30 | 24 | 30 | 32
9 - ISD | MHHS-DEL1935 SITFTS-0390 BSCCO ISD Data Changes Publish | Helix (BSCCo) | ISD | LSS, MDS, VAS, SAA, CDCA, FAA, MSA, ADS, SDS, MSS, UMSO, UMSDS, REGS, SUP, LDSO, EES | Helix (BSCCo), REGS, EES | 3 | 9 | 3 | P | 2 | I | [6 empty] | 12 | 10 | 21 | 21 | 21 | 21 | 31 | 25 | 31 | 33
9 - ISD | MHHS-DEL1931 SITFTS-0380 BSCCO ISD Data Changes re-submit | Helix (BSCCo) | ISD |  | Helix (BSCCo) | 1 | 6 | 2 | EC | 3 | I | [6 empty] | 13 | 11 | 22 | 22 | 22 | 22 | 32 | 26 | 32 | 34
9 - ISD | MHHS-DEL1936 SITFTS-0400 BSSCO ISD Data use Post-Change | Helix (BSCCo) | ISD | LSS, MDS, VAS, SAA, CDCA, FAA, MSA, ADS, SDS, MSS, UMSO, UMSDS, REGS, SUP, LDSO, EES | Helix (BSCCo), REGS, EES | 2 | 9 | 9 | P | 3 | I | [6 empty] | 14 | 12 | 23 | 23 | 23 | 23 | 33 | 27 | 33 | 35
9 - ISD | MHHS-DEL1933 SITFTS-0420 ISD Data Previous Version Check | MSA, ADS, SDS, MSS, UMSO, UMSDS, REGS, SUP, LDSO, EES | MSA, ADS, SDS, MSS, UMSO, UMSDS, REGS, SUP, LDSO, EES |  | REGS, EES | 1 | 1 | 10 | EC | 4 | I | [6 empty] | 15 | 13 | 24 | 24 | 24 | 24 | 34 | 28 | 34 | 36
9 - ISD | MHHS-DEL1932 SITFTS-0410 BSSCO ISD Data Download Fails | MSA, ADS, SDS, MSS, UMSO, UMSDS, REGS, SUP, LDSO, EES | MSA, ADS, SDS, MSS, UMSO, UMSDS, REGS, SUP, LDSO, EES |  | REGS, EES | 1 | 1 | 0 | N | 5 | I | [6 empty] | 16 | 14 | 25 | 25 | 25 | 25 | 35 | 29 | 35 | 37
CROSS COHORT
3 - Change of Supplier | MHHS-DEL1813 SITFTS-0010 COS | SUPI, SUPC | REGS | EES, LDSO, MDS SMSI, SMSO, AMSI, ADSO, SDSI, SDSO, ADSI, ADSO, UMSO, UMSDS, SUPC SUPL, MDR, CSS | CSS, MDR, REGS, EES, Helix (MDS) | 4 | 26 | 6 | P | 1 | C | Y | Yi+e | Yrel | Y |  |  | 1 | 1 | 1 | 1 | 8 | 8 | 14 | 14 | 14 | 14
3 - Change of Supplier | MHHS-DEL1814 SITFTS-0020 COS DS Change | SUPI, SUPC | REGS, SDSI, ADSI, UMSDS | EES, LDSO, MDS, SUPO, SUPI, SUPL, SUPC, SMSC, ADSC, SDSO, ADSO, UMSO, MDR | CSS, MDR, REGS, EES, Helix (MDS) | 5 | 27 | 9 | P | 2 | C | Y | Yi+e | Yrel | Y |  |  | 2 | 2 | 2 | 2 | 9 | 9 | 15 | 15 | 15 | 15
3 - Change of Supplier | MHHS-DEL1816 SITFTS-0030 COS MS Change | SUPI, SUPC | REGS, SMSI, AMSI | EES, SUPI, SUPC, SUPL, LDSO, MDS, ADSC SDSC, AMSO, SMSO, CSS | CSS, MDR, REGS, EES, Helix (MDS) | 2 | 27 | 10 | P | 2 | C | Yi+e | Y |  |  |  |  | 3 | 3 | 3 | 3 | 10 | 10 | 16 | 16 | 16 | 16
3 - Change of Supplier | MHHS-DEL1818 SITFTS-0040 COS MS DS Change | SUPI, SUPC | REGS, SMSI, AMSI, SDSI, ADSI | EES, LDSO, MDS, SUPO, SUPI, SUPL, SUPC, SMSO, AMSO, SDSO, ADSO, CSS | CSS, MDR, REGS, EES, Helix (MDS) | 3 | 32 | 6 | P | 3 | C | Y | Yi+e | Yrel |  |  |  | 4 | 4 | 4 | 4 | 11 | 11 | 17 | 17 | 17 | 17
3 - Change of Supplier | MHHS-DEL1819 SITFTS-0045 COS MS DS Change Lapsed Appointments | SUPI | REGS, SUPC | SUPO, SUPI, AMSO, ADSO, AMSI, ADSI, SMSI, SDSI, CSS | CSS, REGS | 2 | 19 | 10 | N | 4 | C | Y | Y |  |  |  |  | 5 | 5 | 5 | 5 | 12 | 12 | 18 | 18 | 18 | 18
3 - Change of Supplier | MHHS-DEL1817 SITFTS-0035 COS DS Change Est Read | SUPI | REGS, SDSC, SDSI | EES, SUPC, SUPI, SUPO, LDSO, MDS, CSS | CSS, REGS, EES, Helix (MDS) | 1 | 29 | 8 | EC | 5 | C | Y | [5 empty] | 6 | 6 | 6 | 6 | 13 | 13 | 19 | 19 | 19 | 19
3 - Change of Supplier | MHHS-DEL1815 SITFTS-0025 DS Change Linked Diff Suppliers | SUPI | REGS, SDSO, SDSI, ADSI, ADSO | EES, SUPC, SUPI, SUPL, LDSO, MDS, SMSO, SMSI, AMSI, AMSO, CSS, MDR | CSS, MDR, REGS, EES, Helix (MDS) | 3 | 34 | 15 | EC | 6 | C | YL | YL |  |  | Y | Link, Rel, Imp/Exp - IR7
3 - Change of Supplier | MHHS-DEL1820 SITFTS-0095 COS MS DS Change Switch Cancel | SUPI | REGS | SUPI,SMSI, SDSI | CSS, REGS | 1 | 19 | 4 | N | 7 | C | Y | [5 empty] | 7 | 7 | 7 | 7 | 14 | 14 | 20 | 20 | 20 | 20
4 - Change of Data | MHHS-DEL1799 SITFTS-0130 DS Change | SUPC | REGS, SDSI | LDSO, EES, MDS, SUPC, SMSC, AMSC, SDSI, SDSO, ADSI, ADSO, UMSDSI, UMSDSO, CSS, MDR | CSS, MDR, REGS, EES, Helix (MDS) | 4 | 1 | 16 | P | 1 | C | Y | Y | Yi+e | Y |  |  | 10 | 10 | 10 | 10 | 1 | 1 | 7 | 7 | 7 | 7
4 - Change of Data | MHHS-DEL1802 SITFTS-0150 DS Change Linked MPANs Scenario 1 | SUPC | REGS | LDSO, EES, SMSC, MDS, SDSI, SDSO, SUPC, CSS, MDR | CSS, MDR, REGS, EES, Helix (MDS) | 2 | 41 | 8 | EC | 2 | C | YL |  |  |  | Y | Link, Rel, Imp/Exp - IR7
4 - Change of Data | MHHS-DEL1804 SITFTS-0170 DS Change Linked MPANs Scenario 2 | SUPC | REGS, SDSI, ADSI | SMSI, LDSO, EES, MDS, SDSO, SUPO, AMSI, ADSO, SUPC, CSS, MDR | CSS, MDR, REGS, EES, Helix (MDS) | 3 | 41 | 12 | EC | 2 | C | YL | YL |  |  | Y | Link, Rel, Imp/Exp - IR7
4 - Change of Data | MHHS-DEL1803 SITFTS-0160 DS Change with Rejections and Lapsed | SUPC | REGS, SDSI | SUPC | REGS | 3 | 9 | 3 | N | 3 | C | Yrel | Yrel |  |  | Y | Link, Rel, Imp/Exp - IR7
4 - Change of Data | MHHS-DEL1801 SITFTS-0140 DS Changes with Rejections | SUPC | REGS, SDSI | LDSO, EES, MDS, SDSO, SUPC, CSS, MDR | CSS, MDR, REGS, EES, Helix (MDS) | 3 | 30 | 8 | N | 4 | C | Yi+e | Yi+e | Yi+e |  | Y | Link, Rel, Imp/Exp - IR7
4 - Change of Data | MHHS-DEL1800 SITFTS-0135 DS Change Multiple Appts | SUPC | REGS, SDSI | LDSO, EES, SDSI, MDS, SDSO, SUPC, CSS | CSS, REGS, EES, Helix (MDS) | 1 | 42 | 8 | EC | 5 | C | Y | [5 empty] | 11 | 11 | 11 | 11 | 2 | 2 | 8 | 8 | 8 | 8
5 - Change of Metering | MHHS-DEL1808 SITFTS-0110 MS Change | SUPC | REGS | LDSO, EES, SDSC ADSC, SMSI, SMSO, AMSI, AMSO, SUPC | REGS, EES | 5 | 38 | 14 | P | 1 | C | Yi+e | Yrel | Y | Y |  |  | 12 | 12 | 12 | 12 | 17 | 17 | 1 | 1 | 1 | 1
5 - Change of Metering | MHHS-DEL1810 SITFTS-0120 MS DS Change | SUPC | REGS | LDSO, EES, MDS, SUPC, SMSI, SMSO, AMSI, AMSO, SDSI, SDSO, CSS, MDR | CSS, MDR, REGS, EES, Helix (MDS) | 5 | 4 | 17 | P | 2 | C | Y | Yi+e | Yrel | Y |  |  | 13 | 13 | 13 | 13 | 18 | 18 | 2 | 2 | 2 | 2
5 - Change of Metering | MHHS-DEL1811 SITFTS-0190 MS DS Appointment Change | SUPC | REGS, SMSI, SDSI, AMSI, ADSI, UMSO, UMSDS | LDSO, EES, MDS,SUPC | REGS, EES, Helix (MDS) | 5 | 26 | 18 | P | 3 | C | Y | Yrel | Yi+e | Y |  |  | 14 | 14 | 14 | 14 | 19 | 19 | 3 | 3 | 3 | 3
5 - Change of Metering | MHHS-DEL1807 SITFTS-0105 MS Change during COS | SUPC | REGS,SMSI, AMSI, | LDSO, EES, SUPC, SMSO, AMSO, SDSC, ADSC, CSS | REGS, EES, CSS | 6 | 29 | 12 | P | 4 | C | Y | Y |  | Y |  |  | 15 | 15 | 15 | 15 | 20 | 20 | 4 | 4 | 4 | 4
5 - Change of Metering | MHHS-DEL1809 SITFTS-0115 MS Change with old MS Meter Update | SUPC | REGS | LDSO, EES, SDSC, SMSI, SMSO, SUPC | REGS, EES | 2 | 29 | 7 | EC | 5 | C | Y | [5 empty] | 16 | 16 | 16 | 16 | 21 | 21 | 5 | 5 | 5 | 5
5 - Change of Metering | MHHS-DEL1812 SITFTS-0200 MS DS Appointment Change Rejection | SUPC | REGS, SUPC | LDSO, EES SMSI, SMSO, AMSI AMSO, SDSI SDSO, ADSI, ADSO | REGS, EES | 2 | 7 | 13 | N | 6 | C | Y | Y |  |  |  |  | 17 | 17 | 17 | 17 | 22 | 22 | 6 | 6 | 6 | 6
6 - Metering Changes | MHHS-DEL1916 SITFTS-0860 MET Market Segment Change | SUPC | LDSO, SMSI, REGS, SDSI, AMSO, AMSI, SMSO | SUPC, SDSC, ADSO, MDS, EES, ADSI, SDSO | REGS, EES, Helix (MDS) | 4 | 90 | 14 | P | 3 | C | Y | Y | Y |  |  |  | 18 | 18 | 18 | 18 | 3 | 3 | 9 | 9 | 9 | 9
6 - Metering Changes | MHHS-DEL1918 SITFTS-0870 MET Connect Type Change (MS) | SUPC | LDSO, REGS, SMSI, SDSI, AMSO, MSAI, AMSI | MDS, EES, ADSO, ADSI | REGS, EES, Helix (MDS) | 2 | 94 | 12 | P | 4 | C |  | Y |  |  |  |  | 19 | 19 | 19 | 19 | 4 | 4 | 10 | 10 | 10 | 10
6 - Metering Changes | MHHS-DEL1919 SITFTS-0880 MET Connect Type Change with missing Services (MS) | SUPC | LDSO,SMSI, REGS, AMSI, | SDSI, EES, MDS, AMSO, ADSO, ADSI, ADSC, AMSC, SUPC | REGS, EES, Helix (MDS) | 2 | 114 | 14 | EC | 5 | C |  | Y |  |  |  |  | 20 | 20 | 20 | 20 | 5 | 5 | 11 | 11 | 11 | 11
6 - Metering Changes | MHHS-DEL1890 SITFTS-0845 MET DISCONNECT During COS DS MS Appts Lapse | SUPI | REGS, SMSC, SUPC, LDSO, AMSC, | SDSC, EES, MDS, SMSI, SDSI, SUPI, CSS | REGS, EES, CSS, Helix (MDS) | 3 | 86 | 12 | EC | 6 | C | Y | Y | Y |  |  | IF-50 | 21 | 21 | 21 | 21 | 6 | 6 | 12 | 12 | 12 | 12
6 - Metering Changes | MHHS-DEL1892 SITFTS-0855 MET DISCONNECT Linked Export only | SUPC | SMSC, LDSO, REGS, AMSC | SDSC, EES, MDS, SUPL, ADSC, SUPC, CSS | REGS, EES, CSS, Helix (MDS) | 2 | 71 | 10 | EC | 6 | C | YL | YL |  |  | Y | Link, Rel, Imp/Exp - IR7
6 - Metering Changes | MHHS-DEL1917 SITFTS-0862 MET Change of Market Segment with Cos | SUPI | CSS, SUPI, SUPO, SUPC, REGS, LDSO | AMSI, MDS, EES, SMSO, SDSO, ADSC, ADSI, CSS | REGS, EES, CSS, Helix (MDS) | 1 | 103 | 14 | EC | 6 | C | Y | [5 empty] | 22 | 22 | 22 | 22 | 7 | 7 | 13 | 13 | 13 | 13
7 - Consumption | MHHS-DEL1937 SITFTS-0012 CONS CoS Transfer of Reads | SUPI, SUPC | SUPI, SUPC, REGS, SDSC, ADSC, UMSDS, AMSC, SMSC, CSS, UMSO | EES, MDS, CSS | REGS, EES, CSS, Helix (MDS) | 6 | 37 | 9 | P | 1 | C | Y | Yi+e | Y | Y |  |  | 8 | 8 | 8 | 8 | 15 | 15 | 21 | 21 | 21 | 21
7 - Consumption | MHHS-DEL1938 SITFTS-0132 CONS DS Change Transfer of Reads | SUPC | SUPC, REGS, SDSI, ADSI, SDSO, ADSO, UMSDSI, UMSDSO, CSS | LDSO, EES, CSS | REGS, EES, CSS | 4 | 9 | 6 | P | 1 | C | Y | Yi+e | Yrel | Y |  |  | 9 | 9 | 9 | 9 | 16 | 16 | 22 | 22 | 22 | 22