## Utilita
Organisation: | Utilita Energy |  | MHHS-DEL2446 SIT Operational Data Approach comments Log v1.0
Constituency: | Supplier, MSS/MSA
Date: | 2024-04-04
Anonymised: | Yes
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete |  |  |  |  | Programme to complete once consultation window has closed.
Comment Reference | Reviewer | Artefact Reference and Name (Please select from drop down list) | Document Section/Process Step | Comment | Suggested Change | Response | Status
| Utilita Energy |  |  | Column D does not enable a participant to select the document DEL-2446 as it only has options for the Migration Framework documents |  | As part of the programme governance it was agreed that links would not be included in documents. Please review in the Collaberation base. | acknowledgement
| Utilita Energy |  |  | Page 10 Section 8: It is mentioned that PPs "may be asked to reset their systems to that state before the start of the execution of the non-functional and operational tests" - if this is something that is required during this phase of testing, please can clarification be given on: 1. How participants will be informed of this 2. How timelines will be adjusted to factor in this task and any associated delays caused to testing execution | Further information to be provided on this | Participants will be provided with a 2 week notice period to reset their systems - this will be communicated via an email and bi-lateral meetings. We will align this with maintenance and deployment of change windows. | acknowledgement
Utilita Energy

## Elexon
Organisation: | Elexon Ltd. |  | MHHS-DEL2446 SIT Operational Data Approach comments Log v1.0
Constituency:
Date: | 2024-04-08
Anonymised:
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete |  |  |  |  | Programme to complete once consultation window has closed.
Comment Reference | Reviewer | Artefact Reference and Name (Please select from drop down list) | Document Section/Process Step | Comment | Suggested Change | Response | Status
1 | Sailaja Puthota |  | 7.1 E2E Choreography | We have received a total of apprx.ly 7500 MPANS for SITF Cyce1. Are we expecting the remaining MPANS as part of other SITF Cycles? |  | Yes that’s correct. 3500 for Cycle 2 Functional tests, 4,000 MPANS for migration. A refreshed 10,000 MPANS for settlement testing in the SITB environment.
2 | Sailaja Puthota |  | 7.1 E2E Choreography | When can we expect a data loading schedule for this SIT Operation testing |  | This is detailed in section 10 of the document Detailed plans will be published Mid May in the DWG
3 | Sailaja Puthota |  | 7.1 E2E Choreography | Are we expecting any new MPIDS or Market participant roles or any data updates for ISD data for SIT Operational testing |  | Yes there will be a requirement to update ISD as new market partipants could be added or existing market participants could be removed, specifically for onboarding/off boarding tests.
4 |  |  | 7.1 #2 PP and DIP Bilateral | Assuming this data would be provided by MHHS,Do we have a tentative timeline by when this data would be available for loading in SITB? |  | As per last section of the document section 10.
5 |  |  | 7.3 Test Data Generators | Is it correct to assume that the consumption data would be sent by participants to Helix system during the SIT operational testing and hence Helix system doesn’t require to generate any consumption data? |  | That’s a correct assumption
6 |  |  | 6.1 | section 5.3 of the test approach document states that BCDR would be proven by assurance/static testing. However, this section refers to any data present in the system. Please could you align this with the description in the test approach document? |  | Thank you we will align
7 |  |  | 6.1 | This CR is yet to be discussed and details approved and therefore is out of the scope for this SIT Operational test. It will need to go through the change management process referred to in this document. |  | Noted
8 |  |  | 7.3 Test Data Generators | Please could you confirm whether we can use our own data generators or we need to use one provided by yourselves or re-used from CIT Functional? |  | Yes you are able to use your own data generators. Note added to the documents - Number 4

## RECCo
Organisation: | RECCo |  | MHHS-DEL2446 SIT Operational Data Approach comments Log v1.0
Constituency: | Central Party / Code Body
Date: | 2024-04-09
Anonymised:
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete |  |  |  |  | Programme to complete once consultation window has closed.
Comment Reference | Reviewer | Artefact Reference and Name (Please select from drop down list) | Document Section/Process Step | Comment | Suggested Change | Response | Status
| Jonny Moore |  |  | We have no comments on the Test Data Approach and Plan.
Utilita Energy

## Triage Status (hidden)
Triage status​ | Description​​
Accepted ​​ | Comment has been accepted and change has been made to the artefacts
Rejected​​ | Comment reject - No change will be made to artefacts
Acknowledge​​ | Comment is not related to Consultation 1 Artefacts but may be picked up in a later tranche or within other workstreams.
Requires further clarification with PP​​ | Comment is not fully understood by the Migration Team and requires clarification with the comment raiser.​​​
Clarification Provided​​ | No change made - clarification is provided in response to reviewers comment​​

## Control Sheet (hidden)
Artefact
MHHS-DEL2426-[01]-Migration Framework Foundations v0.1
MHHS-DEL2427-[02]-Migration Framework-Principles and Guidelines v0.1
MHHS-DEL2428-[03[-Migration Capacity Calculations-Method Statement v0.1
MHHS-DEL2429-[03a]-Migration Capacity Calculations-Parameters v0.1
MHHS-DEL2430-[04]-Migration Requirements and Processes v0.1
MHHS-DEL2431-[04a]-Migration Business Process Models v0.1