## Consolidated Log
Home
MHHS-DEL3422 - SIT Regression Testing Test Approach and Plan Comments Log
*Organisation: | Various |  | Please add your comments to the template below, ensuring that you fill all of the mandatory columns marked with an *. If you have no comments and want to confirm you have reviewed the document, please input 'Confirmed Reviewed' in the Comment box and 'n/a' for the remaining boxes. Where mandatory columns have not been filled, these comments may be rejected or the sender may be asked to provide more detail.
*Constituency:
*Comment Owner Anonymised:
*Date: | 2025-02-07
Comment ID | *Ref # | *Comment | *Suggested Change | *Impact of not making the Change | *Comment Owner
To be populated by the Programme | Input the Ref # of the area of the document you are commenting on | *Succinctly state the comment and the basis for the concern | *Provide detail of the change or action required to resolve the comment | *Provide a rationale for the change detailing the impact or materiality as a result of not making the recommended change | *Provide the name of person providing the comment | Action (Accept/Reject) | Response | Comment Status (Complete/Pending)
E.On UK | 2.1.2 Three Sprint Approach | Its's expected to complete the Regression tests within a sprint i.e. 2 week time. Its very optimistic to run the tests within 2 weeks without having the regression test scenarios in place. | There should be caveat that its expectation but it can be confirmed only after the test scenarios have been agreed and assessment has been done with respect to execution timing. | Document is giving confidence with respect to running regression suite within 2 weeks without supporting details and it can impact the Go-Live schedule if its not planned and executed carefully. | Grijesh Singh | Reject | In section 7.1.1.3, the document states "The intention is the Core Regression Test pack will be sized according to a reasonable test velocity from a SIT Functional & Migration sprint. This will allow for a balance between achievability and breadth of coverage. It should be noted that the Core Regression Test pack will be much smaller than the scope of SIT Functional and SIT Migration Testing: essentially it will be the size of one sprint."
E.On UK | 2.1.3 Pre-Regression Settlement Tests | Settling Normally and testing accuracy report is also part of regression testing but this section is giving the impression that its's not part of regression testing. | Clarity is required that Settling Normally and testing accuracy report is also part of regression testing. | There is no material impact. Its just about clarity. | Grijesh Singh | Accept | Added "This is considered a part of Regression Testing."
E.On UK | 2.1.5 Operational and Non-Functional Tests | Its not mentioned that when decision will be made related to identified tests for running alongside or after Operational test phase in SIT B env. | Decision point needs to be mentioned as there should be specific reason for not arriving on decision at this point. | It will provide the clarity for the resource requirement to support this phase. | Grijesh Singh | Reject | The Regression Test Pack schedule is stated in section 8.2.1, SIT Regression SI Preparation Schedule.
E.On UK | 3.5.1 Assumptions | Operational and Non-Functional regression tests are expected to run alongside with these phases but no reason has been provided that adding these wouldn't impact the timeline for these phases. | There should be some reason for supporting these assumptions otherwise it would impact timeline. | It would provide the confidence to have this assumption. | Grijesh Singh | Reject | Operational and Non-Functional tests are only going to be considered as part of the construction of the Core Regression Test Pack. One of the criteria will be practicality of running the tests.
E.On UK | 5.1 In Scope | As per regression approach, production scenario would be imitated for creating the required data for a scenario. This may result running the migration tests and few functional tests to have the pre-requisite for a specific test scenario in regression scope. | This should be clarified as it may drive additional effort for running a test in scope. | If data would be created by running scenarios then it should be quantified otherwise it would impact the test schedule. | Grijesh Singh | Reject | This is covered in Section 7.1.2 Test Data
E.On UK | 5.2 Out of Scope | Test scripts defect shouldn't be out of scope. Regression tests are not new and it should have been run successfully in previous phases but any required correction shouldn't be out of scope. | This should be part of assumption that test script change wouldn't be required. | There is no material impact. Its just about clarity. | Grijesh Singh | Reject | The document states "We will use the latest versions of the test scripts." This should include any fixes applied as a result of test script defects and therefore is addressed.
E.On UK | 6 Test Architecture and Coverage | SIT Regression testing will happen in SIT A env isn't fully correct as Non-Functional and Operational will happen in SIT B env. | Correction of the details. | There is no material impact. Its just about clarity. | Grijesh Singh | Accept | Added "Additionally, any Operational or Non-Functional Tests included in the Core Regression Test Pack must be run in the SIT-B environment, which is also under current use by the programme."
E.On UK | 6 3rd Point | SIT A env will be in use for SIT F and M for Non-MVC participants during the regression testing. If all the previous MPANs have been removed from DIP and Helix to imitate the Production Go-Live scenario then it would impact the Non-MVC SIT Testing. | It should be clarified that Non-MVC related MPANs would be retained in DIP and Helix. | Approach has impact on Non-MVC SIT. | Grijesh Singh | Accept | Added "3)a. Non-MVC participants will need to restart any tests in flight, as no MPANs will be retained."
E.On UK | 6 4th Point | DIP and Helix will start with no data isn't correct as it will have the data for the Non-MVC SIT participants. | It should be clarified that Non-MVC participants related data would be present in DIP and Helix at the start of Migration. | Approach has impact on Non-MVC SIT. | Grijesh Singh | Accept | Amended
E.On UK | 7.1.2.2 Test Data in DIP | Clearing DIP fully will impact the Non-MVC SIT. | Historic Data should can be cleared only for MVC participants. | Approach has impact on Non-MVC SIT. | Grijesh Singh | Reject | Non-MVC must restart tests.
E.On UK | 7.1.2.3 Test Data in Helix | Clearing Helix fully will impact the Non-MVC SIT. | Historic Data should can be cleared only for MVC participants. | Approach has impact on Non-MVC SIT. | Grijesh Singh | Reject | Non-MVC must restart tests.
E.On UK | 7.1.4 Participant Preparation | Does Programme will create a template that Participant needs to fill as a readiness report. | Clarity regarding the Participants Test Readiness status reporting. | There is no material impact. Its just about clarity. | Grijesh Singh | Accept | Removed references to Participant Readiness Report.
E.On UK | 7.1.5 Test Entry Criteria | Its mentioned that SIT PP pairing will be same as at the end of the SIT test phase but its not clarified in the document that test where pairing is required needs to be run both paired cohort. | Cross cohort tests are also in scope so approach related to this needs to be clarified. | Cross cohort tests are generally long tests so clarity is required if both the paired cohort need to run. | Grijesh Singh | Accept | Added "This is for the purpose of any paired-cohort tests in the Core Regression Test Pack."
E.On UK | 7.2.9 Participant Test Completion Report | Its expected that this report would be looking the Participant related open defect and work off plan only. If there is no open defect then this report doesn't make any sense as all the information is available with the Programme. | SIT Phase is managed by Programme and participant have responsibility with respect to their own system only. | Clarity is required to set the expectation. | Grijesh Singh | Reject | The Programme can see this point but for traceability and assurance purposes a Participant Regression Test Completion Report will still be required.
E.On UK | 8.2.2 | Its expected that PP SIT Cycle 3 completion report would be looking the Participant related open defect and work off plan only. If there is no open defect then this report doesn't make any sense as all the information is available with the Programme. | SIT Phase is managed by Programme and participant have responsibility with respect to their own system only. | Clarity is required to set the expectation. | Grijesh Singh | Reject | The Programme can see this point but for traceability and assurance purposes a Participant Regression Test Completion Report will still be required.
Eon Next | p6 Executive Summary | This should outline the purpose of the Regression Approach & Plan and what it aims to articulate for PPs and set the scene for the follow on deliverables/artefacts e.g. test suite, 'scoring' criteria etc | Potential for review and changes to be made to the summary |  | Ellie & Fi | Accept | Added two sentences on the purpose of regression testing to Section 2.0. Added a sentence referring to artefacts in Section 2.1.1.
Eon Next | p6 The E2E Testing and Integration Strategy defines that “System Integration Testing (SIT) will include functional, non-functional, operational and migration testing. Each of these elements will have a set of regression tests to verify change/defect fixes.This document sets out regression testing for each of the above phases, where appropriate." | Contradicts itself by stating 'only where appropriate' - Regression Tests should be approached across all SIT Phases. | Potential for review and changes to be made |  | Ellie & Fi | Accept | Added clarification: "where deemed appropriate through the test scoring process outlined below."
Eon Next | 2.1 Regression HL Overview | Consider resequencing the doc so section 2 is the scope for the document so as to flow better | Potential for review and changes to be made |  | Ellie & Fi | Reject | The high level overview is a subsection of the Executive Summary and should be used for those who cannot read the detail in the document as a whole.
Eon Next | 2.1.2 The main phase of regression testing will be divided into three sprints: the first will drive out regression test defects. If it runs smoothly and successfully, there will be an option to exit Regression Testing early. | Surely this is dependent on how many tests need to be run in order to find the defects in the first sprint (believe this will be 2 or 3 weeks)? | Programme to review/respond |  | Ellie & Fi | Reject | The velocity of the MVC cohorts in the later stages of Cycle 3 will be used to determine the size of the sprint, and the scoring process will determine the scope of tests included in the Core Pack. What needs to be run will be determined by the scoring process, as recommended through SITWG.
Eon Next | 2.1.2 The number of tests will be derived from the velocity of the Minimum Viable Cohort (MVC) participants in a specified sprint (to be determined). | This was our initial comment before the detail came to life later in the document, wish to share so as to recognise our line of thought We disagree with the 3 sprint approach here as Programme is constraining the scope of regression testing to the number of tests that a performing cohort can run in a 2/3-week window. At Nov SITWG, Next suggested programme do not constrain scope based on time so as to reach a better / rounded / quality suite of test areas to prioritise. The Programme should start with MoSCoW and then understand the sprint approach - you may require cohorts to execute the scope in similar way to Settlement testing to ensure coverage | Programme to review/respond |  | Ellie & Fi | Accept | Added "The detail of scope will be addressed in section 7, but will be determined through the scoring process."
Eon Next | 2.1.4 Non-MVC cohorts will be able to continue with any unfinished SIT Functional (SITF) and SIT Migration (SITM) tests in the SIT- A environment once the CoS Settlement tests have completed. Then, they can run regression testing in parallel with the MVC cohorts. | Programme should consider making this explicitly clear in terms of what non-MVC PPs will have to run concurrently with regression based on the POAP - will non-MVC have to complete the same exit criteria for cycle 3 (100% execution, 85% pass) before commencing regression? | Programme to review/respond |  | Ellie & Fi | Reject | This is explicitly clear in Section 7.1.5 Test Entry Criteria
Eon Next | 2.1.5 Operational and Non-Functional Tests will be scored and evaluated as part of the construction of the Core Regression Test Pack. However, it is expected that any tests added to the Core Regression Test Pack from these test phases will be conducted in the SIT-B environment alongside or after the end of the Operational Test phase. | How much time in SIT B is there in order to do this - if Ops completion is 4/7, will programme extend a SIT B NFT/Ops window between 4/7 and 8/8 when regression ends in SIT A as per POAP? Do Programme have a financial/operational constraint on when SIT B is going to be decommissioned? | Programme to review/respond |  | Ellie & Fi | Reject | Part of the scoring process will address the feasibility of running Operational and Non-Functional tests as part of the regression process. The Programme did not want to rule them out of scope at this stage without going through the process.
Eon Next | 2.2 Figure 1 – Detail of Programme Plan on a Page, showing the Regression Test Phase | What date / version is this - should be referenced? | Programme to review/respond |  | Ellie & Fi | Accept | Added version 3.0 to Figures 1 and 6
Eon Next | 2.2 Figure 1 - Code freeze 16 June | This is not referred to at all in the whole document - this is the underlying code base for go live and therefore should be discussed in the A&P within an environments section and/or Test Preparation section | Programme to review/respond |  | Ellie & Fi | Reject | This Code Freeze is considered beyond the scope of this document and should be addressed through communications with the Programme.
Eon Next | 2.2 Figure 1 - 16 June to 8 August | SIT Regression phase is referred to as 7 weeks within the document yet on the calendar this is 8 weeks | Programme to review/respond |  | Ellie & Fi | Accept | Amended references from seven to eight weeks.
Eon Next | 3.2 Review and approvals | This repeats earlier section - suggest remove | Programme to review/respond |  | Ellie & Fi | Accept | Deleted bullets of reviewers and approvers, but kept the process for approval of the document.
Eon Next | 3.5 Assumptions and Caveats | Suggest move behind regression scope and approach sections This should be part of a RAID section. There are no Risks, Issues and Dependencies called out in the whole document yet there are many that should be included | Programme to review/respond |  | Ellie & Fi | Reject | Follows format set out in previous programme Test Approaches and Plans.
Eon Next | 3.5.1 The following assumptions have been made in the development of this test plan: | Test Approach & Plan | Update the text |  | Ellie & Fi | Accept | changed text to 'document.'
Eon Next | 3.5.1 Assumptions | Would suggest grouping the assumptions by commonality - e.g. defects, coverage, environment etc to support PP review | Programme to review/respond |  | Ellie & Fi | Accept | Added 2 headings
Eon Next | 3rd Assumption - Regression Testing can safely overlap with SIT Operational Testing. | Consider rephrasing - Regression testing can successfully be resourced and executed by cohorts across SIT A as well as concluding SIT Operational in SIT B | Programme to review/respond |  | Ellie & Fi | Accept | Updated.
Eon Next | Assumption 5 - Participants may choose to conduct further regression testing over and above that set out by the Programme, and any tests undertaken by Participants will not affect completion of the Regression Testing Phase by MVC cohorts. | How will PPs choose further regression testing if no time capacity is allowed/available in the 7/8 weeks to achieve this? | Programme to review/respond |  | Ellie & Fi | Accept | Added "should timescales allow"
Eon Next | Assumption 8 - SIT Settlement Regression tests will... | This suggests there will be more than 1 settlement test run in regression (Settling Normally and...?) yet as we know, SIT A has reporting constraints (LDSO and Helix Accuracy reports?) - is this therefore a typo?? | Programme to review/respond |  | Ellie & Fi | Reject | Further settlement tests may be included in the Core Regression Test Pack depending on the outcome of the scoring process.
Eon Next | Assumption 8 - However, no Licenced Distribution System Operator (LDSO)’s are connected in SIT-A, and Distribution Use of System (DUoS) is not available. Thus, the full test case cannot be run in this environment. Once the rest of SITF and SITM regression testing starts, the Settling Normally test case will be impractical to run. | See above comment Is this therefore a risk for some PPs on the steps that can't be run in SIT A? What is the point in running settling normally again if all steps cannot therefore be successfully run and proven in SIT A for Regression? | Programme to review/respond |  | Ellie & Fi | Reject | The LDP and SRO agree that the risk this poses is acceptable, given environmental constraints.
Eon Next | Assumption 9 - We will plan to run 3 cycles of regression testing, executing the same set of regression test scripts. This will allow for any defects found in the first cycle to be fixed and retested during the second. The third cycle should then ensure any defect fixes have not introduced new defects. | This assumption states 'we will' as opposed to 'we assume' | Programme to review/respond |  | Ellie & Fi | Accept | Text amended to "We will run 3…"
Eon Next | Assumption 10 - Participants will be able to achieve a similar test velocity during the regression phase to that achieved in comparable SIT Functional and SIT Migration cycles. | Assumption is PP's will attempt to. This is not clear however until regression suite is known as we know that X Cohort tests (if identified for the pack) take longer and are more complex | Programme to review/respond |  | Ellie & Fi | Reject | The scope of the Core Regression Test Pack will be agreed with SITWG and will have a fundamentally achievable size given velocity from previous sprints.
Eon Next | Assumption 11 - Any SIT Operational or Non-Functional Regression tests evaluated in the core pack and deemed to be in- scope for Regression Testing can be tested in the SIT-B environment alongside the conclusion of the Operational Testing phase. | See response in row 19 | Programme to review/respond |  | Ellie & Fi | Accept | The scope of the Core Regression Test Pack will also be evaluated according to pragmatic factors with respect to time and environmental constraints.
Eon Next | Assumption 12 - The SIT Regression test window is planned for a 7-week period, and testing completes within these timescales. | Rewrite & raise related risk - The programme plan is constrained to a timebox of 7/8 weeks to conclude regression testing - any longer will risk M10 and hitting the CR055 approved baselined plan | Programme to review/respond |  | Ellie & Fi | Accept | Programme raise risk R1056 around timebox constraints. Amended to 8 weeks. | Complete
Eon Next | Assumption 13 - There are no changes to the participant cohort team makeups. | Consider rephrasing - Cohort team TOM partners - should this also consider cross cohort pairings? | Programme to review/respond |  | Ellie & Fi | Accept | Text amended to "Any changes to the participant cohort team makeups are manageable and will not impact test velocity."
Eon Next | Assumption x - NEW | New assumption - Design is stable / no further IR's to be deployed/ code freeze reference needed and what it represents for M10 readiness | Programme to review/respond |  | Ellie & Fi | Accept | Added "• Design is stable and no further Interim Releases (IRs) to be deployed."
Eon Next | 4 - Objectives | This should come before assumptions (RAID) section | Programme to review/respond |  | Ellie & Fi | Reject | Assumptions and Caveats were addressed in previous Test Approaches & Plans at this section of the document (cf SIT Functional Test Approach & Plan)
Eon Next | 5 Scope, p11 | Should come after Executive Summary | Programme to review/respond |  | Ellie & Fi | Reject | Scope was addressed in previous Test Approaches & Plans at this section of the document (cf SIT Functional Test Approach & Plan)
Eon Next | 5.1.1 SIT Functional, Migration, Operational and Non-Functional Testing | No mention of legacy regression testing that should be covered? e.g. DTN changes, affected BPs outside of legacy MPANs and Migration start/KO | Programme to review/respond |  | Ellie & Fi | Reject | Legacy regression testing is outside the scope of the Programme, as set forth in the E2E Testing & Integration Strategy.
Eon Next | Settlement tests, including “Settling Normally” when feasible. | Earlier sections confirm this test as in scope so why state "when feasible"? | Programme to review/respond |  | Ellie & Fi | Accept | Text amended
Eon Next | Migration, potentially including reverse migration. | Why point this out? Reverse migration is part of migration for many in SIT - if to be discounted, should this be considered under 'caveats'?! | Programme to review/respond |  | Ellie & Fi | Accept | Text amended
Eon Next | All of the above tests will be listed in the ‘SIT Regression Test Framework and Evaluation Score Sheet’ [REF-19]. | c 400 for functional and migration + Ops/NFT and theme 8 settlements - how big is this score sheet going to be?!! The manageability of this? It should be pointed out that SIT-F & M are coming up to 1 year of execution, having started on IR5. We are now on IR8.6 and xxx defects later - should be really considering tests that were executed in earlier cycles and have not yet returned to in later cycles on later versions of base code | Programme to review/respond |  | Ellie & Fi | Reject | Programme feels that tests passed on the oldest versions of Interim Releases are potentially higher value candidates for regression, given the number of code changes since they passed.
Eon Next | Defects, focusing on those areas which were problematic, or where P1 and P2 defects were raised. | Is this covering any party incl CPs? | Programme to review/respond |  | Ellie & Fi | Accept | Added a sub bulletpoint for clarity.
Eon Next | The SIT Regression Tests will include all theme areas below: (table 1 | This covers functional, migration yet as the section title suggests, nft and ops 'themes' need inclusion. | Programme to review/respond |  | Ellie & Fi | Accept | Added two additional rows
Eon Next | 5.1.2 - The Programme recognises there are logistical and environmental constraints around regression testing the Operational and Non-Functional Testing phases. Therefore, whilst all Operational and Non-Functional tests will be evaluated according to the SIT Regression Test Framework and Score Sheet, they will have to be executed within the currently scheduled test phases upon completion of the primary SIT tests. | Please can the A&P explicitly call out the logistical and environmental constraints? Would this be a caveat? This is a repeat/duplicate of a point already covered earlier in the document. | Programme to review/respond |  | Ellie & Fi | Accept | Added "Constraints include but are not limited to: • Test Data Load for Non-Functional Stress Tests • LDSO and DUoS availability in the SIT-A environment • Resource availability for Operational testing"
Eon Next | 5.1.3 - Test environments will remain available, should they not affect MVC regression testing. | In the plan, SIT B won't be available after 4/7/25 - what happens should it be required further for regression testing? | Programme to review/respond |  | Ellie & Fi | Accept | Programme raised Risk R1057 around the extension to SIT-B should regression testing not be complete. | Complete
Eon Next | 6. (2) The “settlement accuracy reporting” will be implemented to support CoS settlement tests. | What does this mean will be and won't be available to PPs? See rows 29 and 30 | Programme to review/respond |  | Ellie & Fi | Reject | While the full test case will not be able to be run, the Programme feels accuracy testing will be high value and valid testing despite constraints.
Eon Next | 6. (3) All previous Meter Point Administration Number (MPAN) test data will be removed from Helix and DIP | Would it be advisable to say, "in order to simulate a true likeness to Migration start, MPAN data used for SIT testing to date will be removed".. | Observation |  | Ellie & Fi | Accept | Text Amended
Eon Next | 6. (3) but those MPANs will not be utilised for regression testing. Those parties can opt to remove previous MPAN data from their systems, but it is not mandated, as some services have significant technical constraints in undertaking this activity. | New assumption/risk - new data = new challenges/defects at the start of regression phase | Observation |  | Ellie & Fi | Accept | Programme raised Risk R1058. | Complete
Eon Next | 6. (4) New test data will be provided to all central services and PPs for loading in the regression window prior to regression start, which the exception of Helix and DIP, whose environments will start within no data within them and will be populated by execution of migration processes. | Consider combining with point 3 as a full Data statement. | Observation |  | Ellie & Fi | Reject | Point understood but the Programme feels one item is about removal of data and the other is about new data.
Eon Next | p14 SIT Test participants will have proven their connectivity to the environment but will need to load a new set of regression test data and confirm readiness for testing. Please refer to section 7.1.2 Test Data for further details. | repeat of point 4 above, consider removing | Observation |  | Ellie & Fi | Accept | Removed reference to loading new data.
Eon Next | p14 In parallel with CoS Settlement Testing in SIT-A, the Programme will undertake the Settling Normally test case. It will not be feasible to do this later in the regression test schedule when the other SIT-F and SIT-M tests are being run. Additionally, it should be noted that LDSO’s are not connected to the SIT-A environment and no DUoS Billing related test steps will be able to be run. | Potential to expand the rationale as to why these steps cannot be run/achieved - see earlier points on settlement testing | Observation |  | Ellie & Fi | Reject | Programme feels that rationale behind this approach has been explained.
Eon Next | p14 SIT environments requirements are set out in ‘MHHS-DEL618 - Environment Approach & Plan’ [REF-03]. Please refer to this document for the details on: • Management and tracking environment build, and associated reference data. • Planning and allocation in the use of environments for relevant participants, including user access permissions and control. • Environment Connectivity Proving. • Maintenance, availability, and monitoring of environments, including the specification of back-ups, exports, refreshes, or roll backs. • Controlling deployments into environments, including data configuration, version control and release notes. • Tracking and coordination in resolving environment issues using the defect management workflow. • Environment requirements for the various stages within PIT, SIT and UIT phases. | The Environment Approach & Plan v3.0 has not been updated since June 2024 therefore its hard to refer to requirements when not aligned to CR055 or contain details for SIT Ops or SIT Regression phases | Observation |  | Ellie & Fi | Reject | These specific bulletpoints should still apply. | Complete
Eon Next | 7.1 test preparation - SIT Regression testing will evaluate and re-use test cases from the existing SIT Functional, Settlement, SIT and SIT Migration test pack. Additionally, Operational and Non-Functional test cases will be scored and evaluated but will need to be run during the end of the Operational test phase. | Repeat of info already covered | Observation |  | Ellie & Fi | Accept | Text amended to avoid repitition.
Eon Next | 7.1 test preparation - Before testing commences the SI Test team will prepare and walk participants through a DITL “Day in the Life” pack, providing all necessary SIT Regression execution details. It should be noted that the currently scheduled regression test window will be relatively short. Test evaluation and selection will need to be pragmatic and high value. | Preparation activities should state the same activities we have completed for all SIT Phases - e.g. test data, test environment, IR code base / code freeze (?) for all PPs, DITL, Calls etc. Could copy/paste from a previous SIT-phase A&P | Observation |  | Ellie & Fi | Reject | This is nearly the same format followed by the SIT Functional Test Approach and Plan, modified to suit this phase.
Eon Next | 7.1.1.1. Industry Programme Expert | Who's this? Plural or singular? | Programme to review/respond |  | Ellie & Fi | Accept | Amended
Eon Next | 7.1.1.1 Technical SME | This does not include a functional lead or a settlements lead | Programme to review/respond |  | Ellie & Fi | Accept | Added SIT Functional Lead. Industry Experts include Settlements lead.
Eon Next | 7.1.1.1 All Business processes listed in the scope section of this document | The themes are listed in the scope - not the processes? | Programme to review/respond |  | Ellie & Fi | Accept | Removed reference to scope section
Eon Next | 7.1.1.1 All S1 & S2 Defects raised during SIT, and Operational test phases, including those resolved by Central Party and Participants. | S1 and S2 when first raised as opposed to potential downgrade after the event? | Programme to review/respond |  | Ellie & Fi | Accept | Added "(after triage)"
Eon Next | 7.1.1.1 Defects, focusing on those areas which were problematic | CP or PP or both? | Programme to review/respond |  | Ellie & Fi | Accept | Added "for both Central Parties and Programme Participants"
Eon Next | 7.1.1.1 Code Bodies - Confirmation of key areas to be covered during SIT Regression test execution • Review of SIT Regression test pack for coverage | Particularly in light / stress against PP qualification reqs - SIT Regression takes place after the QAD final submission | Observation |  | Ellie & Fi | Accept | Added "against qualification requirements"
Eon Next | 7.1.1.1 NOTE: Participants are welcome to review further assets if they wish to supplement the Core Regression Pack. | Please can "assets" be replaced with "tests/test scripts/test cases or scenarios" Participants should advise which additional scripts they wish to run to supplement the core regression pack - however we may face 'time out' or these are considered as running > M10 as SITA sandbox activity and will not compromise SIT Completion Report and QAD sign off? How will this work in practice? | Programme to review/respond |  | Ellie & Fi | Accept | Amended to "NOTE: Participants are welcome to review further assets test scripts, cases and scenarios if they wish to supplement the Core Regression Pack. This activity is voluntary at the cohort’s discretion, and may be impacted by other programme priorities."
Eon Next | 7.1.1.2 The SI test team will create a framework to review all SITF, Settlement, SITM, Operational and Non-Functional tests and SIT defects, | SIT Tests and Defects - shorten as we know the scope covers all SIT phases. | Observation |  | Ellie & Fi | Accept | Amended
Eon Next | 7.1.1.1 We will ask the Code Bodies and Central Parties to feed into the selection criteria, by confirming the key business processes / tests which they believe should be executed during SIT Regression testing. | This is a repeat of information This excludes PPs - should PPs feed in at same time? | Programme to review/respond |  | Ellie & Fi | Accept | Added "Programme Participants"
Eon Next | 7.1.1.2 The SIT Regression selection criteria we are considering are as follows: 1) Criticality of business processes and those which will be used near Day 1, as advised by the code bodies and SI project teams. 2) Areas with a high number of Central Party defects 3) Areas with a high number of updates/DINs; temporary fixes; or where workarounds and “passed with observations” were used 4) Areas where there has been high Test Case volatility 5) Tests passed against earlier versions of code (e.g. IR 5 or IR 7) 6) Tests that passed with workarounds, declaration, or observations 7) LDP/SRO assessment | Duplicated the same information as the above table - keep one or the other | Observation |  | Ellie & Fi | Accept | Removed earlier criteria list
Eon Next | 7.1.1.2 The following will be reviewed in the scoring process and considered for inclusion in the regression test pack, ensuring comprehensive Regression test coverage: • All business processes and themes, focusing on the key business processes, and including coverage of central parties’ processes (these can be found in the Collaboration SharePoint site.) • All Parties and Party roles • Areas where there have been multiple cohorts with the same tests which have been “passed with observations” and/or “passed with workarounds” • Areas which were problematic, especially those where P1 and P2 defects were raised. • Areas where we advised the participants to use a workaround, or “pass tests with observations”, during test execution, for example MDR Appointments related to CR56; and SEG changes. • Areas where there were many Change requests / DINs and Temporary fixes delivered during execution | See row 65 comment | Observation |  | Ellie & Fi | Accept | Added "• Environmental constraints (eg SIT-B connectivity and timelines)"
Eon Next | 7.1.1.3 The intention is the Core Regression Test pack will be sized according to a reasonable test velocity from a SIT Functional & Migration sprint. This will allow for a balance between achievability and breadth of coverage. | Repeat from earlier in the doc - row 17 | Observation |  | Ellie & Fi | Reject | Accepted but the programme feels the point is important to note in both sections.
Eon Next | 7.1.1.3 It should be noted that the Core Regression Test pack will be much smaller than the scope of SIT Functional and SIT Migration Testing: essentially it will be the size of one sprint. | Based on current execution velocity and understanding whether Regression cycle 1/sprint 1 will be a 2 or 3 week window, the maximum number of tests cohort B have passed at full velocity and not having stopped for a maintenance window is sprint 8 (3 weeks) 62 tests - average is lower than this. Max recommend would be 40 for 3 weeks, 30 for 2 weeks subject to length / steps / complexity / pairing or single cohort / MPANs required No of tests should be based on a minimum of 10% / maximum 20% of total test cases/scripts run. This next comment was written prior to us then reading that all tests had to be run in one sprint/cycle and then repeated subject to defects: Expectation if keeping to the 7/8 weeks would be that tests would cover a 6 week period leaving a week for re-run following defects/queries - c 50-60 tests (min 20% coverage of your total tests) covering Smart, Trad, Advanced, UMS. Single cohort/joint cohort. | Programme to review/respond |  | Ellie & Fi | Reject | Programme feels it is too early to predict 'point value' for sprint size.
Eon Next | 7.1.1.3 Migration (SITM), including reverse migration • SIT Functional (SITF) • Settlement testing, including Settling Normally. NB this test case must be run in parallel with CoS Settlement testing in SIT-A, not alongside the rest of the Core Pack • Operational and/or Non-Functional End-to-End Tests, as needed | This alone feels greater than 1 sprint/cycle's worth of effort, esp point in row 71 and 'dress rehearsal' and anything else required to support this and MWG requirements | Observation |  | Ellie & Fi | Reject | Note the Settling Normally test case will not be executed during the regression sprints, and the Operational and/or Non-Functional tests should be different resources in a different environment.
Eon Next | 7.1.1.4 of or after the completion of Operational Testing in the SIT-B environment. These tests should be selected for both achievability and value provided. | Point already made above Need to know when these will be executed in SIT B in parallel to the timing of SIT A activity - POAP to show? Assume 4/7 to 8/8 in SIT B in parallel to regression in A? | Repeat of earlier points re timing/availability of SIT B |  | Ellie & Fi | Reject | Previous references to O/NFT have not explicityly called out achievability and value as criteria.
Eon Next | 7.1.1.5 Dress Rehearsal of the migration process, to migrate legacy MPANs into an MHHS state • Tests which will mimic processes used near Day 1 of live operations • Key MHHS business processes and customer journeys | 3rd bullet very wide scope - if conducting a review and scoring exercise/framework, all scope is therefore prioritised? Unless the scoring structure is then prioritised but PPs need to complete the whole scope?!! The document should make it clear that in order for regression tests to run, tests will start at clean legacy MPAN to move into migration to allow other tests to be run on that data set - this isn't prioritisation, this is the running order for execution. See row 69 | Observation |  | Ellie & Fi | Accept | Added "Test prioritisation will be fully transparent throughout the scoring process and in the Core Regression Test Pack when distributed to Programme Participants."
Eon Next | 7.1.1.6 The Core SIT Regression test pack will undergo the following review, consultation, and approval process: 1) LDP Peer Review 2) SRO and Design Team Review 3) Code body review 4) Central party review 5) Participant review 6) SITWG Review / Consultation 7) SITAG Approval The Cohort Regression test pack will undergo the following review, consultation, and approval process: 1) LDP Peer Review 2) SRO and Design Team Review 3) Participant review 4) SITWG Review / Consultation 5) SITAG Approval | Repeat of earlier info - consolidate | Observation |  | Ellie & Fi | Reject | Not on the Test Pack, but identical process to the Test Approach & Plan.
Eon Next | Supplemental Testing to the Core Pack The SIT Regression Test pack [REF-20] should be seen as the minimum testing coverage required for regression test purposes. We encourage cohorts to seek to run additional tests to ensure their individual solutions are robust, especially with respect to any internal defects. The Programme feels this is an opportunity that may not be available after the scheduled Regression Test period. | Repeat/expansion of page 17 statement. Can Programme confirm whether CP support will be available to PPs post regression completion (and core pack) at 8/8 to run these? If Programme is encouraging cohorts to run additional tests, is the expectation the amount selected could be run in the remaining 4/5 week window assuming the programme only provide enough tests for 1 sprint (2 or 3 weeks) How does this apply to Non-MVC cohorts? | Programme to review/respond |  | Ellie & Fi | Accept | Added "It should be noted the Programme will endeavour to support cohorts in these efforts but programme milestones and timelines may take precedence, so this should be a factor in any decision to run additional tests."
Eon Next | 7.1.2 Prior to SIT Regression Test commencement, the SI Data team will ensure all necessary data pre-requisites have been implemented and identify sets of suitable data and data generators that participants can use for each of their SIT test cases in scope. | Consider being clear as to data requirements for SIT A & those that may be required for SIT B subject to evaluation/scoring and outcome of SIT-NFT and Operational once it starts in March for PPs | Programme to review/respond |  | Ellie & Fi | Reject | Data requirements are dependent on the exact tests to be run; we have a good idea of what will be in the pack but it is difficult to give requirements that will cover all possibilties at this point. Programme expects this to be shared in a timely manner with participants.
Eon Next | 7.1.2 Initially PPs will execute the migration business processes for a defined set of MPANs (which will be <400 MPANs across all Cohorts) to support CoS Settlement tests. | If 50 per cohort will be allocated for COS Settlement testing in SIT A 19/5-13/6, when will the other 1000 MPANs per cohort be provided supporting Regression from 16/6 so as not to impact COS Settlement testing - or will all 1050 be provided at the same time during the 15d maintenance window? | Programme to review/respond |  | Ellie & Fi | Accept | Added "All MPANs will be provided at the same time as all will start in a legacy state, the 400 settlement MPANs will be migrated to MHHS first. Following completion of settlement testing further MPANs will be migrated to support regression tests."
Eon Next | 7.1.4 Participants to review tests for SIT Regression testing as part of the Core Regression Pack. | and additional supplementary tests we wish to run as per above comments? | Programme to review/respond |  | Ellie & Fi | Accept | Added "Participants may also wish to assess any supplementary tests they wish to run in addition to the Core Regression Test Pack."
Eon Next | 7.1.4 SIT-A Environment connectivity confirmed. Helix to send an IF-047, which all participants will need to confirm receipt of. Data Services to send an IF-021 and provide confirmation the message was successfully delivered to the DIP, by checking the DIP Portal. o NB this will be done during the CoS Settlement tests taking place in the SIT-A environment preceding the main phase of Regression Testing. | Need to call out SIT B environment connectivity also subject to NFT/Ops scope requirements as part of test suite review and scoring | Programme to review/respond |  | Ellie & Fi | Accept | Added "• SIT-B Environment connectivity confirmed, subject to Operational and Non-Functional tests in scope."
Eon Next | 7.1.5 Test Entry Criteria | Please confirm / placeholder the need for PPs to enter Regression on IRx and whether this creates a code freeze for ensuring robustness on the code base / Design stability that is intended for production from 22 October 2025 (M11/12) | Programme to review/respond |  | Ellie & Fi | Reject | As this document is being written and reviewed in February 2025, this request is outside the scope of the test approach and plan. The specific IR for production will be communicated to all SIT participants by the Programme.
Eon Next | 7.1.5 Non-Functional Testing has completed its exit criteria. | What is the exit criteria for non-functional SIT? Its been called out for SIT-F & M? | Programme to review/respond |  | Ellie & Fi | Accept | Amended exit criteria section to include Non-Functional Testing.
Eon Next | 7.1.5 COS Settlement testing in the SIT-A environment has been completed (NB this is an interim point after Settlement Regression testing has started and will address the start of SIT Functional and Migration Regression testing). | Is there an assumption that there will be a caveat within the SIT-F completion report for SIT A COS Settlement testing as this won't have concluded when the report is submitted? | Programme to review/respond |  | Ellie & Fi | Accept | Added "Note: Participants may have to include a caveat should this testing not be complete in their own test completion reports."
Eon Next | 7.1.5 NB Operational testing will not be scheduled to be complete by the time Regression testing is due to start. | Move up to sit under NFT bullet point | Observation |  | Ellie & Fi | Accept | Done
Eon Next | The following deliverables have been produced by the SI team, reviewed, assured, and approved as appropriate for the test stage: | Rephrase - "The following artefacts are required for test entry into regression by the Programme:" | Observation |  | Ellie & Fi | Accept | Done
Eon Next | SIT PP pairing confirmed. This will be the same pairings as at the end of the SIT test phase. | SIT Functional test phase | Observation |  | Ellie & Fi | Accept | Done
Eon Next | SIT-A Environment has been confirmed as ready | And arrangements for SIT B environment should NFT/Ops SIT require regression tests to be run post-Operational completing 4/7 | Programme to review/respond |  | Ellie & Fi | Accept | Added"• SIT-B Environment has been confirmed as ready based on Operational or Non-Functional Tests."
Eon Next | Evidence of a successful SIT Cycle 3 Completion has been submitted, assured by the SI and any work off plans agreed and tracked. | State SIT Completion report | Observation |  | Ellie & Fi | Accept | Added "(including a SIT Completion Report)"
Eon Next | 7.2 The SIT Regression approach will test process flows through the full MHHS lifecycles and customer journeys, using tests that are selected to be part of the Core Regression Test Pack. | (...Not in one sprint it won't! ;) | Observation |  | Ellie & Fi | Accept | Removed words "the full"
Eon Next | 7.2 The environment will be setup to simulate a position as close to a legacy state as possible, i.e. where there are no MPANs or participants currently in the market. Testing will commence in parallel with the currently scheduled CoS Settlement tests in the SIT-A environment; the Settling Normally test case will be the only regression test in scope at this time. C&C will be asked to check that the MPANs have been correctly migrated into the EES system. | Repeat | Observation |  | Ellie & Fi | Accept | Clarification: this was context for the additional test execution activity in the first week of testing. Added "After CoS Settlement testing is complete, there will be a full week of migration activities scheduled to condition MPANs for subsequent testing." and this activity added to Section 8.3 Test Execution Schedule.
Eon Next | 7.2 Once those tests have completed the environment constraints (e.g. no more than 400 MHHS MPANs present within Helix) will be removed and SIT-A will then support... | CPs only remove? When if COS Settlements concludes on 13/6 and Regression starts 16/6 - what's the timeframe for this to happen and not create an issue / delay with commencing on 16th june? | Programme to review/respond |  | Ellie & Fi | Accept | Changed the first week of the regression schedule for migration of legacy MPANs. Apart from the migration runs, there should be no delay as MPANs used for regression will already have been loaded in a legacy state.
Eon Next | If all tests pass and no Severity 1 or Severity 2 defects are outstanding, there will be a checkpoint scheduled to assess whether the Regression Phase can complete early. | What about PP supplementary tests as raised above? | Programme to review/respond |  | Ellie & Fi | Reject | Supplementary tests are voluntary and may be superseded by programme priorities. If any Central Party P1/P2 defects are found, they will be triaged and scheduled for fixes; however there will be an additional criterion around impact to programme milestones. Non-Central Party defects should not be considered as a criterion to impact programme milestones.
Eon Next | Otherwise, the plan will be to run the Core SIT Regression test pack 3 times: | As previously stated not convinced you will run all functionality across 1 sprint let alone > 3 times. Again, no word here of when PPs will run their supplementary tests if having to execute the same tests multiple times. | Programme to review/respond |  | Ellie & Fi | Reject | Supplementary tests are voluntary and may be superseded by programme priorities.
Eon Next | we will monitor defects raised and only put forward S1 and S2 CP defects for release. | What will happen with S3 and 4 defects? How / when will these be addressed or not? Who will own them once regression concludes? If SIT Non-MVC parties don't complete Regression but find S1-4 defect after 8/8, how will this be managed by the Programme with regards to M10 readiness for SIT MVC? | Programme to review/respond |  | Ellie & Fi | Accept | Added "S3 and S4 defects will be subject to work off plans created in conjunction with the Programme. Any defects found in Non-MVC cohorts will be added to the programme backlog, triaged and prioritised."
Eon Next | All cohorts will execute the Core SIT Regression test pack. | MVC and Non-MVC? Assuming different start times dependent on Non-MVC submitting their Functional/Migration completion reports (in line with the test entry criteria above)? | Programme to review/respond |  | Ellie & Fi | Accept | Added "(MVC and Non-MVC)"
Eon Next | The day-to-day test execution approach will remain the same as that used during the SIT Cycle 3 test phase. | including for Non-MVC who may start / finish regression later? | Programme to review/respond |  | Ellie & Fi | Accept | Added "including Non-MVC who may finish later during SIT Non-MVC Support."
Eon Next | Each SIT PP will be required and obligated to support other participants’ testing, | Assuming this means Cross cohort testing/pairings | Observation |  | Ellie & Fi | Accept | Yes.
Eon Next | 7.2.1 if the test can then be concluded successfully the test will be reset from “fail” to “pass”. | This is not possible in ADO; it would require the test to be restarted and any previous evidence to be transferred across which is a manual task which can be time consuming | Programme to review/respond |  | Ellie & Fi | Accept | Removed sentence. No intention to change current SITF and SITM processes.
Eon Next | There is also the possibility of marking a test “not applicable” by agreement of all parties concerned and on recording of a valid reason in a defect. | There should be NO 'not applicable' tests if undergoing review/scoring to create a core regression test suite. All will be applicable | Observation |  | Ellie & Fi | Accept | Agreed. Removed sentence.
Eon Next | Where a test has failed, but during triage a workaround for the associated defect has been identified, which in turn reduces the severity of that defect, the associated failed test can be re-executed using the recommended workaround, if this enables the test to be concluded successfully then the test can be set to “passed with workaround(s)”. | We are testing 'pass with workarounds' therefore at this stage, we would not expect workarounds in the pre-production code base to be present and should not be encouraged as a fix should now be in place? Workarounds should only be considered in an exceptional circumstance at this point in the test process. | Programme to review/respond |  | Ellie & Fi | Accept | Added "Note, these tests may need to be re-run in the second or third regression cycle; a true test that “passed with workarounds” is not desirable at this late stage in the programme lifecycle."
Eon Next | then they will be clearly marked in the test completion report | Please can it be called the Regression test completion report. | Observation |  | Ellie & Fi | Accept | Amended
Eon Next | 7.2.2. Test Data Usage Each SIT Regression Test participant will be allocated a set of suitable test data for each test case in scope for their role. All MPANs records used in testing will be allocated unique reference IDs that will be used in all communications including test result and defect logging in ADO. A sub-set of tests will be used to migrate MPANs, and then these migrated MPANs will be used in follow on tests, to mimic a more production-like data scenario. This detail will need to be part of the Core Regression test pack and schedule. Full details of how test data will be generated and managed during test execution are documented in the SIT Functional Test Data Approach and Plan [REF-21]. | Repeated, section not required | Observation |  | Ellie & Fi | Accept | Amended as the focus is now on the individual tests and data usage per test.
Eon Next | 7.2.4 Test Evidence is required to be captured at every point indicated within SIT Functional Test Cases, with any exceptions documented and agreed. | Can Programme confirm/check, once the core regression pack is known, that the evidence-capture activity was run on those tests originally and fully represent a streamlined set of evidence requirements?Can Programme confirm/check, once the core regression pack is known, that the evidence-capture activity was run on those tests originally and fully represent a streamlined set of evidence requirements? | Programme to review/respond |  | Ellie & Fi | Accept | Added "At the time of writing, the current evidence capture process remains the same as current SIT phases, as set out in their Test Approaches and Plans. However, the programme may relax these requirements in consultation with code bodies and other stakeholders."
Eon Next | 7.2.7 Release & Configuration Management | Programme to raise a risk around Environment downtime as CPs deployments take up time and sprint timing with regression being constrained, based on this approach for all tests to be completed in sprint/cycle 1. Suggest no fixes are deployed in cycle/sprint 1 and then deployed after unless there is a critical defect that then blocks many tests | Programme to review/respond |  | Ellie & Fi | Accept | Agreed to raise a risk. Adeed "A pragmatic approach to release management will be necessary, given the tight timelines associated with the regression test schedule."
Eon Next | 7.2.10 Test Exit Criteria | This is the final code base for M10/11/12 - rigour around the exit needs to be clearly demonstrated and communicated as such. | Programme to review/respond |  | Ellie & Fi | Reject | This is a code management issue and beyond the scope of this document. However, added "Note: This is the final M10/11/12 code base, and rigour will need to be exercised around maintaining its integrity. This will be managed by the Programme and is outside the scope of this document, but participants should be aware."
Eon Next | All priority 1 and 2 tests have passed, | See earlier - all core regression scripts have been scored and are a priority. This is the first mention of a P1/2 order within a prioritised suite | Programme to review/respond |  | Ellie & Fi | Accept | Agreed, this was a holdover from a previous draft. Amended.
Eon Next | any exceptions are documented and agreed; | /"workarounds" to earlier point | Observation |  | Ellie & Fi | Reject | The programme will be rigorous around exceptions but needs this flexibility.
Eon Next | The number of outstanding severity 3-5 defects on each system and the total number of severity 3-5 defects across all systems are documented and agreed; | will there be a priority assigned to these based on the health of the code base for M11/12 - there may be some 3/4 which may be required to be deployed early on in migration? What is the programme / elexon thinking in terms of managing this at M10/beyond? Who's picking these up? Need to be clear against the defect, what impact not fixing it for Go Live will have? | Programme to review/respond |  | Ellie & Fi | Accept | Added "Outstanding S3 to S5 defects may be re-examined as required for M11/12, where this criterion may not have applied in previous test phases."
Eon Next | 8.3 Test Execution Schedule The SIT Regression test timelines are as follows: | Please break this down into the proposed sprints - if sprint 1 is to be full cycle of all core tests - 3 weeks + 3wk + 2wk formation? | Programme to review/respond |  | Ellie & Fi | Accept | Added sprint breakdown
Elexon | 6 | Section 6 Test Architecture & Coverage: References the master settlement timetable changes but does not confirm that no other ISD data changes are planned for this test phase |  |  | ELEXON - Helix Programme | Accepted | Added "No other changes to the ISD are planned."
Elexon | 6 | Section 6 Test Architecture & Coverage: Doesn’t call out that Helix will be performing an environment maintenance uplift to our latest build. (As signposted during the CR55 IA Helix response) |  |  | ELEXON - Helix Programme | Accepted | Added "3) Helix will be performing an environment maintenance uplift to their latest build, per CR055 commitment."
Elexon | 2.1.3 | 2.1.3 Pre-Regression Settlement Tests The Settling Normally test case will be run before the main test phase, in parallel with the Change of Supplier (CoS) Settlement tests being run in the SIT-A environment. This will include testing accuracy reports” : The section doesn't clearly call out the guidelines or the level of evidencing to be followed for testing accuracy reports |  |  | ELEXON - Helix Programme | Rejected | This is part of the Executive Summary and that detail belongs later in the document (eg Section 6 Test Architecture and Coverage).
Elexon | 3.5.1 | “Any SIT Operational or Non-Functional Regression tests evaluated in the core pack and deemed to be in scope for Regression Testing can be tested in the SIT-B environment alongside the conclusion of the Operational Testing phase.” : This introduces a risk that SIT-B is required longer than planned, which would incur additional support resource overhead / cost. |  |  | ELEXON - Helix Programme | Rejected | The Programme feels subsequent coverage of the practicality of these tests will mitigate their selection, but it was felt it was too early to descope them at this stage without industry consultation.
Elexon | 7.1.1.4 | Operational and Non-Functional Regression Test Pack. “Thus, any tests from these phases identified for regression testing should be run at the end of or after the completion of Operational Testing in the SIT-B environment: This introduces a risk that SIT-B is required longer than planned, which would incur additional support resource overhead / cost. |  |  | ELEXON - Helix Programme | Accepted | Added "Practicality of running these tests will be a criterion in the scoring process."
Elexon | 5.2 | Out of scope: PIT testing is mentioned as out of scope, hence it is assumed that MHHS is not expecting any PIT reports from PP's before commencing the SIT regression testing phase, please confirm |  |  | ELEXON - Helix Programme | Accepted | Confirmed, the Programme is not expecting any PIT reports from PPs prior to the start of the regression phase.
IPA | 2.1.4 | Require clarification on the plan for non-MVC Regression. Does it mean non-MVC Participants have to complete their regression in the same timeframe as MVC Participants? | Additional clarity on plan for non-MVC regression testing, outlining the window for non-MVC regression | Additional clarity on plan for non-MVC regression testing | TT | Accept | Added "All Non-MVC SIT Participants must still complete Regression Testing."
IPA | 2.1.5/7.1.5 | Confirmation if regression testing will be conducted in SIT-B? Section 2.1.5 makes reference to testing in SIT-B but section 7.1.5 only calls out SIT-A ready as entry criteria | Confirm environments for regression and make consistent throughout document | To provide clarity on environments | TT | Accept | Added "• SIT-B Environment has been confirmed as ready based on Operational or Non-Functional Tests."
IPA | 7.2.10 | Will the 7 week regression window be scheduled in Sprints? e.g. Sprint 1 = 2 weeks Sprint 2 = 2 weeks Sprint 3 = 3 weeks | Providing additional detail on the schedule of 7 week window | Clarity | TT | Accept | Added detail to section 8.3 Test Execution Schedule
IPA | 7.2.10 | References 'Priority 1 and 2' tests however not clear in this document that describes what these priorities are? | Additional information on priority definitions | Clarity | TT | Accept | Removed reference to Priority 1 and 2 tests.
Imserv | Section 3.5.1 Any SIT Operational or Non-Functional Regression tests evaluated in the core pack and deemed to be inscope for Regression Testing can be tested in the SIT-B environment alongside the conclusion of the Operational Testing phase. | Regression testing has been shown on the plans as being carried out in the SIT-A environment. Using the POAPs, there is no reference to Regression testing being carried out for Ops or NFR and/or using the SIT-B environment. Is the addition to Regression testing including Ops and NFR new? I'm not clear if this is even needed as we will have just finished Ops and NFR in SIT at this point? Or is the introduction to it being done in SIT-B if it were to occur correct? The implication of using the SIT-B environment beyond the end of SIT Operational as currently defined, further increases our costs of maintaining this additional environment, that is unplanned and unexpected currently. Can guidance and clarification be provided around the expectation of this change for using the SIT-B environment extended beyond SIT NFT and Ops? | Clarification and detail is needed over the inclusion of Regression testing for Ops and NFR, and around the use of the SIT-B environment for a longer period than currently understood as being defined. | The need for further extensions to our environments need to be understood so they can be managed from a technical, support and cost perspective. | Richard French | Reject | There is no certainty we will need the SIT-B environment or that Operational or NonFunctional Tests will be a part of the Core Regression Test Pack. However, it was felt the Programme could not descope these from Regression Testing without taking them through the scoring process. Practicality and pragmatism will form part of the criteria around scoring however.
Imserv | Section 2.1.4 Non-MVC cohorts will be able to continue with any unfinished SIT Functional (SITF) and SIT Migration (SITM) tests in the SIT- A environment once the CoS Settlement tests have completed. | Does this mean that no other SIT Functional Testing can take place during Settlement CoS Testing? If yes, that’s not been stated before. If yes, when is Settlement Testing going to be interwoven with Functional Testing, to mimic real life scenarios | Clarity is required to detail any restrictions planned during the Settlement CoS Test window with rationale as to why | Non-MVC SIT progress impact during this time. Restricting tests that introduce no risk to Settlement Testing doesn’t make sense and needs communicating | Lee Cox | Accept | Added "During CoS Settlement testing in the SIT-A environment, no other functional testing may occur as this will impact the accuracy reports needed for the Settling Normally test case. Thus, outstanding SITF and SITM tests will be paused during CoS Settlement testing in the SIT-A environment." to Section 5.1.3 Non-MVC Regression Testing.
Imserv | Section 3.5.1 The SIT Regression test window is planned for a 7-week period, and testing completes within these timescales | 16-Jun to 08-Aug is an 8 week period Programme Plan v6.17 indicates 3 SIT Regression Sprints: Regression Sprint 1 - 16/06 to 27/06 Regression Sprint 2 - 30/06 to 18/07 Regression Sprint 3 - 21/07 to 08/08 | Request these Sprint Dates are recorded in this Test Approach and Plan to reflect the Regression Test Schedule |  | Lee Cox | Accept | Changed all references from seven weeks to eight.
Imserv | Section 5.1 Figure 3 – Sample SIT Regression Test Framework and Evaluation Score Sheet | Figure 3 introduces weighting associated with criteria Section 7.1.1.2 indicates that details of scoring criteria will not be in this document | The statement in 7.1.1.2 should be reiterated alongside Figure 3 |  | Lee Cox | Accept | Moved to 7.1.1.2
Imserv | Section 5.1 Bulleted list of Market Participants | Electricity Suppliers do not have their (SUP) acronym in brackets | Minor typo |  | Lee Cox | Accept | Amended
Imserv | Section 5.1.3 The Programme will continue to offer support to non-MVC candidate cohorts for regression testing, but participants should not expect the same level of focus and flexibility throughout the rest of the SIT test phases. Test environments will remain available, should they not affect MVC regression testing. | What does 'Test environments will remain available, should they not affect MVC regression testing' mean? During the Programme Regression Test Window, non-MVC participants can continue SIT F testing as long as it doesn’t impact MVC Cohorts executing Regression Testing? | Clarity required |  | Lee Cox | Accept | Added "During the Regression Test window, non-MVC participants can continue SITF an SITM testing as long as it does not impact MVC Regression Testing."
Imserv | Section 6 3) All previous Meter Point Administration Number (MPAN) test data will be removed from Helix and DIP environments before SIT regression commences, the SI team will endeavour to replicate the start of M11 as close to live as is practically possible. Other Central Services and PPs systems will not need to be cleared down of previous test data MPANs, but those MPANs will not be utilised for regression testing. Those parties can opt to remove previous MPAN data from their systems, but it is not mandated, as some services have significant technical constraints in undertaking this activity. | What happens to Participants/Cohorts that are incomplete with SIT Functional Testing and are reliant on the MPANs planned for removal to complete their SIT tests? Are Non-MVC Participants expected to start again i.e. Migrate them and then get them into the right state to support and required SIT F Test? | Clarity required on this approach |  | Lee Cox | Accept | Added "3)a. Non-MVC participants will need to restart any tests in flight, as no MPANs will be retained." Anticipated that legacy and MHHS MPANs will be provided but to be confirmed.
Imserv | Section 6 In parallel with CoS Settlement Testing in SIT-A, the Programme will undertake the Settling Normally test case. It will not be feasible to do this later in the regression test schedule when the other SIT-F and SIT-M tests are being run. | Why can't Functional Testing that doesn’t impact Settlement Runs be executed in parallel? When is Helix going to be tested against Settlement Testing in parallel with other functional processes? |  |  | Lee Cox | Reject | Functional testing running in parallel with CoS Settlement testing in SIT-A would adversely impact accuracy reports. Helix is being exercised as all data flows still run through Helix systems for the limited 400 MPANs that exist in the environment at that time. These are purely settlement focused MPANs, however.
Imserv | Section 7.1.1.2 • Areas which were problematic, especially those where P1 and P2 defects were raised. | Do you mean Sev1 and Sev2 Defects? |  |  | Lee Cox | Accept | Amended to Sev1 and Sev2
Imserv | Section 7.1.2.4 The ESS SIT-A environment be populated with the 8,000 MPANs via the CSV provided. | Typo - ESS, should be EES | Minor typo |  | Lee Cox | Accept | Amended
Imserv | Section 7.1.5 SIT Regression test entry will be dependent on the following SIT Cycle 3 exit criteria having been met: | This section is quoting overall SIT Functional Test Stage Exit Criteria. Is this document introducing a new concept i.e. Cycle 3 Exit Criteria? | Clarity requested on what is meant by SIT Cycle 3 Exit Criteria and where else this is documented |  | Lee Cox | Accept | Amended to "the following SIT exit criteria"
Imserv | Section 7.1.5 • Participant SIT Cycle 3 Test Completion Reports published and approved. | Is this document introducing a new deliverable? Nowhere else is a Participant Test Completion Report for SIT Cycle 3 documented Participant obligation, as per Milestone T3-TE-0046 - SIT Functional Testing End (Minimum Viable Cohort) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) This reference from v6.17 of Programme Plan The Programme Plan is silent on a Cycle 3 Test Completion Report The SIT Approach and Plan is silent on a Cycle 3 Test Completion Report The QAD is silent on a Cycle 3 Test Completion Report FTIG/SITWG papers are silent on a Cycle 3 Test Completion Report | Clarity on new Participant obligation with justification as to why its needed? Included with answer request clarity on what else is required from Participants e.g. A separate Regression Test Completion Report? An addendum to Cycle 3 Test Completion Report to reflect Regression Test completion? Confirmation of when this new deliverable will be baked into QAD, Programme Plans? Confirmation of the change process to be navigated to add this deliverable? |  | Lee Cox | Accept | Amended to "• Evidence of a successful SIT Cycle 3 Completion has been submitted (including a SIT Completion Report), "
Imserv | a | adefect, change to a defect | Minor typo |  | Lee Cox | Accept | Amended
Imserv | General Comment | Document indicates entry criteria for Regression testing requires achievement of exit criteria from Cycle 3 Document indicates potential for Paired Cohort Testing to form part of Regression Testing Document acknowledges that non-MVC Cohorts may well still be progressing SIT Functional Test Scope at point of Regression Test Window Should Regression Testing include Paired Cohort Tests, in order to execute that regression test, do both Cohorts need to have achieved Cycle 3 Exit Criteria? |  |  | Lee Cox | Accept | Amended: "• SIT PP pairing confirmed. This will be the same pairings as at the end of the SITF test phase. This is for the purpose of any paired-cohort tests in the Core Regression Test Pack. For MVC, both cohorts will need to fultill the entry criteria for Regression Testing."
Imserv | General Comment | Its unclear what restrictions will be placed on Cohorts that are still progressing SIT Functional Testing during the Settlement CoS & Regression Test Window | Clarity requested on how non-MVC Cohorts can progress SIT Functional testing between 19-May and 08-Aug 2025 |  | Lee Cox | Accept | Amended 5.1.3 to "At the end of Cycle 3, all MPANs will be cleared from the SIT-A test environment to support CoS Settlement testing. During CoS Settlement testing, no other functional testing may occur as this will impact the accuracy reports needed for the Settling Normally test case. Thus, outstanding SITF and SITM tests will be paused during CoS Settlement testing in the SIT-A environment. All tests outstanding must be restarted after Settlement testing is complete."
Utilita | 2.1.3 Pre-Regression Settlement Tests | Its not clear which Test Env the Settling Normal test is being run in. | Please confirm if that’s to be run in SIT-A or SIT-B Section 6 confirms its taking place in SIT-A | Clarification of Testing Environments | Kev Roper | Accept | Amended.
Utilita | 2.1.4 Non-MVC Regression Testing | Will the Non MVC PPs be expected to complete the full suite of Regression Tests as the MVC if they begin Regression Testing later? | Please confirm if the Non MVC scope will be reduced to accommodate a potential late start | Clarification of Testing Scope | Kev Roper | Accept | Added "All Non-MVC SIT Participants must still complete Regression Testing."
Utilita | 2.1.4 Non-MVC Regression Testing | Its not clear if Regression Testing is compulsory if you are a Non MVC or if it is Mandatory | Please confirm if Non MVC must complete Regression testing or not | Clarification of Testing Scope | Kev Roper | Accept | Added "All Non-MVC SIT Participants must still complete Regression Testing."
Utilita | 3.5.1 Assumptions | Its not clear if the Assumptions listed only apply to MVC PPs? If they apply to Non MVC PPs as well how does their potential late completion of SIT Functional work with the proposed Regression timelines? | Please confirm if the Assumptions apply solely to MVC PPs or clarify how those Assumptions will be handled if they apply to Non MVC PPs | Clarification of Testing Timelines | Kev Roper | Accept | Added "o Non-MVC participant cohorts can extend Regression Testing into the Non-MVC support window." Sub-bullet.
Utilita | 5.1.2 SIT Operational and Non-Functional Testing | It is not clear if this means that there is no need to execute these tests as part of regression If they need to be executed as part pf regression will it be the same party that executed in in the previous phase? | Please clarify if these need to be tested as part of regression | Clarification of Testing Scope | Pete McGilley | Accept | Added "if they are included in the Core Regression Test Pack"
Utilita | 5.2 Out of Scope | The bullet " All the other SIT Stages – these will be the subject of separate Test Approach and Plan documents:" references Non-Functional and Operational Testing, are we to assume this is clarification that they are out of scope for Regression? | Please clarify if these need to be tested as part of regression | Clarification of Testing Scope | Pete McGilley | Accept | Removed references to other test phases except for CIT.
Utilita | 6 Test Architecture & Coverage | Point 3 states "All previous Meter Point Administration Number (MPAN) test data will be removed from Helix and DIP environments before SIT regression commences" How is that possible if SIT Functional Testing for Non MVC PP is running in paralel? | Confirm how this action would impact ongoing tests still in progress by Non MVC parties | Clarification of Testing Data | Kev Roper | Accept | Added "3)a. Non-MVC participants will need to restart any tests in flight, as no MPANs will be retained."
Utilita | 7.1.1.3 Core Regression Test Pack | Same question as above For those Non MVC PPs will they be expected to complete all the same Regression Tests as the MVC if they begin Regression Testing later? | Please confirm if the Non MVC scope be reduced to accommodate a potential late start? | Clarification of Testing Scope | Kev Roper | Accept | As above
Utilita | 7.1.2.2 Test Data Creation within DIP | States "The DIP SIT-A environment will be cleared down of historical MPAN data." | Confirm how this action would impact ongoing tests still in progress by Non MVC parties | Clarification of Testing Data | Kev Roper | Reject | See section 6 "3)a. Non-MVC participants will need to restart any tests in flight, as no MPANs will be retained."
Utilita | 7.1.2.3 Test Data Creation within Elexon Settlement | States "The Helix SIT-A environments will be cleared down of historical MPAN data." | Confirm how this action would impact ongoing tests still in progress by Non MVC parties | Clarification of Testing Data | Kev Roper | Reject | See section 6 "3)a. Non-MVC participants will need to restart any tests in flight, as no MPANs will be retained."
Utilita | 7.1.4 Participant Preparation | Are these steps really needed as all PPs involved will have already been actively using SIT-A during SIT Functional Cycles 1 to 3? | Confirm if these steps are redundant | Clarification of Testing Pre-Requisites | Kev Roper | Reject | It's felt this is valuable activity after the environment maintenance period.
Utilita | 7.1.5 Test Entry Criteria | A bullet in these section states " NB Operational testing will not be scheduled to be complete by the time Regression testing is due to start." However there is a requirement to test operational, how do we do that when operational testing is not complete? | Confirm if Operational testing should be complete before we enter regression | Clarification on Entry criteria | Pete McGilley | Reject | Section 2.1.5 states "However, it is expected that any tests added to the Core Regression Test Pack from these test phases will be conducted in the SIT-B environment alongside or after the end of the Operational Test phase."
Wheatley Solutions | 7.1.1.6 | Document mentions 'Cohort Regression test pack' with approval process. However this is the first specific mention of the Cohort Regression test pack as distinct from the Core SIT Regression test pack. | Clear definition of the distinction between the Core SIT pack and the Cohort test pack should be provided. | As this is the first reference to the Cohort specific test pack, it is unclear as to how this differs to the Core pack. | Stuart Atkins | Accept | Removed reference to Cohort Regression test pack.
SMS | 2.1.2 | It is not clear how the 8 weeks will be divided into to 3 sprints. | Provide further clarity on the dates or length of the sprints | Improves visability and planning capabilities and resources | Robert Langdon | Accept | Expanded table in Section 8.3
SMS | 2.1.2 | The document states is that the second sprint will test fixes identifed in the first sprint | More detail is required on how this will be co-ordinated - i.e. when will fixes be applied to ensure new defects are not introduced part way through sprint. And detail on what happens if it's not ready for start of sprint. | Risk that defects can not be addressed before start of second sprint. E.g. if a defect is found on the last day of the first sprint it is not reasonable to expect a fix by the start of the second sprint. This also allows us to align resource more effectively | Robert Langdon | Accept | 2.1.2 is an Executive Summary section. Added "Contingency time should be used to accommodate defect fixes, and sprint start dates can be adjusted as necessary depending on deployment timelines." to section 8.3.
SMS | 5.1.1 | Whilst the score sheet enables risk to be established, there is no detail of what score presents a level of risk to be selected for regression testing | Further clarity of the selection criteria should be provided | This is essential to be socialised and rationalised by the programme and participants to ensure we are clear to what extent regression testing mitigates risk. This should not be based on a post evaluation review to select a risk level (scoring) which selects a volume of tests which aligns with capacity/timespan allocated to regression testing | Robert Langdon | Reject | This scoring and criteria system will be worked through fully at SITWG.
Callisto | 5 | The scope does not include legacy, as we believe it needs to | Include NHH/HH agent roles in the test scenario design for relevant processes | In order to deliver true end to end testing of the processes, the starting point should be as per the existing production position of MPANs with legacy agents appointed. Our legacy capability has been present in SIT throughout, at the request of the Programme, and we believed it was required to allow the programme to meet its own exit criteria. So far SIT has not utilised this capability at all, despite repeated requests to include it. We believe running true E2E regression from the start point with agents acting has to be better than using stubs | Simon Harrison | Accept | The Programme is happy to support NHH/HH agent roles in Callisto's cohort but no other cohorts are able to support this testing. Please work with the LDP to ensure this testing is scheduled and prepared for accordingly.
Callisto | 7.2.10 (&3.5.1) | Standard best practice for test regression is a minimum of two stable runs. What happens if defects are found in run 2, or run 3? | The exit criteria should require a minimum of 2 'clean' regressions, and the whole phase should plan for contingency sprints needed to meet that requirement | Exiting with a single clean regression run significantly increases the risk of issues occurring in production, especially given the amount of design releases, defect fixes and number of participating parties in cycle 3 | Simon Harrison | Reject | The Programme has been under challenge to justify the third run of testing from other participants. Given testing is ultimately a risk mitigation exercise, this seems the right balance between timescales and risk.
EDF | 5.1.1 | Included in the factors considered are 'Negative test cases, and Business process edge cases'. Should we really be including edge cases within a core regression pack?? | Review the need to include edge cases as unsure of the benefits | edge cases will only increase the test window | Julie Middleton | Accept | Removed
EDF | 7.1.1.4 | 7.1.1.3 relates to the Core Regression Pack, however, 7.1.1.4 relates to the Operational and NonFunctional regression pack. Are there multiple Regression packs or just the 1 core regression pack? | Needs to be clear | Confusion as to which regression pack to run | Julie Middleton | Accept | Removed "Test Pack" from subheading, to refer only to Operational and Non-Functional Regression Tests.
EDF | 7.1.1.6 | First mention of the Cohort Regression Test Pack. Are there 2 different regression test packs, Core and Cohort? Is there an existing cohort regression pack? | Needs to be clear what the Cohort Regression pack is | Confusion as to which regression pack to run | Julie Middleton | Accept | Removed
EDF | 7.1.5 | duplicated bullet point. Remove All Non-Functional tests have been executed as previous bullet point states 'Non-Functional Testing has completed its exit criteria'. | Remove 'All Non-Functional tests have been executed'. As not required | remove duplication | Julie Middleton | Accept | Removed
EDF | 7.2.4 | Confusion around statement 'capturing evidence for 2 out of 8 Test Runs'. Unsure how this works with the Core Regression pack. Are there 8 test runs and only 2 are related to test evidence? Is this section a cut & paste from the SIT Functional approach and plan?? | Needs to be clear | Confusion around when evidence is captured | Julie Middleton | Accept | It was. Removed reference to make clearer.
EDF | 8.1 | Within section 7.2.9 it confirms that the test completion report should be submitted within 5 days after test completion. If test completion is 8/8/25, then should the SIT functional end and SIT Migration end be 15/08/25. The plan also doesn’t show the regression window for NF | SIT end dates should reflect the additional 5 days to submit the completion report or the approach should reflect that the completion report be submitted by 08/08 | It needs to be clear of the final end date, and whether the participants need to submit the completion report by 8/8 or by 15/8. | Julie Middleton | Accept | Programme to add overarching Programme Completion Report as well as Participant Completion Reports to the Programme Plan.
St Clements | 2.1.4 | Are you expecting non-MVC parties to run both functional/migration SIT and regression at the same time? | Clarification required | Not advisable to run functional tests and regression tests concurrently | Richard Warham | Accepted | Added "All Non-MVC SIT Participants must still complete Regression Testing, but need to complete prior SIT phases before they begin."
St Clements | 2.1.4 | Running functional/migration SIT you run the risk of requiring defect fixes whilst simulataneously running regression. Does this introduce a risk that regression may not be run on the 'final' code? | Clarification required | Clarification required | Richard Warham | Reject | The purpose of running regression testing is to find regression issues. The programme does not feel this approach introduces additional risk.
St Clements | 7.1.2.1, 1) | Number of required MPANs to be confirmed. Assume these are MPANS at created state in August 2023 datacut and do not need to be created. (the same as 4 i) | Clarification required | Clarification required | Richard Warham | Accepted | Added "This number to be confirmed through the data preparation process."
St Clements | 6 | Why add a smoke test stage for an existing environment especially when it takes place whilst the environment is being used for CoS settlement tests? The first paragraph of this section acknowledges SIT-A as being an established system | Remove the requirement to smoke test an existing environment | Unnecessary step as SIT-A environment is already being used within the programme | Richard Warham | Reject | There will be significant maintenance work going on before the start of CoS Settlement SIT-A testing, and participants may clear down their own environments. It seems prudent to conduct quick smoke tests to ensure everything is back to full operation.
St Clements | 7.1.4 | Does the IF-047 need to be loaded? If so, will the ISD being used for preparation be valid for CoS Settlement tests already taking place in SIT-A? | Clarification required | Clarification required | Richard Warham | Accepted | Added "The ISD will be published at the beginning of the test phase."
St Clements | 7.2.4 | How can regression be executed for all 8 cohorts if functional/migration SIT has potentially not been completed by all 8 cohorts? Will regression be running concurrently with functional/migration SIT? | Should individual cohorts complete functional/migration SIT before running regression? What is the impact if this is allowed? | I would have thought it was appropriate to run regression after all functional testing has completed | Richard Warham | Reject | It's anticipated that MVC Cohorts will run regression after completion of functional and migration, but before Non-MVC cohorts are finished. It would not make sense from a programme point of view to make those cohorts wait until the slowest cohort completed when they aren't in the MVC.
St Clements | 3.5.1 | 5th bullet. Participants can conduct further regression testing but this should be in their own environments and not SIT-A, otherwise there may be additional demands on central party support whilst supporting core regression | Clarify in what environments participants can conduct further regression testing | Restrict tests by cohorts outside of the prescribed list within SIT-A to enable central parties to focus on the mandatory tests | Richard Warham | Accepted | Added "It should be noted the Programme will endeavour to support cohorts in these efforts but programme milestones and timelines may take precedence, so this should be a factor in any decision to run additional tests." to 7.1.1.6
St Clements | 5.2 | 2nd bullet. Have all test script defects identified in SIT been fixed? | Clarification required | Clarification required | Richard Warham | Reject | All test script defects associated with Core Regression Test Pack tests are expected to be fixed.
St Clements | 7.1.1.6 | Are parties being encouraged to run additional regression tests in SIT-A or within their own environments? Running in SIT-A will have an impact on central parties | Clarify in what environments participants can conduct further regression testing | Restrict tests by cohorts outside of the prescribed list within SIT-A to enable central parties to focus on the mandatory tests | Richard Warham | Accepted | Added "It should be noted the Programme will endeavour to support cohorts in these efforts but programme milestones and timelines may take precedence, so this should be a factor in any decision to run additional tests." to 7.1.1.6
Participant #1 | 2.1.1 | "Regression tests will be chosen by a scoring system" Where do we find details of the scoring system to be used. This needs to be defined and referenced by this document to allow appropriate review of this document. | Programme to publish the scoring system. | Without this document, this TAP cannot be fully reviewed | Participant #1 | Reject | The details are laid out in Section 7, test preparation. It will be done in conjunction with SIT Working Group.
Participant #1 | 2.1.2 | The TAP needs to provide cross reference to the Main programme planned tasks and any related milestones to remove any risk of misunderstanding | Provide cross reference to the programme plan and related milestones | Clarification and definition of the Sprints and removal of any potential misunderstandings | Participant #1 | Reject | Regression tasks are clearly outlined in the Programme Plan.
Participant #1 | 2.1.2 | The TAP assumes progress to plan or ahead of plan ( also called out in 3.5.1 Assumptions). What is the Approach to slower than anticipated Regression. | The option needs exploring with detail included as to the approach for slower than assumed Regression. | This is a significant lesson learned from SIT testing and the significant extension of time over the original test model | Participant #1 | Reject | The scope of the Core Regression Test Pack is determined by actual test velocity, not assumptions.
Participant #1 | 2.1.2 | What is the approach being taken to derive the velocity to be used in Regression | More detail needs to be provided to allow participants to understand how the programme will model this velocity. Concern based on previous modelling accuracy | Participants need to understand the approach and plan for this to be able to fully review this TAP | Participant #1 | Reject | This is the Executive Summary, detail is in Section 7 Test Preparation.
Participant #1 | 2.1.4 | Can Non-MVC run settlements testing in parallel with MVC regression testing | Please Clarify | Participants attempting to run tests when they shouldn't | Participant #1 | Reject | Non-MVC will need to run the same Settlement Tests as everyone else.
Participant #1 | 2.1.5 | Where can reviewers find the detail of the scoring mechanism to be applied | Please clarify | Support participants pre regression planning | Participant #1 | Reject | Section 7 shows some detail, the rest will be in SITWG.
Participant #1 | 2.2 | Why is this not referring to the master Programme plan? This should be the central reference for all planning activities | Please add detail (UID please) of the tasks as detailed in the programme master plan | Risk of main plan and PoaP misalignment | Participant #1 | Reject | This was produced by PMO based on the master Programme plan.
Participant #1 | 3.5.1 | Where Participants choose to undertake additional testing, what assumption is the programme making to protect sufficient MPAN for parties yet to complete regression and any parallel testing | More detail required to assure participants sufficient MPAN will exist to allow participants to undertake additional testing or if this will limit additional retesting | Potential to run out of MPAN for testing | Participant #1 | Reject | This information is in Section 7.1.2 Test Data
Participant #1 | 3.5.1 | Settling normally, without the LDSO and DUoS being available, what is the validity of executing this test if it can only be partially executed | Either engage the participants or programme to provide appropriate stubs to allow testing to be fully executed | Inaccuracy of test leading to issues in Live | Participant #1 | Reject | While the full test case will not be able to be run, the Programme feels accuracy testing will be high value and valid testing despite constraints.
Participant #1 | 3.5.1 | Assumption that participants will be able to achieve similar test velocity. How can this be assumed given this is moving tests to a different environment and key endpoints (LDSO DUoS) will not be present | Document needs to expand on why this is an assumption given the many issues we have seen in SIT that resulted in significantly longer execution cycles | Programme not prepared for or ready to support over run of regression testing | Participant #1 | Reject | These tests will be run in the same environment they originally passed in. The test velocity referred to is not Settlement tests but SITF and SITM. CoS Settlement tests will be run before the primary Regression Test phase begins.
Participant #1 | 3.5.1 | Approach refers to 3 sprints, assumptions state 7 weeks, sprints are typically 2 weeks so this indicates one sprint will be 3 weeks. The programme plan currently shows 3 regression tasks, 1 x 10 days, 2 x 15 days so 8 weeks total | More detail required regarding the sprint timescales as there appears to be misalignment in the document and with the programme plan | incorrect planning assumptions for regression resulting in participants unable to fully support the plan and assumptions | Participant #1 | Accept | Updated test execution schedule is in Section 8.3.
Participant #1 | 3.5.1 | Assumes no changes to Cohort teams makeup. Suggest this may not be a valid assumption as the planned dates for regression could be impacted by the Cohort participants as the may have resource changes June through August, this is peak resource annual leave with school holiday season in flight | Invalid assumption, if this expected participants to also remain unchanged - needs to be reviewed and adjusted accordingly | Team makeups change likely slowing ability to progress regression as assumed by the programme | Participant #1 | Accept | Amended to "Any changes to the participant cohort team makeups are manageable and will not impact test velocity"
Participant #1 | 5.1.3 | Document states that other participants should not expect the same level of focus and flexibility through the rest of SIT test phases | What happens to a Non-MVC participant if they are delayed or unable to exit Regression due to the MVC cohorts being given priority treatment | Potential discrimination of other participants delaying their ability to meet programme timescales | Participant #1 | Accept | Added "The Programme will work with Non-MVC candidate cohorts to minimise disruption to their testing."
Participant #1 | 7.1.1 | Encouraging Cohorts to undertake supplemental testing | What if this supplemental testing is not true regression testing and identifies defects that have not been previously identified, how will these be managed and subsequently taken through a regression test? | Extended regression testing period how does the programme plan to manage this "extended testing" without impacting ongoing regression testing and would an MVC cohort undertaking "extended testing" take priority over a non-MVC undertaking Regression testing | Participant #1 | Accept | Added "This activity is voluntary at the cohort’s discretion, and may be impacted by other programme priorities." If an MVC candidate's supplemental regression activities are adversely impacting a number of other cohorts, the Programme can bring it to a close.
Participant #1 | 7.1.1.2 | Doc [REF 19] SIT regression Test Framework | When will this be made available to test participants. | Lack of visibility could impact participant planning and readiness | Participant #1 | Reject | This is outlined in Section 8.2.1 SIT Regression Preparation Schedule
Participant #1 | 7.1.16 | Is this an open concurrent review with all participants reviewing at same time or is this a sequential review e.g. 1 through 7 / 5 | More detail on how the review process will work | lack of control and limited document validation | Participant #1 | Reject | Unsure of which section to which PP is referring, but full preparation schedule should be outlined in Section 8.2.1 SIT Regression Preparation Schedule.
Participant #1 | 7.2.1 | test pass or fail During SIT, a test set to fail would necessitate a complete restart and could not be started from the point of failure | Is it viable to use the other states available in SIT - Blocked and Paused to ease progress and prevent restarts | Potentially the use of "fail" status requires restart tests that could have been re-commenced from the point the defect was raised where another test status was used. | Participant #1 | Accept | Agreed, removed references to moving a test from fail to pass and not applicable.
Participant #1 | Figure 6, Sections 8.2.1, 8.2.2 and 8.3 | If this plan changes will a new version of the document be published? | Would it be better to link to the formal external PoaP document so that the documents are not tied to specific versions and dates? Also noting this states current, any person picking the document up at a future date would need to check latest planning details and these are not available from this document | Regression is not planned accordingly due to out of date information | Participant #1 | Accept | Added "Should these plans change the latest Programme Plan will always be found here."
British Gas | 2.1.1 Regression Test Scoring and Core Pack | Regression Test Scoring and Core Pack will be decided by the programme at SITAG Query - When will that happen and will there be the opportunity to challenge? | Need to add additonal reivew layer performed by the industry to provide neccesary comments in terms of test scoring and the core pack selection made. | Industry participant will also be having the view on business criticallity which does not only impact central parties but also every market participant roles and hence should given an opportunity to review and comment on the scoring performed and core pack selected | Lynda Kristiansen | Rejected | This information is in Section 8.2.1 SIT Regression Preparation Schedule.
British Gas | 2.1.2 Three-Sprint Approach | The number of tests will be derived from the velocity of the Minimum Viable Cohort (MVC) participants in a specified sprint (to be determined). The intention is that this will provide a balance of achievable tests run and coverage. Comment - Shouldnt a risk based approach be considered based on data rather than a quantative one. Timeline rather than quality | The methodology of no: of tests selection should be changed from MVC test pace to coverage and quality assurance and if required extend the regression timelines rather than trying to confining the regression to the planned timelines. | The objective of regression testing is to ensure there are no major issues that will be leaked into production due to the enormous amount of changes that the systems have undergone over a period of more than a year. Hence reducing the regression scope to fit it within the MVC test velocity or the tests we could just achieve within 2 weeks sprint is not acceptable | Lynda Kristiansen | Rejected | All testing is risk-based and constrained by project timelines. The Programme feels this approach balances risk with delivery and will catch high value regression defects, with the opportunity to fix them within programme planned dates. With longer sprints or no sprints, the opportunity to fix any defects found is lost. However, the Programme is open to counterproposals.
British Gas | 2.1.4 Non-MVC Regression Testing | Then, they can run regression testing in parallel with the MVC cohorts. Query - Is that the 85% or 100% target and can MHHS confirm there will be no delay in Non MvC joining as MvC are prioritised? | MVC and Non-MVC to be given equal priority and support if the cohorts in both categories are joinng regression testing at the same time. | By giving equal priority to MVC and Non-MVC cohorts performing regression testing during the same timeline will ensure that we are not punishing the Non-MVC cohorts for performing well and keeping pace with the MVC group. | Lynda Kristiansen | Accepted | Added "All Non-MVC SIT Participants must still complete Regression Testing, but need to complete prior SIT phases before they begin." Exit criteria for SITF and SITM remain unchanged.
British Gas | 2.2 Overall Test Schedule | Comment - The relative position and timescales of the regression testing at 7 weeks appears dispropionate and small relative to the overall testing plan which is over a year (March 24 to April 25) | Need to extend timelines for regression testing to give a fair and proportionate timeline to perform a thorough assurance on the quality of the changes being delivered |  | Lynda Kristiansen | Rejected | Programme milestone challenges are outside the scope of this document. There should be avenues to challenge the programme plan dates via other means.
British Gas | 3.5.1 Assumptions | The SIT Regression test window is planned for a 7-week period, and testing completes within these timescales Query - What are the criteria for the 3 phases. Given the programme and SIT testing has run by this time for 15 months 7 weeks for regression testing seems very ambitious. Will testing be timeboxed and a 'time out' approach be taken | Query | Query | Lynda Kristiansen | Accepted | The approach should be detailed in Section 5 Scope, Section 6 Test Architecture and Coverage, Section 7 Test Approach, and Section 8 Test Schedule.
British Gas | 3.5.1 Assumptions | Non-MVC participant cohorts can continue to test in parallel without affecting MVC regression testing in the SIT-A environment. Comment - Can the MHHS programme be certain there will be no impacts or delays as a result of parallel testing? Moreover, currently we have both MVC and Non-MVC performing tests together till date in SIT-B without impacting each other, so what impacts or delays the programme forsee? | Query | Query | Lynda Kristiansen | Accepted | The Programme is confident there will be no impact but wanted to be cautious with calling this assumption out.
British Gas | 5.1.3 Non-MVC Regression Testin | The Programme will continue to offer support to non-MVC candidate cohorts for regression testing, but participants should not expect the same level of focus and flexibility throughout the rest of the SIT test phases. Comment - This is not explained in enough detail and can be interpreted in many ways. Please provide what wont happen wrt to support that happens now | The details on the level of support Non-MVC group can expect if they join regression along with MVC group. MVC and Non-MVC should be given equal priority and support if the cohorts in both categories are joinng regression testing at the same time. | By giving equal priority to MVC and Non-MVC cohorts performing regression testing during the same timeline will ensure that we are not punishing the Non-MVC cohorts for performing well and keeping pace with the MVC group. | Lynda Kristiansen / Lee Wilson | Accepted | Amended to "The Programme will continue to offer support to non-MVC candidate cohorts for regression testing, but participants should not expect the same level of focus and flexibility throughout the rest of the SIT test phases. Test environments will remain available, should they not affect MVC regression testing. During the Regression Test window, non-MVC participants can continue SITF an SITM testing as long as it does not impact MVC Regression Testing.. At the end of Cycle 3, all MPANs will be cleared from the SIT-A test environment to support CoS Settlement testing. During CoS Settlement testing, no other functional testing may occur as this will impact the accuracy reports needed for the Settling Normally test case. Thus, outstanding SITF and SITM tests will be paused during CoS Settlement testing in the SIT-A environment. All tests outstanding must be restarted after Settlement testing is complete. As well, defect fixes for MVC regression issues will be prioritised over non-MVC defect fixes, as the objective of the Programme at that point will be to minimise risk to the completion of MVC Regression Testing. The Programme will work with Non-MVC candidate cohorts to minimise disruption to their testing."
British Gas | 5.1.3 Non-MVC Regression Testin | Query - Can we get anymore clarity on what reduced support actually means? Does it mean its going to take an unreasonable amount of time to get our regression tests ran? That doesn’t really seem that fair especially if we have to commit resources to this | Query | Query | Lee Wilson | Accepted | We don't anticipate a large disparity between MVC and Non-MVC candidate cohorts, but the Programme's responsibility is to deliver the MVC. It simply means that at this late stage before M10, if there is any conflict then MVC will get the priority call. We anticipate that most non-MVC concerns should be addressed in a timely manner and will work to minimise impact on non-MVC cohorts. It is in the programme's interest to have more cohorts complete SIT, not less.
British Gas | 5.1.3 Non-MVC Regression Testin | MVC regression defects prioritized over Non-MVC regression defects. Comments - How can Non-MVC regression defect less important when compared to MVC defects? What if Non-MVC has identified a significant defect which the MVC group failed to identify? | Defect prioritization including fix should be based on the gravity of the issue being raised rather than priotizing based on MVC - Non MVC groups. | de-prioritizing Non-MVC defects may introduce signifant issues in production if un | Lee Wilson | Rejected | The programme's responsibility is to deliver the MVC out of SIT testing by CR055 timelines. As above, this does not minimise the importance of defects found during non-MVC testing; it simply means an additional emphasis added to the defect prioritisation.
British Gas | 7.1.1.2 SIT Regression Test Scoring | The SI test team will create a framework to review all SITF, Settlement, SITM, Operational and Non-Functional tests and SIT defects, and select a sub-set of these tests to run during SIT Regression. Each test and defect will be reviewed against several criteria, all of which will carry a weighting. We will ask the Code Bodies and Central Parties to feed into the selection criteria, by confirming the key business processes / tests which they believe should be executed during SIT Regression testing Comment - How transparent will this process be wrt scope/risk. Will we say a baselined version so we can track what gets removed should the testing get behind in 7 weeks. Also the comment for 2.1.1 above applies here as well | Programme to publish detailed list of finalized scenarios/ test cases prior to the test phase commencement enabling the industry partcipants to track the scoping until closure Need to add additonal reivew layer performed by the industry to provide neccesary comments in terms of test scoring and the core pack selection made. | Industry participant will also be having the view on business criticallity which does not only impact central parties but also every market participant roles and hence should given an opportunity to review and comment on the scoring performed and core pack selected | Lynda Kristiansen | Rejected | The test scoring process will undergo full review by the SITWG over two sessions: 1) to review the criteria and weighting, and 2) to review the full list of scored tests. In between, there will be an industry review of tests and their scores, as outlined in Section 8.2.1 SIT Regression Preparation Schedule.
British Gas | 7.1.5 Test Entry Criteria | SIT Regression test entry will be dependent on the following SIT Cycle 3 exit criteria having been met: • All SIT Functional & Migration tests (including Settlement where possible) have executed, and the overall test pass rate is 85% or above or any exceptions are documented and agreed. Query - Can MHHS Testing confirm for SIT participants not in the first phase of regression testing and still working on other SIT phases wont be delayed, and assurance delayed as a result of MVC regression and timeline objectives? | Query | Query | Lynda Kristiansen | Accepted | The Programme cannot confirm this as the objective of the programme - and the promise to Ofgem - is to deliver the MVC testing to CR055 timelines. However, the programme also recognises the value generated by Non-MVC testing and will seek to minimise disruption and impact. Added "The Programme will work with Non-MVC candidate cohorts to minimise disruption to their testing." to section 5.1.3.
British Gas | 12 Appendix | Query - Is Regression testing MvC and Non MvC expected to be identical? The document doesn't detail any commonality or indeed distinction for Non MvC. |  |  | Lynda Kristiansen | Accepted | Added "Non-MVC cohort candidates will be required to run the same Core Regression Test Pack as the MVC cohort candidates. It is anticipated that such runs will be smoother when executed prior to other cohorts." to Section 5.1.3 Non-MVC Regression Testing.
British Gas | 12 Appendix | Contingency and timeframe No contingency within the regression testing phases. 7 weeks doing 3 phases and feeding back changes seems extremely challenging if quality is to be maintained | Need to add contingency in plan in case regression test activities don't go according to the plan rather than reduction in scope towards the end |  | Lynda Kristiansen | Accepted | Expanded section 8.3 to show the contingency added to the end of the Regression Schedule.
RECCo | 3.5.1 | Bullet 8 states that LDSOs are not connected in SIT-A. Please could you confirm this is actually the position and if so, please explain the rationale. We believe LDSO functionality has been tested in SIT A and would expect them to be part of regression testing. Note that this statement is also repeated in section 6, penultimate paragraph | Explain what is meant in bullet 8 |  | RECCo | Accepted | Added a sub-bullet "o For further detail, LDSOs are not set up to receive the IF-021 consumption data on SIT-A or receive the settlement output reports for ingestion into their associated DUoS Billing Systems as this was not part of the original test scope."
RECCo | 3.5.1 | There is an assumption that any SIT Operational tests required for regression will be run alongside the end of SIT-Operational testing. Is there a risk that this will not be useful as the tests will be run in the same version of the environment that they had previously been for SIT-Operational? If these tests are deemed necessary for regression is an alternate approach required? | Review the value of running Operational regression tests in a parallel with SIT-Operational. |  | RECCo | Accepted | Added "Practicality of running these tests will be a criterion in the scoring process." The Programme did not want to descope Operational and Non-Functional testing unilaterally without consultation with industry, but it must be recognised that there are additional constraints for running Regression Testing in SIT-B.
RECCo | 6.1 | The first paragraph states that SIT Regression will take place in SIT-A. However earlier in the document it is stated that any Non-Functional or Operational tests included in the regression pack will tested in SIT-B | Clarify which environments will be used |  | RECCo | Accepted | Amended the first sentence to: "SIT Regression testing will be undertaken primarily within the MHHS SIT-A environment, with potential Operational and Non-Functional tests executed in the SIT-B environment"
RECCo | 7.1 | There is a statement that regression testing will re-use test cases from previous SIT cycles. Is it also possible that additional tests will be required, for example to test any CRs implemented since the test scripts were created? | Consider how new test cases required to prove CR implementation can be added. |  | RECCo | Accepted | Added "No new tests will be a part of the Core Regression test pack."
RECCo | 7.1.1 | It would be useful for Code Bodies and other industrty participants to review the scoring framework and how test cases have been scored. Without this it will be difficult to understand how the final list of test cases has been calculated. | Detail industry reviews of the scoring framework and evaluation scoresheet. |  | RECCo | Rejected | Code Bodies are listed in Section 7.1.1.1 SIT Asset Reviews and will be included in the industry review outlined in Section 8.2.1 SIT Regression Preparation Schedule.
RECCo | 7.1.1.2 | There is a statement that the scoring criteria will be brought to SITWG for review. Should this document also be brought to SITAG for review / approval. | Detail governance path for the scoring criteria / framework. |  | RECCo | Rejected | This effort properly belongs with SITWG to delve into the detail of the scoring criteria. The results will be reported and SITAG can feed back concerns. As well, the SIT Regression Pack Approval sits with SITAG as part of T3-TE-0122.
RECCo | General | There are multiple references to the SIT Regression Test Framework and the Evaluation Score Sheet. As this is an approach and plan, we would expect the delivery dates for these products to be included. | Timeline for delivering the SIT Regression Test Framework is required |  | RECCo | Accepted | Added "(including Regression Test Framework)" to the SIT Regression Test Pack drafted in Section 8.2.1 SIT Regression Preparation Schedule.
RECCo | 8.2.1 | The table covers the review and approval of the approach and plan document and then the approval of the Regression Test Pack (REF-20) but gives no time for agreeing the SIT Regression Test Framework (REF-19) and Evaluation Score Sheet ahead of developing the Test Pack | Timeline for delivering the SIT Regression Test Framework s required. Including the SITWG review detailed in section 7.1.1.2 and SITAG approval. |  | RECCo | Rejected | This effort properly belongs with SITWG to delve into the detail of the scoring criteria. The results will be reported and SITAG can feed back concerns. As well, the SIT Regression Pack Approval sits with SITAG as part of T3-TE-0122.
RECCo | 2.1.4 | Refers to SIT Non-MVC running regression in parallel with SIT MVC. Is this the only opportunity for SIT Non-MVC regression? Additional opportunity would be beneficial for these partes in addressing any defects that may otherwise cause a delay to them demonstrating that they have met the required standards and can be Qualified. The document refers to parties being able to conduct further regression, (e.g. 3.5.1) but unclear if this is facilitated through SIT or is PIT. | Clarify additional scope for SIT Non-MVC regression once the SIT MVC regression phase has ended. |  | RECCo | Accepted | Added "Non-MVC candidates can count on programme support during the Non-MVC Support phase outlined in the Programme Plan (here)." to Section 5.1.3 Non-MVC Regression Testing.
RECCo | 8.2 and 9.2.1 | We welcome the opportunity to feed into the selection of the Core Regression Tests. This will help ensure coverage of the tests required for Qualification. It is not clear when Code Bodies will be engaged to support this activity and Code Bodies have not been included in the RACI | Please clarify when Code Bodies will be engaged in the development of the Core Regression Pack and include Code Bodies Role within the RACI. |  | RECCo | Accepted | Code Bodies should get sight of the Regression Test Framework and Core Regression Test Pack through industry review. Added Code Bodies to RACI.
RECCo | 7.1.1.6 | Cohort Regression test pack'. This is not mentioned elsewhere in the document and it is not clear how and when this will be produced | Clarify approach and plan for developing the Cohort Regression test pack |  | RECCo | Accepted | Amended to "The Core SIT Regression test pack will be constructed using the Regression Test Framework, and undergo the following review, consultation, and approval process:"