## REVIEW Drafted Formal Response
Organisation: | Full SoLR Consultation Feedback and Responses
Constituency:
Date: |  | MHHS-DEL3713 Supplier of Last Resort (SoLR) Consultation Comments and Responses Log v2.0
Anonymised:
| Reviewer to Complete |  |  |  | Programme to complete once consultation window has closed.
Comment Reference | Reviewer | Page | Section | Comment | Response | Status
1 | E.ON Next | 5 | 1.5 | We do not anticipate that a delay in data following the DIP indentifer and routing within the DIP to be a significant issue. There is a natural delay in data while the appointed supplier agrees the terms with the administrator. As long as the appointed supplier can complete the DIP onboarding process they can factor this delay into the actions taken to protect the customer | The alignment will be as per the Ofgem instruction - The DIP Manager has provided SoLR Guidance which was issued with the Consultation and is available on the Collaboration base - https://www.mhhsprogramme.co.uk/migration-and-transition/transition/service-activation/elexon-helix-supplier-of-last-resort-solr-consultation.
2 | E.ON Next | 5 | 1.5 | We would recommend that a portolio report is provided to the gaining Supplier for Entity 45 & M16 so that a robust portfolio reconciliation can be completed to ensure that the gaining supplier has all the required sites associated with the company that has entered the SOLR process | Ofgem provides a portfolio report to prospective suppliers, from the information provided from Elexon and Xoserve.
3 | E.ON Next | 7 | 1.5 | We agree that the guidance provided provides enough information for us to be able to complete the DIP process. There are no additional points we would like to raise. | Statement - No action required
4 | E.ON Next | 7 | 1.5 | There is no additional information that we would require to contact the DIP manager | Statement - No action required
5 | E.ON Next | 8 | 1.8.1 | We would already be qualified and would look to move any customers onto our own billing system via the COS process rather than migrate the old suppliers MPID into the new MHHS arrangements. We would recommend a portfolio report to enable the gaining supplier to be able to identify any meter points that would fall under UMS and Smart Exemptions so the gaining supplier could identify these customers at the earliest opportunity. | Ofgem provides a portfolio report to prospective suppliers, from the information provided from Elexon and Xoserve.
6 | E.ON Next | 8 | 1.8.2 | Depending on the size of the SOLR supplier this could impact the gaining suppliers migration capacity envelope. This process will need further development to help suppliers identify how much of the failing suppliers portfolio had not been migrated to MHHS arrangements for the gaining supplier to be able to take the right actions. It would be important for the gaining supplier to know which wave the failing suppliers were in for migration start date. We would also expect SOLR to be included in the programmes early life support model to ensure that MHHS was not impacted and any potential issues and replans of capacity were accounted for and that this was an adapatble and moveable approach. | This has been discussed in the Migration Group and the feedback was: ID 15 – Migration Capacity during SoLR We have been considering the issue of how migration would be managed for MPANs that are subject to a SOLR between M11 and M15 and the principles that should govern this: • Where a Supplier Gains MPANs as part of a SOLR, capacity will be allocated as per existing rules to the incoming Supplier • The Incoming Supplier will not be held to any Migration Start Date agreed by the outgoing Supplier • The incoming Supplier will be allowed to designate a new Migration Start Date and submit a Migration Plan for the MPANs being acquired. The plan must adhere to the Migration framework. • The obligation to migrate all MPANs by M15 remains Once a SOLR has been confirmed an account manager from the MCC will engage the incoming supplier to initiate the planning process. It is recognised that there will be preparatory activity required therefore we would propose a period of eight weeks for plans to be created and submitted to the MCC. Depending upon proximity to M15 this may have to be expedited This information is available via the MHHS Collaboration based if you have signed up to it.
7 | E.ON Next | 9 | 1.9 | We agree with the scenarios that you have stated for a non qualified supplier E.ON Next would be qualified so would not adopt this process | Statement - No action required
8 | E.ON Next | 10 | 1.11 | We agree that the additional information of, QAD status, Linked to P476, Migration status and Dip status would support the SOLR process and the gaining supplier with next steps to take. | Statement - No action required
9 | Avanade (DIP Service Provider) | pp2-3 | 1.2.3 & 1.2.4 | Minor feedback on 2 screenshots in the SoLR Guidance document - for review by DIP Manager | This has now been updated and shared on the collaboration base
10 | National Energy System Operator (NESO) |  |  | NESO is not a DIP user and does not receive data direct from the DIP. NESO receives settlement data from Elexon in files such as the P0210 and the SAA-I014. NESO acknowledges the risk of a SOLR event during migration, however NESO does not believe that it is directly impacted by such an event and any data issues will be resolved prior to it receiving its settlement files. | Statement - No action required
11 | National Grid Electricity Distribution | 6 | 1.5 | The temporary mismatch of data between ISD and the DIP Identifier/routing is unlikely to cause any operational or reporting issues for NGED, specifically in terms of DUoS billing, as ISD entity 45 is not used by DURABILL when producing outgoing messages or any daily data management processes. In addition, the data in entity M16 is used to determine the DIP ID effective on the date the message was produced but as this DIP ID will be the same on both the end dated and the new records, the production of the outbound message will be the same (irrespective of whether the message was produced before or after the ISD updates have been made and loaded into DURABILL). | The respondent has highlighted that they do not believe they are directly impacted
12 | National Grid Electricity Distribution | n/a | n/a | According to the DIP Guidance Document, it appears that a SoLR may be informed by the DIP Manager of the relevant webhooks address(es) that they need to set up, either before or after the point that they become responsible for the MPID. With this in mind, if the DIP Manager does not inform the SoLR of the relevant webhooks address(es) until after they become responsible for the MPID, please could you clarify what would happen to any REP900s that are issued from DURABILL between the point of the SoLR taking responsibility and the webhook address(es) being set up? We would stress that it is imperative for all DUoS invoices to reach the SoLR reliably and without delay, in order to ensure timely payments. We would also like to ensure that there will not be a requirement/need for the DNO to resend volumes of messages in this scenario. | We would recommend that If the Replacement Supplier sets up their webhooks prior to the SoLR date, then no messages are lost. Prior to the SoLR date messages are routed to the Failing Supplier, after the SoLR date messages are routed to the Replacement Supplier. There will be a continuity of service for the DIP Id. That is the Replacement Suppliers responsibility to action.
13 | National Grid Electricity Distribution | n/a | n/a | In common scenarios where a SoLR takes responsibility for an MPID part way through a month, referring specifically to DUoS billing for that month in particular, please could you clarify what the obligations of the SoLR would be in respect of SITE invoices that are generated to cover settlement dates prior to the point of them taking responsibility of the MPID? To clarify, two SITE invoices (on separate REP900s) would be issued for that month due to the MPID transfer, the first for the pre-transfer period and the second for the point that the SoLR took responsibility onwards. However due to both invoices being issued to the same MPID/DIP ID, they would both be sent to the SoLR. Would the SoLR have to pay the invoice which covers settlement dates prior to the point that they took responsibility? And if so, would there be a facility to claim this amount back? | Elexon, Helix with the support of the MHHSP are working together with the LDSO to understand and address this concern
14 | National Grid Electricity Distribution | n/a | n/a | At present the option is available for HH PDF invoices to be emailed, so invoices for periods prior to the SoLR will be addressed to the administrator and may not be seen by the supplier taking responsibility. If this supplier begins to receive invoices that are to cover periods prior to the date that they took over, we would question whether this could cause confusion which may lead to potential issues and/or additional queries for DNOs. | Elexon, Helix with the support of the MHHSP are working together with the LDSO to understand and address this concern
15 | National Grid Electricity Distribution | n/a | n/a | We have some concerns that the proposal for ISD Entity 45 is to end date the existing record with the old company registration number and create a new record with the new company registration number and a new EFD. This would mean that the EFD for the Supplier MPID is amended to a date after existing SSD’s for the same Supplier MPID, causing data integrity issues, and restricting the Suppliers ability to retrospectively change data prior to their new EFD. This could have unintentional impacts on CSS/Registration systems. | Elexon, Helix with the support of the MHHSP are working together with the LDSO to understand and address this concern
16 | Electricity North West Ltd | Page 6 | SoLR Process Consultation | DNOs are involved in the downstream processes when a Suppliers registrations are suspended and following a SolR being appointed. We have concerns the current process has not considered the impact or role on DNOs sufficiently for both these instances. Specifically, we note the current process lack defining and have not addressed the following questions: 1) what process are in place to ensure that the relevant webhooks addresses are set up by the SoLR party in a timely manner in order to receive MHHS transactions? 2) how will the process ensure that all relevant transactions that were addressed/sent to the original Supplier are forwarded to the the SoLR party and avoid the need for any resending of data or other intervention from sending Parties? There is potential that outbound messages may not reach the SOLR if they have not set up the relevant webhooks address in time as they may not be informed of the DIP ID until after they have assumed responsibility for the MPID. We are raising this as a concern and request clarity and a defined process on this part of the process. As currently written the proposals, could lead to DNOs being forced to re-trigger volumes of messages and this could also have the potential to delay DUoS payment to DNOs etc. | We would recommend that If the Replacement Supplier sets up their webhooks prior to the SoLR date, then no messages are lost. Prior to the SoLR date messages are routed to the Failing Supplier, after the SoLR date messages are routed to the Replacement Supplier. There will be a continuity of service for the DIP Id. That is the Replacement Suppliers responsibility to action.
17 | Electricity North West Ltd | Page 6 | SoLR Process Consultation | We have concerns the current process does not provide assurance on DuoS billing. If the same DIP ID is retained for old and new supplier then invoices (via REP900s) and aggregated billing statements (via REP901s) will be issued to the SoLR for settlement dates prior to the date that they were appointed. How will the process ensure that this does not cause any issues for reconciliation and payment of invoices by the SoLR? Current legacy process allows LDSO's the option to email HH PDF invoices so anything prior to the SOLR is addressed to the administrator if appropriate and are not seen by the incoming supplier. If the incoming supplier starts receiving invoices for periods prior to the date they took responsibility will this cause any issues/confusion/additional queries etc? We request this is considered and assurances put in place as part of this process. | Elexon, Helix with the support of the MHHSP are working together with the LDSO to understand and address this concern
18 | Electricity North West Ltd | n/a | n/a | We support/endorse the St Clements response | The respondent supported another respondents comments
19 | Scottish Power Energy Networks | 5 | 1.3 | We do not believe that it is appropriate to state that this mainly affects suppliers, this process affects other Industry participants and if one is being mentioned, we believe that all parties impacted should be referenced. DNO's are impacted in terms of the Registration service and Billing, we need to ensure that the appropriate updates are made to systems to allow industry processes to reflect the SOLR. While this document appears to have been reviewed by many parties, there does not appear to have been any recognition of the DNO processes relating to SOLR and any impacts on the Registration systems to ensure continuity of processes. In terms of billing if the same MPID is used there will be no way to differentiate the previous supplier invoices from the new supplier , this will result in both inaccurate billing and confusion with Suppliers. | Elexon, Helix and the MHHSP are working together with the LDSO to understand and address this concern
20 | Scottish Power Energy Networks | 5 | 1.3 | Text states that the intent of a SOLR, is that a customer continues to receive uninterrupted electricity and gas supply. We would suggest that this is reworded to say something along the lines of, that the customer will continue to be billed by a supplier with no interruption for their Electricity or Gas supply. (The current text implies that in the event of an Energy Supplier failing in the market that the Networks would discontinue the physical connection). | Consultation updated
21 | Scottish Power Energy Networks | 6 | 1.5 | closing down of the Entity M16 and E45 and the raising of a new Entity M16 and E45 to align the Market Participant to DIP Participant Mapping Table both in ISD and DIP would cause issues for MPRS BAU Processes. Where the new supplier wishes to update any retrospective (incorrect data) they will not be able to do so prior to the new mapping dates, this could lead to customer detriment depending on the information to be corrected. | Elexon, Helix with the support of the MHHSP are working together with the LDSO to understand and address this concern
22 | Scottish Power Energy Networks | 6 | 1.5 | Actions a Supplier would need to take. Having read this in conjunction with the guidance. We do not believe that the timings (as written) are stringent or clear enough. If there is a delay in the Supplier being able to 'onboard', we have a concern that if there are any delays that this may cause integrity issues on the MPRS system and cause failures in messages being processed. This in turn may cause an increase in registration incidents with the CSS and put an onerous amount of time and resource on the DNO to resolve. We would not want DNO's to be seen as the cause of this issue. We are of the view that the onboarding should commence prior to the EFD to ensure that everything is up an running prior to that date (we assume that this is the intention of this guidance, but this is not clear). | Elexon, Helix with the support of the MHHSP are working together with the LDSO to understand and address this concern
23 | Scottish Power Energy Networks | 6 & 8 | 1.5 & 1.8.2 | If the Entity 45 and M16 are end dated, how are updates from MPRS expected to flow to other market participants (outside of the registration process) Any IF-045s that MPRS may need to send to the Revoked Supplier will be rejected by the DIP inappropriately and may result in incidents being raised to resolve incorrectly. Similar issues will occur for IF-018s and IF-006 for LDSO and Metering Service updates on these MPANs where the current supplier is copied in. We do not believe that the proposed solution considers these issues | Elexon, Helix with the support of the MHHSP are working together with the LDSO to understand and address this concern
24 | Scottish Power Energy Networks | 8 | 1.8.1 | It is unclear to us what is meant by the following section: It is important to highlight that Participants will need to consider any Exemptions from MHHS Requirements for Smart Meter Segment (SMS) and Unmetered Supply (UMS) with a Supplier Qualification that they have in place. Code Bodies will collaborate with Suppliers completing Qualification on any Placing Reliance implications of a SoLR. We would assume that if a supplier has an exception on place for a particular market sector, this should be considered by Ofgem at the point that the details of the supplier exiting the market are provided. If the incoming Supplier is not qualified at the point of the SOLR date, surely this would prohibit them from becoming a SOLR supplier. | To clarify we were highlighting that if a Supplier had an exemptions in place then Elexon would provide that information to Ofgem for consideration as part of the SoLR process.
25 | Scottish Power Energy Networks | 6 |  | We have concerns the current process does not provide assurance on DuoS billing. If the same DIP ID is retained for old and new supplier then invoices (via REP900s) and aggregated billing statements (via REP901s) will be issued to the SoLR for settlement dates prior to the date that they were appointed. How will the process ensure that this does not cause any issues for reconciliation and payment of invoices by the SoLR? Current legacy process allows LDSO's the option to email HH PDF invoices so anything prior to the SOLR is addressed to the administrator if appropriate and are not seen by the incoming supplier. If the incoming supplier starts receiving invoices for periods prior to the date they took responsibility will this cause any issues/confusion/additional queries etc? We request this is considered and assurances put in place as part of this process. | Elexon, Helix with the support of the MHHSP are working together with the LDSO to understand and address this concern
26 | Scottish Power Energy Networks | 10 | 1.11 | We strongly support the intention to provide the migration status, and details of any exemptions to Ofgem. We believe that this would allow Ofgem to make an informed decision in their appointment of the SOLR supplier, and their ability to support industry processes where the outgoing supplier is MHH migrated. | The respondent has confirmed the additional information Elexon has suggested to provide would support the SoLR process for the Replacement Supplier.
27 | Scottish Power Energy Networks | 11 | 2.2 | We would suggest that there is a section in here around the update to the Alliances if there are to be changes to the ISD Effective dates | Elexon, Helix with the support of the MHHSP are working together with the LDSO to understand and address this concern
28 | Scottish Power Energy Networks |  | General | We have seen the response provided from SCS and fully support the points made (and as such have no added these in here to avoid duplication). | The respondent supported another respondents comments
29 | Northern Powergrid | N/A | N/A | Consideration should be given to how DNOs are impacted by this process, as a recipient of change of supplier data and the data master for alliance data. | Elexon, Helix with the support of the MHHSP are working together with the LDSO to understand and address this concern
30 | Northern Powergrid | N/A | N/A | Our service provider, St Clements, have provided comments related to MPRS functionality. | Elexon, Helix with the support of the MHHSP are working together with the LDSO to understand and address this concern
31 | Northern Powergrid | N/A | N/A | The REC and DCUSA governance relating to this process should be impact assessed and existing operational issues considered. | Elexon, Helix with the support of the MHHSP are working together with the LDSO to understand and address this concern
32 | Northern Powergrid | N/A | N/A | Thought should be given to how a SoLR will be dealt with during MHHS migration, in terms of volumes, impacts etc. | This has been discussed in the Migration Group and the feedback was: ID 15 – Migration Capacity during SoLR We have been considering the issue of how migration would be managed for MPANs that are subject to a SOLR between M11 and M15 and the principles that should govern this: • Where a Supplier Gains MPANs as part of a SOLR, capacity will be allocated as per existing rules to the incoming Supplier • The Incoming Supplier will not be held to any Migration Start Date agreed by the outgoing Supplier • The incoming Supplier will be allowed to designate a new Migration Start Date and submit a Migration Plan for the MPANs being acquired. The plan must adhere to the Migration framework. • The obligation to migrate all MPANs by M15 remains Once a SOLR has been confirmed an account manager from the MCC will engage the incoming supplier to initiate the planning process. It is recognised that there will be preparatory activity required therefore we would propose a period of eight weeks for plans to be created and submitted to the MCC. Depending upon proximity to M15 this may have to be expedited This information is available via the MHHS Collaboration based if you have signed up to it.
33 | British Gas |  | General | The scope states that "SoLRs happen on the transfer of an MPID, not a CoS". However, this is not how SoLR events operate in practice, at least in our experience, most recently with Rebel Energy. Whilst its true that MPIDs are transferred to the SoLR supplier once Ofgem has made its decision as to which supplier will become the SoLR, the SoLR process and transfer of customers is typically completed immediatly though CoS - transferring the failed suppliers customers into the SoLR systems. This is how we have operated every SoLR event that we have been appointed for. This document is based on the assumption that the SoLR supplier will operate the failed suppliers MPID / systems and transfer the customers into their own systems / portfolio at a future point. As such the processes describing the establishment of new DIP IDs for the failed suppliers MPIDs and issues created through the re-mapping of MPIDs to the replacement supplier, would not be relevant in our experience. Many of the issues that this consultation seeks to address only occur under this scenario. We believe that the SoLR working group could benefit from re-visiting the processes and issues described in this consultation, taking input from REC parties / personel who have been actively engaged in recent SoLR events. We would be happy to support such conversations if helpful. | The MPID transfer has to happen first but we understand that Replacement Supplier will aim to CoS MPAN's as quickly as possible to one of their existing MPIDs, and that’s is what also happens with CSS.
34 | UK Power Networks | n/a | n/a | Based on our current understanding of the intended process, if there is a delay in the new Supplier completing all activities associated with setting up new webhooks, will any messages transmitted to the DIP Id (e.g. REP-900, REP-901) since the SoLR effective date be immediately available to them? | We would recommend that If the Replacement Supplier sets up their webhooks prior to the SoLR date, then no messages are lost. Prior to the SoLR date messages are routed to the Failing Supplier, after the SoLR date messages are routed to the Replacement Supplier. There will be a continuity of service for the DIP Id. That is the Replacement Suppliers responsibility to action.
35 | UK Power Networks | n/a | n/a | Based on our current understanding of the intended process, if there is a delay in the new Supplier completing all activities associated with setting up new webhooks, will the new Supplier be able to use the DIP "replay" functionality to gain access to any messages sent to the DIP Id (e.g. REP-900, REP-901) in the meantime that they may not otherwise have access to? | We would recommend that If the Replacement Supplier sets up their webhooks prior to the SoLR date, then no messages are lost. Prior to the SoLR date messages are routed to the Failing Supplier, after the SoLR date messages are routed to the Replacement Supplier. There will be a continuity of service for the DIP Id. That is the Replacement Suppliers responsibility to action. For a Replacement Supplier they can use the replay functionality but only from their EFD.
36 | EDF Energy |  | All | As discussed in a call with Mark Pemberton/Karen Lavelle/Rob Golding on the 3rd June, the processes for managing a SoLR event set out in the consultation are based on the assumption that the Replacement Supplier becomes directly responsible for managing the MPANS of the Failed Supplier from the point of the SoLR, and that any dataflows and/or DIP messages would need to be routed to the Replacement Supplier’s systems from that point. This is not generally the case. In our experience of managing multiple SoLRs as a Replacement Supplier, what happens on most occasions is that the systems and processes of the Failed Supplier remain in place and operational following the SoLR, usually being operated by the appointed administrator. They will continue to manage the MPANs in the Failed Supplier’s portfolio (although possibly on a reduced basis) until they can be migrated to the Replacement Suppliers systems, usually via the Change of Supplier (CoS) process. Once this migration process is complete steps will be taken to close down the Failed Supplier’s systems, with any remaining dataflows (for example those related to settlement) being routed to the Replacement Supplier from that point. Each SoLR is different and will depend on exactly what has happened to the Failed Supplier – in some cases they will cease to exist and not be able to maintain any operations from that point (in which case the processes detailed in the consultation might be more appropriate), in other cases the Replacement Supplier might choose to retain the Failed Supplier’s MPID (and even their systems) and operate using them on an ongoing basis. The bespoke nature of the SoLR process needs to be reflected in the documentation, and allow for different actions to be taken depending on the exact nature of the SoLR in question. | The failed Supplier should not have access to data once it is transferred, as it has no licence or BSC Obligations it is the Replacement Suppliers responsility. If the Recplacement supplier decides to run the Failing Suplliers systems and process through an Administrator then they need to request access to the data. Establish the required webhooks, security certs under their own ownership.
37 | EDF Energy | 4 | 1.2 | This section notes that ‘ISD will be published every two weeks, which may lead to temporary mismatches between ISD records (such as Entity 45 and M16) and the DIP Identifier’ and that this could have ‘potential implications for data flows, reporting accuracy, and supplier obligations’ however it is not clear what issues this potential mismatch could create. In line with the previous comment, I believe that the impact of this mismatch is unlikely to be material if the Failed Supplier’s systems and processes continue to be operational after the SoLR has occurred and allocated legal responsibility to the Replacement Supplier – in which case it should be possible to continue processing as usual. This section needs to be updated to reflect that the impacts will vary depending on the exact nature of the SoLR and the status of the Failed Supplier’s systems and processes following the event. | Just to clarify the MDD process currently catch's up after a SoLR and can be up to a month after an event, the ISD process is only up to 2 weeks after a SoLR event but as per the ISD Design a new 45 wuold be issued with the SoLR EFD. The DIP will be updated as part of the instruction to Elexon from Ofgem and as per the DIP SoLR Guidance - https://www.mhhsprogramme.co.uk/migration-and-transition/transition/service-activation/elexon-helix-supplier-of-last-resort-solr-consultation.
38 | EDF Energy | 5 | 1.3 | In line with previous comments I think it would be useful to clarify that the transfer of the MPID may not mean that the Replacement Supplier will start to receive+F106 dataflows/DIP messages for that MPID into their systems – in some cases the Failed Supplier’s systems and processes will remain operational, so while the Replacement Supplier is legally responsible for the MPID, they may not carry our processing for that MPID within the same systems as their existing MPIDs. | Just to clarify - The failed Supplier should not have access to data once it is transferred, as it has no licence or BSC Obligations it is the Replacement Suppliers responsibility. If the Replacement supplier decides to run the Failing Suppliers systems and process through an Administrator then they need to request access to the data. Establish the required webhooks, security certs under their own ownership.
39 | EDF Energy | 6 | 1.5 | Typo - SD should be ISD | Consultation updated
40 | EDF Energy | 6 | 1.5 | This section notes that ‘this lag in ISD update may result in temporary inconsistencies’ – however as noted previously these inconsistencies will not have an impact if the Failed Supplier’s systems remain in situ following the SoLR award as they will continue to receive and process DIP messages as ‘business as usual’. Transferring responsibility for an MPID to a new supplier does not necessarily mean that the systems and endpoints associated with that MPID will change. | The Failing Supplier need to work with the Replacement Supplier to gain access to messages and new webhooks established. The Failing Supplier should not have access to data once it is transferred, as it has no licence or BSC Obligations it is the Replacement Suppliers responsibility. If the Replacement supplier decides to run the Failing Suppliers systems and process through an Administrator then they need to request access to the data. Establish the required webhooks, security certs under their own ownership
41 | EDF Energy | 6 | 1.5 | In line with previous comments, where the document refers to ‘What actions a replacement supplier would need to take’, the actions noted would only be required where the Replacement Supplier wants the DIP messages associated with the MPID they have taken on to be directed to a different endpoint/DIP Account – this will not be required if the Failed Supplier’s systems remain in situ after the SoLR award. I think the critical action here is for the Replacement Supplier to contact the DIP Manager immediately following the SoLR award so that they can agree what (if any) changes need to be made to DIP messaging. | The Failing Supplier need to work with the Replacement Supplier to gain access to messages and new webhooks established. The Failing Supplier should not have access to data once it is transferred, as it has no licence or BSC Obligations it is the Replacement Suppliers responsibility. If the Replacement supplier decides to run the Failing Suppliers systems and process through an Administrator then they need to request access to the data. Establish the required webhooks, security certs under their own ownership
42 | EDF Energy | 7 | 1.8 | Typo - no DIP impact_ should be no DIP impact) | Consultation updated
43 | EDF Energy | 8 | 1.8.2 | Typo - the third bullet point in this section should be two bullet points, they sem to have merged into one. | Consultation updated
44 | EDF Energy | 9 | 1.9 | I do not agree that this is an invalid scenario in all cases and stated in the document. Where the Failed Supplier’s systems and process will remain in place and operational until an orderly migration to the Replacement Supplier’s systems can take place (via the Change of Supplier process with a Reverse Migration) this scenario is valid – the Failed Supplier will continue to manage any migrated MPANs in the MHHS arrangements until they are transferred to the Replacement Supplier. This is only an invalid scenario where the Failed Supplier’s systems and processes no longer exist, in which case the Replacement Supplier would not be able to maintain any migrated MPANs. | A non MHHS Qual supplier would not be permitted to manage MHHS enabled meter points - The SoLR process would required the issue of API end points to the incoming Supplier for DIP. These would not be issued to a non Qualified Supplier.
45 | Smartest Energy Business | N/A | SoLR Business Process | Confirmed Reviewed | Respondent confirmed that they had reviewed - No action
46 | Smartest Energy Business | N/A | SoLR - DIP Guidance Note | Confirmed Reviewed | Respondent confirmed that they had reviewed - No action
47 | Smartest Energy Business | 3 | SoLR Process Consultation Final V.01 | Contents page sections do not reflect the document - Summary sections 1.1 - 1.4 and Consultation sections 2.1 - 2.7 appear to have been combined into sections 1.1 - 1.11. Appendix is shown as section 3 in the contents, but is section 2 in the document. This should be updated. | Consultation updated
48 | Smartest Energy Business | 6 | SoLR Process Consultation Final V.01 | typo - 'can managing their systems…' should be 'can manage their systems…' | Consultation updated
49 | Smartest Energy Business | 10 | SoLR Process Consultation Final V.01 | states valid scenarios are in section 2.4 and that the non-valid scenario is in section 2.5, however these sections do not exist and should instead state section 1.8 and section 1.9 respectively | Consultation updated
50 | Smartest Energy Business | 11 | SoLR Process Consultation Final V.01 | States 'Undertake a CoS at a later date to transfer the MPIDs to one of your existing MPIDs.' - should this instead say 'transfer the MSIDs to…' or 'transfer the MPANs to…'? | Consultation updated
51 | Smartest Energy Business | 6 | SoLR Process Consultation Final V.01 | • Do you anticipate any operational or reporting issues resulting from a temporary mismatch (of up to two weeks) between ISD (Entity 45 and M16) and the DIP Identifier and routing within the DIP, following a SoLR event? Answer - No | Respondent confirmed that they had reviewed - No action
52 | Smartest Energy Business | 6 | SoLR Process Consultation Final V.01 | • Would the closing down of the Entity M16 and E45 and the raising of a new Entity M16 and E45 to align the Market Participant to DIP Participant Mapping Table both in ISD and DIP cause any operational or reporting issues? Answer - No | Respondent confirmed that they had reviewed - No action
53 | Smartest Energy Business | 7 | SoLR Process Consultation Final V.01 | • Does the guidance provide enough information for you to manage the process? Answer - Yes | Respondent confirmed that they had reviewed - No action
54 | Smartest Energy Business | 7 | SoLR Process Consultation Final V.01 | • Are there any specific aspects of the DIP id transfer process that you believe require further clarification or guidance to support your operational readiness? If so, please prioritise your top one or two areas of concern. Answer - No | Respondent confirmed that they had reviewed - No action
55 | Smartest Energy Business | 7 | SoLR Process Consultation Final V.01 | • In an SoLR event the replacement Supplier would need to contact the DIP Manager at DIPManager@elexon.co.uk. Is there any further information that you would require? Answer - Yes, clarification of the information to be contained within the initial contact email | If the Replacement Supplier requires new certs and webhooks we would expect the Replacement Supplier to contact/work with the DIP Manager as per the DIP SoLR Guidance - We have provided the contact email address for the Replacement Supplier, in case they need support.
56 | Smartest Energy Business | 8 | SoLR Process Consultation Final V.01 | • In an SoLR event the replacement Supplier would need to contact the MHHS Qualification team at MHHSQualification@elexon.co.uk. Is there any further information that you would require? Answer - Yes, clarification of the information to be contained within the initial contact email | If the Replacement Supplier requires any guidance regarding MHHS Qualification as part of a SoLR - We have provided the contact email address for the Replacement Supplier, in case they need support.
57 | Smartest Energy Business | 8 | SoLR Process Consultation Final V.01 | • In an SoLR event the replacement Supplier would need to contact the MHHS Migration team at Migration@mhhsprogramme.co.uk. Is there any further information that you would require? Answer - Yes, clarification of the information to be contained within the initial contact email | If the Replacement Supplier requires any guidance regarding MHHS Migration as part of a SoLR - We have provided the contact email address for the Replacement Supplier, in case they need support. Obligations on Replacement Suppliers will be contained within the Migration Framework and with discissions held in the Migration Working Group.
58 | Smartest Energy Business | 10 | SoLR Process Consultation Final V.01 | • Do you agree with the four valid scenarios and that your system processes can support these? (Section 2.4) Answer - Yes | Respondent confirmed that they had reviewed - No action
59 | Smartest Energy Business | 10 | SoLR Process Consultation Final V.01 | • Do you agree with the current non-valid scenario? Would your system be able to support if this were to be enacted? (Section 2.5) Answer - Yes | Respondent confirmed that they had reviewed - No action
60 | Smartest Energy Business | 10 | SoLR Process Consultation Final V.01 | We are considering proposing the following additional information for Ofgem. Please comment on their relevance, usefulness, or feasibility. • The Qualification Status of all Parties (MHHS Qualified or Not). • If Parties have any Exemptions as part of their Qualification linked to P476. • Migration Status against Migration plan for Parties MHHS Qualified. • DIP Status. Answer - The above all appear to be relevant, useful and feasible | The respondent has confirmed the additional information Elexon has suggested to provide would support the SoLR process for the Replacement Supplier.
61 | Smartest Energy Business | 10 | SoLR Process Consultation Final V.01 | • Is there any additional information you think we should be providing Ofgem? Answer - No, the four additional items listed on page 10 appear to cover it. | The respondent has confirmed the additional information Elexon has suggested to provide would support the SoLR process for the Replacement Supplier.
62 | Smart DCC | 2 | 1.2.1.2.3 – Supplier of Last Resort Business Process | No concerns; this doesn't impact DCC at all. | Respondent confirmed that they had reviewed - No action
63 | Smart DCC | 3 | 1.2.1.2.3 – Elexon SOLR Internal update Business Process | Transfer of MPIDs is in the standard process however as in the recent case with British gas they chose to switch all of the consumers and therefore this process isn't needed, this won't always be the case but in the instances where we use switching (which is the cleaner way anyway) I dont think this section is needed though i dont think it would cause harm to keep it as they would be empty mpids shortly after the process begins. (see associated image to the right by DCC_2) | To clarify the Transfer of MPID is enacted by Elexon and impacted Code Bodies on behalf of Ofgem for the Replacement Supplier and needs to happen first before a CoS can be enacted. A CoS can happen straight after the transfer of MPID, this process is driven by the Replacement Supplier.
64 | Smart DCC | 3 | 1.2.1.2.3 – Elexon SOLR Internal update Business Process | We don't understasnd this part of the process; Elexon seem to be referring to CSS receiving updates via email (from the customer?) which then pass onto the code manager, this is not something we've seen before nor can understand how it would work. We would need further understand on this to comment properly on this element. What is this process, how does it work and why? (see associated image to the right by DCC_3) | Elexon do not have any contact with the DCC during the SoLR Event. The existing communications between Ofgem, RECCO and DCC will remain As-Is
65 | Smart DCC |  |  | Can we confirm if the SoLR trigger for the DCC process will remain Ofgem led? I’m assuming this is the case but good if we can confirm. | Ofgem will continue to inform Code Bodies of SoLRs
66 | Smart DCC |  |  | For the scenario where the SoLR gains a failed supplier MPID and does not immediately switch MPXN to its other Supplier MPID’s we could highlight a risk that the SoLR would need to manage: Where an MDR is appointed for an MPAN, this will remain appointed in CSS following the MPID transfer (I think) but the SoLR may not have contractual/operational arrangements in place with the MDR; could this create a period where HH data is not provided into settlements + would the transfer invalidate the legal permission that the MDR has to access this data? | The risk is based on the size of the Portfolio. The replacement supplier would have to get contracts in place with the current agents or new agents as quickly as possible. The risk is the same today, as it s currently with a SoLR process and will remain the same until the Settlement Calendar is shorten. Agents act today.
67 | Smart DCC |  |  | What happens if the SoLR is not managed through MPID transfer e.g. Switching/COS gain. Where is this described? | The MPID transfer has to happen first but we understand that Replacement Supplier will aim to CoS MPAN's as quickly as possible to one of their existing MPIDs, and that’s is what also happens with CSS.
68 | Smart DCC |  |  | What is the mechanism for informing the Participants of misalignments and data accuracy? | Emailed DCC - Still awaiting confirmation
69 | Smart DCC |  |  | What is the mechanism for ensuring/validating the gaining party is in receipt of all losing party customer data/information? | Ofgem provides a portfolio report to prospective suppliers, from the information provided from Elexon and Xoserve.
70 | Smart DCC |  |  | How will this SoLR impact the role of an MDR, if at all? | The risk is based on the size of the Portfolio. The replacement supplier would have to get contracts in place with the current agents or new agents as quickly as possible. The risk is the same today, as it s currently with a SoLR process and will remain the same until the Settlement Calendar is shorten. Agents act today.
71 | Smart DCC |  |  | Mentions that MHHS to Non MHHS will not be able to service these meter points. How will this impact prepay consumers and those most critical? Will (and when) they be placed on a non disconnect and for how long? | We can not support the scenario of migrated MPANs being transferred to a Non Qualified Supplier
72 | Smart DCC |  |  | No feedback. There is no reference to DCC within this document. | Respondent confirmed that they had reviewed - No action
73 | Smart DCC |  |  | No feedback. There is no reference to DCC within this document. | Respondent confirmed that they had reviewed - No action
74 | Smart DCC |  |  | No feedback. There is no reference to DCC within this document. | Respondent confirmed that they had reviewed - No action
75 | Smart DCC |  |  | The Elexon consultation seeks to define and prepare industry-wide coordination during a structurally complex MHHS transition. My Service Design ensures that DCC performs its technical and operational duties, I think the 2 documents complement each other, however, based on my knowledge I dont see there being any direct feedback that i can provide. | Respondent confirmed that they had reviewed - No action
76 | ESG-NiR | N/A | Diagram 1.2.1.2.3 - Top Diagram | The Diagram needs to be updated also include Communications with other participants such as DCP where a supplier (either SolR, Receiving or both ) use the services of such an organisation | Elexon will be issuing Circulars as we do now, which Participants can sign up for. With DIP Connection Providers - Would expect the Replacement Supplier to contact relevant agents and have commercial arrangements in place.
77 | ESG-NiR | N/A | Diagram 1.2.1.2.3 - Top Diagram | The Diagram needs to be updated also include communications with other participants such as an Administrators that will be involved in running the SoLR party through to completion of the SoLR event. | We assume that an Administrator would be appointed to run the failed supplier systems/processes and that Ofgem would inform the Replacement supplier of who that would be. Elexon has no interaction with Administrator of a Failed Supplier.
78 | ESG-NiR | N/A | Diagram 1.2.1.2.3 - Top Diagram | There appear to be many odd dotted lines scattered around the flowchart. Are these intentional? If so please provide detail as to their purpose, if not please remove | The Diagram has been updated. V0.11 issued
79 | ESG-NiR | N/A | Diagram 1.2.1.2.3 - Top Diagram | Please provide a key to explain the various signs used throughout the diagram within the various flow chart symbols | The Diagram has been updated. Key added
80 | ESG-NiR | N/A | Diagram 1.2.1.2.3 - Top Diagram | The Flows chart uses many occurrences of the Decision symbol ( diamond / rhombus) with + signs within them. These are not standard flowchart nomenclature as Diamonds represent decision / branching points. Please explain their purpose. | The Diagram has been updated. Key added
81 | ESG-NiR | N/A | Diagram 1.2.1.2.3 - Top Diagram | Many symbols contain + symbols that appear to have hyperlinks to other documents, many + symbols do not, please clarify the difference between them. If there are differences, please clarify how readers are expected to interpret such differences | The Diagram has been updated. Key added
82 | ESG-NiR | N/A | Diagram 1.2.1.2.3 - Lower Diagram | The Diagram needs to be updated also include Communications with other participants such as DCP where a supplier (either SolR, Receiving or both ) use the services of such an organisation | Elexon will be issuing Circulars as we do now, which Participants can sign up for. With DIP Connection Providers - Would expect the Replacement Supplier to contact relevant agents and have commercial arrangements in place.
83 | ESG-NiR | N/A | Diagram 1.2.1.2.3 - Lower Diagram | The Diagram needs to be updated also include communications with other participants such as an Administrators that will be involved in running the SoLR party through to completion of the SoLR event. | We assume that an Administrator would be appointed to run the failed supplier systems/processes and that Ofgem would inform the Replacement supplier of who that would be. Elexon has no interaction with Administrator of a Failed Supplier.
84 | ESG-NiR | N/A | Diagram 1.2.1.2.3 - Lower Diagram | The Diagram needs to be updated also include communications with other participants such as an GlobalSign that will be involved in undertaking physical Certificate exchanges if required ( Please also see later details as this interaction will be a potentially significant concern during the physical SoLR Process) | We have assumed that if a Replacement Supplier has access to DIP then they will already have GobalSign - Please refer to the DIP SoLR Guidance - https://www.mhhsprogramme.co.uk/migration-and-transition/transition/service-activation/elexon-helix-supplier-of-last-resort-solr-consultation.
85 | ESG-NiR | N/A | Diagram 1.2.1.2.3 - Lower Diagram | There appear to be many odd dotted lines scattered around the flowchart. Are these intentional? If so please provide detail as to their purpose, if not please remove | The Diagram has been updated. V0.11 issued
86 | ESG-NiR | N/A | Diagram 1.2.1.2.3 - Lower Diagram | Please provide a key to explain the various signs used throughout the diagram within the various flow chart symbols | The Diagram has been updated.Key added
87 | ESG-NiR | N/A | Diagram 1.2.1.2.3 - Lower Diagram | The Flows chart uses many occurrences of the Decision symbol ( diamond / rhombus) with + signs within them. These are not standard flowchart nomenclature as Diamonds represent decision / branching points. Please explain their purpose. | The Diagram has been updated. V0.11 issued
89 | St Clements | N/A | N/A | What reporting requirements will there be around the SoLR process. The current Revoked Supplier License Report does not include new MHHS Data Items. Data Items that may be relevant but are currently not reported on include: MHHS Migration Status, Connection Type, Market Segment, Domestic Premise Indicator, Data Service and Metering Service | Ofgem provides a portfolio report to prospective suppliers, from the information provided by Elexon and Xoserve. If we want additional information we would need to work with Ofgem on how that information is provided.
90 | St Clements | N/A | N/A | MPRS does not load Company Registration Number from ISD Entity 45, this is not a necessary data item for MPRS functionality. MPRS does load the MPID, EFD and ETD. The End Dated record in ISD Entity 45 will trigger the end dating of the Supplier record in MPRS, and end date the Supplier Alliance triggering a notification to CSS. The new record in ISD Entity 45 will update the existing MPID record in MPRS, with the new EFD, this will recreate the alliance in MRPS and trigger another alliance update to CSS. Risks and issues 1. If the records are loaded correctly, the end result will be a new EFD for the existing Supplier that is AFTER the existing SSD's in MPRS for that Supplier, causing data integrity issues. 2. The new EFD for the Supplier may also lead to restrictions in what the Supplier is able to retrospectively update for the MPAN. 3. There is a risk the records are ordered incorrectly in ISD, resulting in the Supplier being end dated in MPRS. 4. There is a risk CSS loads the alliance notifications which are sent in close proximety in the wrong order resulting in the Alliance being end dated in CSS. | Elexon, Helix with the support of the MHHSP are working together with the LDSO to understand and address this concern
91 | St Clements | N/A | N/A | The MPID/DIP ID mapping is not changing and so the record in M16 does not need to be amended. MPRS uses this table to update the DIP ID for the existing Supplier relating to the MPID, and to update the EFD/ETD of that DIP ID. If the proposed SoLR process was used it would give rise to the following issues 1. If records were ordered incorrectly, the DIP ID could be end dated in MPRS, meaning MPRS would not recognise the Supplier as a valid MHHS participant 2. If the records were ordered correctly, the EFD of the DIP ID will be amended to a later date which could cause data integrity issues or validation issues | Elexon, Helix with the support of the MHHSP are working together with the LDSO to understand and address this concern
92 | St Clements | N/A | N/A | Pending migrations could still receive follow on DIP messages and be progressed to confirmed after the SoLR and so if there are any pending migrations for a MHHS Qualified Supplier, the respective SoLR must be MHHS Qualified. The documentation specified this for Active Migrated MPANs, but Pending Migrations also need to be considered. | Portfolios with migrated MPANs or Pending Migrations should only be given to MHHS Qualfied Suppliers. Migraton capacity will be allocated to the Replacement Supplier.
93 | St Clements |  | 1.5 | How will the setting of the ETDs work in practice? Will the the ETD be set in ISD M16/45 when OFGEM enforces the ban on customer gains, preventing DIP access for the Supplier. Then the EFD of the new record is set once the bidding is complete and the winning Supplier takes control? Essentially, not Ending the old and creating a new record in the same ISD Catalogue Version Or will The Records remain open with DIP access controlled through other methods (certificate revokation) and then the ETD and new EFD records created in the same ISD Catalogue version? | Elexon, Helix with the support of the MHHSP are working together with the LDSO to understand and address this concern
94 | St Clements | N/A | 1.5 | If the DIP ID is end dated then any IF-045s that MPRS may need to send to the Revoked Supplier will be rejected by the DIP raising falase positive support tickets. Similar issues will occure for IF-018s and IF-006 for LDSO and Metering Service updates on these MPANs where the current supplier is copied in | We would recommend that If the Replacement Supplier sets up their webhooks prior to the SoLR date, then no messages are lost. Prior to the SoLR date messages are routed to the Failing Supplier, after the SoLR date messages are routed to the Replacement Supplier. There will be a continuity of service for the DIP Id. That is the Replacement Suppliers responsibility to action.
95 | St Clements | N/A | 1.8.2 | Currently Gaining Suppliers who win control of a SOLRed supplier's portfolio will often transfer that portfolio to its own MPID (via bulk CoS) then close off the MPID in MDD. This activity may impact MPRS Performance during transition. Consideration should be given to delaying internal switching until transition is complete | In almost all instances Suppliers will wish to undertake the CoS activity after the MOID transfer, to allow them to manage these customers effectively within their own systems, restrictions on this activity could lead to customer detriment in terms of effectively servicing these accounts. Furthermore switching volumes and migration volumes fall under sperate, concurrent obligations. The portfolio sizes of Suppliers subject to SOLR tends to be sub 100k portfolio size and therefore well within supported switching volumes.
96 | St Clements | N/A | 1.11 | consideration should be given to MHHS Associated (linked) Export MPANs where the Import Supplier has their licence revoked but the Export Supplier is still operational. If the Metering Service is part of the Supplier Business and is also suspended then the Export MPAN effectively has no functional Metering Service and the Export Supplier cannot appoint their own service without the Association being ended. | To confirm this is out of scope for this consultation. The Replacement supplier appoints their own agents and a qualified MOA that should be able to support their portfolio - Suggest raising with RECCo as an issue
97 | St Clements | N/A | N/A | Preferred Solution is for M16 to be untouched in the case of a SoLR as the mapping is not changing, and for the existing record in ISD Entity 45 to be updated with the new customer registration number, but existing EFD. If the Customer Registration Number cannot be amended in ISD Entity 45, our next preference is for the existing record to be removed entirely and a new record created for the new Customer Registration Number, but with the original EFD of the MPID (the EFD that existed for the deleted record). This is to ensure the Supplier MPID EFD is prior to SSD of it's associated registrations. | Elexon, Helix with the support of the MHHSP are working together with the LDSO to understand and address this concern
For the below comments - Co-pilot assistance was used in anaylsis of themes
98 | ESG | ESG | Misalignment with Industry Practice | Proposed MPID transfer approach conflicts with common use of CoS in actual SoLR events. | To clarify the Transfer of MPID is enacted by Elexon and impacted Code Bodies on behalf of Ofgem for the Replacement Supplier and needs to happen first before a CoS can be enacted. A CoS can happen straight after the transfer of MPID, this process is driven by the Replacement Supplier.
99 | ESG |  | System Lockdown at EFT | Locking systems at EFT disrupts message flows, causing data misalignment and settlement issues. | The Failing Supplier need to work with the Replacement Supplier to gain access to messages and new webhooks established. The Failing Supplier should not have access to data once it is transferred, as it has no licence or BSC Obligations it is the Replacement Suppliers responsibility. If the Replacement supplier decides to run the Failing Suppliers systems and process through an Administrator then they need to request access to the data. Establish the required webhooks, security certs under their own ownership
100 | ESG |  | Loss of System Access | Revoking API keys, DIP IDs, and certificates at EFT prevents outgoing suppliers from completing data exchanges. | The Failing Supplier need to work with the Replacement Supplier to gain access to messages and new webhooks established. The Failing Supplier should not have access to data once it is transferred, as it has no licence or BSC Obligations it is the Replacement Suppliers responsibility. If the Replacement supplier decides to run the Failing Suppliers systems and process through an Administrator then they need to request access to the data. Establish the required webhooks, security certs under their own ownership
101 | ESG |  | Administrator Role Overlooked | Lack of guidance for Administrators managing technical tasks like PKI and system access. | We assume that an Administrator would be appointed to run the failed supplier systems/processes and that Ofgem would inform the Replacement supplier of who that would be. Elexon has no interaction with Administrator of a Failed Supplier. If the Replacement Supplier requires the Administrator to have access to data/systems they need to request/approve that access.
102 | ESG |  | Migration Complexity | ETL is risky and resource-intensive; CoS is more stable but requires extended system access. | To clarify the Transfer of MPID is enacted by Elexon and impacted Code Bodies on behalf of Ofgem for the Replacement Supplier and needs to happen first before a CoS can be enacted. A CoS can happen straight after the transfer of MPID, this process is driven by the Replacement Supplier.
103 | ESG |  | DIP Portal Access Risks | Removing DCP/IT users too early blocks critical PKI and migration activities. | The alignment will be as per the Ofgem instruction - The DIP Manager has provided SoLR Guidance which was issued with the Consultation and is available on the Collaboration base - https://www.mhhsprogramme.co.uk/migration-and-transition/transition/service-activation/elexon-helix-supplier-of-last-resort-solr-consultation. The Failing Supplier need to work with the Replacement Supplier to gain access to messages and new webhooks established. The Failing Supplier should not have access to data once it is transferred, as it has no licence or BSC Obligations it is the Replacement Suppliers responsibility. If the Replacement supplier decides to run the Failing Suppliers systems and process through an Administrator then they need to request access to the data. Establish the required webhooks, security certs under their own ownership
104 | ESG |  | Fragmented SoLR Processes | Lack of alignment between MHHS, Smart, CSS, and other industry SoLR processes increases risk of data inconsistency. | We have been working with MHHS, RECCo and the process is as close to the AS-IS now and is aligned with CSS and DIP.