## Slide 1: M10/M11 LDSO Reporting Template
Version 1.0
MHHS-DEL4059
Document Classification: Public

## Slide 2: M10/M11 Cutover Plan Reporting
LDSOs are required to provide regular status updates to the Programme, outlining progress on their cutover activities
To support this, the Programme has developed templates for Participants to complete, which include:
  A list of all cutover activities for which Participants are required to provide a RAG status and an expected finish date
  A risk and issue log
  A free-text section for any additional feedback or comments
Reporting will occur on a weekly basis from the 6th August up until M10. Details of the reporting cadence can be found on slides 5 and 6. The completed templates should be sent to the OpReadiness team at opreadiness@mhhsprogramme.co.uk by 3pm each Wednesday
The Programme will collate the submissions from Participants and produce a consolidated dashboard, which will be made available on the Collaboration Base. This dashboard will provide an overview of collective progress
Please note: The dashboard will present anonymised data, no individual Participant names will be disclosed, only aggregated figures will be shared

## Slide 3
Monday | Tuesday | Wednesday | Thursday | Friday
28/07 | 29/07 | 30/07 | 31/07 | 01/07
04/08 | 05/08 | 06/08 | 07/08 | 08/08
11/08 | 12/08 | 13/08 | 14/08 | 15/08
18/08 | 19/08 | 20/08 | 21/08 | 22/08
25/08 | 26/08 | 27/08 | 28/08 | 29/08
M10/M11 Cutover Plan Reporting Schedule (1/2)
Reporting shared with Programme
Reporting shared with Programme
Reporting shared with Programme
Reporting shared with Programme
Weekly update at GLIG
Weekly update at GLIG
Weekly update at GLIG
Weekly update at GLIG
TORWG

## Slide 4
Monday | Tuesday | Wednesday | Thursday | Friday
01/09 | 02/09 | 03/09 | 04/09 | 05/09
08/09 | 09/09 | 10/09 | 11/09 | 12/09
15/09 | 16/09 | 17/09 | 18/09 | 19/09
22/09 | 23/09 | 24/09 | 25/09 | 26/09
29/09 | 30/09 | 01/10 | 02/10 | 03/10
M10/M11 Cutover Plan Reporting Schedule (2/2)
Reporting shared with Programme
Weekly update at GLIG
Weekly update at GLIG
Weekly update at GLIG
TORWG
PSG
MCAG
Reporting shared with Programme
Reporting shared with Programme
TORWG

## Slide 5: M10/M11 Cutover Plan Status Report – LDSOs
Activities | Start Date | Finish Date | Expected Finish Date | Current RAG | Commentary
Qualification Pathway 2 |  | 29/08/2025 | LDSO to update | LDSO to update | LDSO to update (if relevant)
Qualification Pathway 3 |  | 11/09/2025 | LDSO to update | LDSO to update | LDSO to update (if relevant)
Early Life Support Implemented |  | 19/09/2025 | LDSO to update | LDSO to update | LDSO to update
Completion of the pre-M10 MHHS Data Cleanse | 2024 | 22/09/2025 | LDSO to update | LDSO to update | LDSO to update
DIP Onboarding | 04/08/2025 | 22/08/2025 | LDSO to update | LDSO to update | LDSO to update
Deployment of MPRS 9 | 06/08/2025 | 01/09/2025 | LDSO to update | LDSO to update | LDSO to update
ISD Population | 11/09/2025 | 15/09/2025 | LDSO to update | LDSO to update | LDSO to update
Population of Market Segment (95%) | 06/08/2025 | 12/09/2025 | LDSO to update | LDSO to update | LDSO to update
Population of Domestic Premises Indicator | 06/09/2025 | 08/09/2025 | LDSO to update | LDSO to update | LDSO to update
Pre-M10 Service Activation – LDSOs | 11/09/2025 | 18/09/2025 | LDSO to update | LDSO to update | LDSO to update
Population of Market Segment (100%) | 12/09/2025 | 22/09/2025 | LDSO to update | LDSO to update | LDSO to update
MPRS – Registration Services, UMSO Role, LDSO Role and Data Population Activities | 19/09/2025 | 22/09/2025 | LDSO to update | LDSO to update | LDSO to update
All LDSOs and EES to load ISD files via the URL published within the IF-047 via the Elexon data store (note, this should contain the same ISD file as uploaded to the Elexon portal following 11th September, therefore it may not need to be applied by each party) | 22/09/2025 | 22/09/2025 | LDSO to update | LDSO to update | LDSO to update
Following successful loading of ISD data LDSOs can process New Connections via their DB01 interface to MPRS | 22/09/2025 | 22/09/2025 | LDSO to update | LDSO to update | LDSO to update
Each LDSO will track successful sending of the IF-050 message to the DIP | 22/09/2025 | 22/09/2025 | LDSO to update | LDSO to update | LDSO to update
Organisation Name |  | Point of Contact |  | Reporting Period​ | 
RAG Status Guidance
Red – Off track
Amber – In progress but at risk
Green – On track
Blue - Complete

## Slide 6: M10/M11 Cutover Plan Status Report – Risks and Issues
# | Risk/Issue Description | Mitigation Plan | Target Date
1 |  |  | 
2 |  |  | 
3 |  |  | 
Additional Commentary
(Please indicate if there is anything you would like to highlight to the Programme only and not more widely)