## Slide 1: M10/M11 Supplier Reporting Template
Version 1.0
MHHS-DEL4060
Document Classification: Public

## Slide 2: M10/M11 Cutover Plan Reporting
Suppliers are required to provide regular status updates to the Programme, outlining progress on their cutover activities
To support this, the Programme has developed templates for Participants to complete, which include:
  A list of all cutover activities for which Participants are required to provide a RAG status and an expected finish date
  A risk and issue log
  A free-text section for any additional feedback or comments
Reporting will occur on a weekly basis from the 6th August up until M10. Details of the reporting cadence can be found on slides 5 and 6. The completed templates should be sent to the OpReadiness team at opreadiness@mhhsprogramme.co.uk by 3pm each Wednesday
The Programme will collate the submissions from Participants and produce a consolidated dashboard, which will be made available on the Collaboration Base. This dashboard will provide an overview of collective progress
Please note: The dashboard will present anonymised data, no individual Participant names will be disclosed, only aggregated figures will be shared

## Slide 3
Monday | Tuesday | Wednesday | Thursday | Friday
28/07 | 29/07 | 30/07 | 31/07 | 01/07
04/08 | 05/08 | 06/08 | 07/08 | 08/08
11/08 | 12/08 | 13/08 | 14/08 | 15/08
18/08 | 19/08 | 20/08 | 21/08 | 22/08
25/08 | 26/08 | 27/08 | 28/08 | 29/08
M10/M11 Cutover Plan Reporting Schedule (1/2)
Reporting shared with Programme
Reporting shared with Programme
Reporting shared with Programme
Reporting shared with Programme
Weekly update at GLIG
Weekly update at GLIG
Weekly update at GLIG
Weekly update at GLIG
TORWG

## Slide 4
Monday | Tuesday | Wednesday | Thursday | Friday
01/09 | 02/09 | 03/09 | 04/09 | 05/09
08/09 | 09/09 | 10/09 | 11/09 | 12/09
15/09 | 16/09 | 17/09 | 18/09 | 19/09
22/09 | 23/09 | 24/09 | 25/09 | 26/09
29/09 | 30/09 | 01/10 | 02/10 | 03/10
M10/M11 Cutover Plan Reporting Schedule (2/2)
Reporting shared with Programme
Weekly update at GLIG
Weekly update at GLIG
Weekly update at GLIG
TORWG
PSG
MCAG
Reporting shared with Programme
Reporting shared with Programme
TORWG

## Slide 5: M10/M11 Cutover Plan Status Report – M10 / M11 Suppliers Qualification Pathway 2
Activities | Start Date | Finish Date | Expected Finish Date | Current RAG | Commentary
MHHS Functionality deployed to Production (declaration to the Programme that this will be complete in line with M11 timelines set out in the Cutover Plan) | 2024 | 14/10/2025 | Supplier to update | Supplier to update | Supplier to update
DIP UIT onboarding | 25/07/2025 | 27/08/2025 | Supplier to update | Supplier to update | Supplier to update
ServiceNow Onboarding | 27/08/2025 | 27/08/2025 | Supplier to update | Supplier to update | Supplier to update
Qualification | 29/08/2025 | 29/08/2025 | Supplier to update | Supplier to update | Supplier to update
DIP Production Onboarding | 11/09/2025 | 22/10/2025 | Supplier to update | Supplier to update | Supplier to update
Organisation Name |  | Point of Contact |  | Reporting Period​ | 
RAG Status Guidance
Red – Off track
Amber – In progress but at risk
Green – On track
Blue - Complete

## Slide 6: M10/M11 Cutover Plan Status Report – M10 / M11 Suppliers Qualification Pathway 3
Activities | Start Date | Finish Date | Expected Finish Date | Current RAG | Commentary
MHHS Functionality deployed to Production (declaration to the Programme that this will be complete in line with M11 timelines set out in the Cutover Plan) | 2024 | 14/10/2025 | Supplier to update | Supplier to update | Supplier to update
DIP UIT onboarding | 04/08/2025 | 09/09/2025 | Supplier to update | Supplier to update | Supplier to update
ServiceNow Onboarding | 09/09/2025 | 09/09/2025 | Supplier to update | Supplier to update | Supplier to update
Qualification | 11/09/2025 | 11/09/2025 | Supplier to update | Supplier to update | Supplier to update
DIP Production Onboarding | 11/09/2025 | 22/10/2025 | Supplier to update | Supplier to update | Supplier to update
Organisation Name |  | Point of Contact |  | Reporting Period​ | 
RAG Status Guidance
Red – Off track
Amber – In progress but at risk
Green – On track
Blue - Complete

## Slide 7: M10/M11 Cutover Plan Status Report – M10 / M11 Suppliers Qualification Pathway 4
Activities | Start Date | Finish Date | Expected Finish Date | Current RAG | Commentary
MHHS Functionality deployed to Production (declaration to the Programme that this will be complete in line with M11 timelines set out in the Cutover Plan) | 2024 | 14/10/2025 | Supplier to update | Supplier to update | Supplier to update
DIP UIT onboarding | 22/08/2025 | 24/09/2025 | Supplier to update | Supplier to update | Supplier to update
ServiceNow Onboarding | 24/09/2025 | 24/09/2025 | Supplier to update | Supplier to update | Supplier to update
Qualification | 26/09/2025 | 26/09/2025 | Supplier to update | Supplier to update | Supplier to update
DIP Production Onboarding | 26/09/2025 | 22/10/2025 | Supplier to update | Supplier to update | Supplier to update
Organisation Name |  | Point of Contact |  | Reporting Period​ | 
RAG Status Guidance
Red – Off track
Amber – In progress but at risk
Green – On track
Blue - Complete

## Slide 8: M10/M11 Cutover Plan Status Report – Risks and Issues
# | Risk/Issue Description | Mitigation Plan | Target Date
1 |  |  | 
2 |  |  | 
3 |  |  | 
Additional Commentary
(Please indicate if there is anything you would like to highlight to the Programme only and not more widely)