## Sheet1
Organisation: | MHHS Programme
Constituency: | All
Date: | 2025-05-16 | MHHS-DEL3718 Helix Operational Readiness Testing Scripts Comments Log v1.0
Anonymised: | No
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete |  |  |  | Programme to complete once consultation window has closed.
Comment Reference | Reviewer | Page | Section | Comment | Response | Status
General | MHHS Programme | General | General | It is difficult to assess and trace the completeness of test scenarios without knowing what the source material is for deriving the scenarios. Some suggestions below, but this needs a position from Helix with a traceability to coverage of source material | added traceability matrix | Completed
CPSD | MHHS Programme | General | General | Given that the runbooks are still under development, how do these feed into ORT scope and scripting given that these were highlighted as a dependency for ORT in GLIG 16/5? | scenarios used in the test cases are the ones that have been presented to industry, run book will be available for ORT testing | Completed
General | MHHS Programme | General | General | The Test Cases focus on Major Incidents, but the exchange of information is likely to be needed for incidents that aren't Major. This should be considered for Incident Management. | 3 major incident test cases are included, 4 normal incident | Completed
CPSD | MHHS Programme | General | General | The key to CPSD arrangements is the exchange of information between Help Desks and Service Desks to support the owner of resolution for incidents. Given that the exchange of information is open and not prescribed, test cases to show coverage of the exchange of information between all desks should be considered (e.g. MPAS Help Desk to Elexon), as per section 7.1 & 7.2 of the CPSD Approach. At the moment, I cannot see any TCs that do this. | Test case added | Completed
CPSD | MHHS Programme | General | General | Please consider the addition of a Test Case that requires direct comms between PP IT Service Desk and Elexon Service Desk so that element can be tested. | Agreed | Completed
PR01 | MHHS Programme | General | PR01 | Problem Management was an area of functionality that was not available for SIT Ops, therefore needs to be exercised with some breadth in ORT. Multiple Test Cases for Problem Management should be added. Pre-conditions need to be better defined to trigger this process. What triggers need to be set to trigger the PR process? How do we exercise this? Can we add a Test Case where mutliple similar issues are raised by different participants (maybe across Parent & Child options). | new test cases added | Completed
General | MHHS Programme | General | General | Please consider a test case for release management to show how this is going to work in practice. We should show that multiple parties will be notified of releases across industry. | Release Management will flow into Change Management Process | Completed
TCPAR01 | MHHS Programme | General | TCPAR01 | The requirements and functionality for Parent/Child accounts needs to be defined before the Test Cases for it can be defined. This is due 16/5 so we would suggest that Test Cases are defined and reviewed after that date. | Agreed | Completed
TCPAR01 | MHHS Programme | General | TCPAR01 | The requirements and functionality for Role Based Access Controls and how security protocols will be maintained needs to be defined before the Test Cases for it can be defined. This is due 16/5 so we would suggest that Test Cases are defined and reviewd after that date. | RBAC is not applicable in the out of the box ServiceNow Service Portal | Completed
TCPAR01 | MHHS Programme | General | TCPAR01 | This only has 1 TC defined, but there should be multiple TCs to exercise different test conditions against requirements. Suggest that role based access defined separately from Parent Child and that there are variations including positive and negative testing. E.g. - successful RBAC test, unsuccessful RBAC test. E.g. Parent/Child - test that St Clements can access cases for MPRS issues for any LDSO. Test that St Clements can't access DUoS billing issues for an iDNO using C&C DUBS. Test that ESG can access cases for one of their customers, but that another customer cannot access issues that might relate to a different service from ESG. Test Case to add a new Child should be covered - it will be common, as should the re-allocation of parties between parent-Child relationships (e.g. on change of service providers for Parties). | Agreed but RBAC out of scope | Completed
TCPAR01 | MHHS Programme | General | TCPAR0 | Add a new user to an organisation to ensure that this is done securely as a Test Case. | Self Registration | Completed
MI01 | MHHS Programme | General | MI01 | This is just pretty standard Major Incident in the Test Case with no Cross-Party Service Desk interaction - these test cases should be focused on the echange of information between service desks, as highlighted above. Information sharing between desks in a secure way, particulary for MPAN data. | Additional test cases added | Completed
| MHHS Programme | General |  | As per the above but for a lower priority incident where the exchange of information is required. Information sharing between desks in a secure way, particularly for MPAN data. An test case that included an incident raised to Elexon and then contacting a 3rd party and exchanging data securly would also demionstrtate how this would work in a CSD situation. | Test case added | Completed
General | MHHS Programme | General | All Test Cases | The Test Cases show outcomes and participants on a generic basis across the whole TC, which makes it very difficult to pass steps and understand who should be involved in which steps. The TCs should be defined in the same format as the SIT Ops Test Cases with the same columns with outcomes, participants (also what is done automatically by ServiceNow and what by people) and data preconditions captured on a step by step basis | Noted | Completed
General | MHHS Programme | General | Overview sheet | The test cases dont appear to be related to any set of requirements - therefore not possible to ascertain coverage. the minimum acceptance would be to have the test cases specific to all funtional, technical and business scenarios | Currently being developed | Completed
General | MHHS Programme | General | Overview sheet | the precondition - integration of service desks (synchronisation and sharing) - where - when and how is that achieved? | termology has been changed, this was meant to reflect communication, not syncronisation | Completed
General | MHHS Programme | General | Test Cases | the expected results - are not specific to the steps and general - each step should have a expected result against it | information added | Completed
General | MHHS Programme | General | Test Cases | Where cross parties need to collaborate (e.g. Triage) - are the relationships (contracts or understandings) agreed? | Not Applicable but contracts are still in progress | Completed
General | MHHS Programme | General | Test cases | The use of the term DIP Portal and the DIP seems to be mixed up in some cases. The DIP portal allows users to view organisation data, view messages etc, the DIP is the service that sends/receives messages. See NI06 | Amended | Completed
General | MHHS Programme | General | Parent/Child | Needs to include scenarios for service providers who support multiple organiations and want to be able to raise/raise incidents on behalf of that org. How they are created and managed needs to be represented in some test cases | further test cases to be added | Completed
General | MHHS Programme | General | Test cases | Numbering needs resolving non-contiguous numbers and a Major incident in NI category | has been altered | Completed
General | MHHS Programme | General | Test cases | Not enough scenarios where Elexon is raising cases to third parties, most are related to orgs raising into Elexon. | further test cases to be added | Completed
NPg1 | Suneer Samad |  | TC_MI01 | The test case does not explicitly specify the responsible party for raising or submitting an incident in test step 3. | To be added during ORT planning | Completed
NPg2 | Suneer Samad |  | TC_MI02 | Step No 8: The test step states: 'Initial communications are sent to the Major Incident Distribution List via ServiceNow and email.' Will the programme team request parties to share their principal contact or distribution list? Will the distribution list contain individual or group contact details? | this has been requested via various forums | Completed
NPg3 | Suneer Samad |  | TC_NI01 | o Step No 5: The test step states: ‘Supplier escalates to LDSO with message ID, timestamp, and context’. Will the Supplier communicate with LDSO via an existing channel such as email or SDEP? o In step 7, the incident is resolved. What is the purpose of the Supplier raising the incident with Elexon (steps 8–26) after LDSO has resolved the issue? | Amended | Completed
NPg4 | Suneer Samad |  | TC_NI06 | o The test step no 2 states,: “LDSO Service Desk raises a case with Elexon Service Desk via ServiceNow including evidence (logs, error codes). Expected: Case is successfully logged and assigned for triage.” LDSO does not have access to Elexon ServiceNow. In this case, what would be the medium of communication? Our understanding was that issues should be raised in the Elexon-provided support portal. | Amended | Completed
NPg5 | Suneer Samad |  | TC_PAR01 | o Will the Parent/Child process be implemented in the Elexon-provided Support Portal? | Yes | Completed
TC_NI01 | Grijesh Singh | TC_NI01 | Test Steps 5-7 | Test step 5 doesn't mention escalation channel and subsequent step 6 and 7 is resolving the issue, so rest of the test steps doesn't make sense. | Amended | Completed
TC_NI03 | Grijesh Singh | TC_NI03 | Test Step 2 | Incident is related to data corruption but its describing as DIP outage. | Amended | Completed
TC_NI05 | Grijesh Singh | TC_NI05 | Description | Duplication of content "Data Service identifies issue with Load Shaping data". | Amended | Completed
TC_NI05 | Grijesh Singh | TC_NI05 | Step 5 | Step 4 confirms that issue was with submitted data from DS so no need to mention "If no error found by Elexon". | Amended | Completed
TC_NI05 | Grijesh Singh | TC_NI05 | Step-7 | What is reason for publishing broadcast message related to LSS issue and resolution if it was with respect to only a specific DS. | Amended | Completed
TC_NI06 | Grijesh Singh | TC_NI06 | Description | Duplication of content "LDSO unable to access the DIP". | Amended | Completed
MHHS-DEL2124 | Ralph Azagoh-Kouadio |  |  | I think the MHHS Service Management Strategy document is wery well written and porperly serves for the MHHS purpose. | Agreed | Completed
ORT | Ralph Azagoh-Kouadio |  |  | The Service Management Operational Readiness Test (ORT) Approach document does not make any mention of the PIT Testing. It seems to be only about the SIT Testing, which we are not involved in. So, though the content of the Service Management ORT document is very solid, does it have any relevance to us, as Non-SIT Wave 4 Participant Supplier? | this is not related to test cases and ORT approach has now been endorsed | Completed
ORT Test Scripts-v0.1 | Ralph Azagoh-Kouadio |  |  | The ORT Test Script Tabs labelled "TC_NI...", often refers to LDSO, Supplier, Data Service or Service User's activities. So, why not label them with the participant designation, or part of the participant designation, so they are easily identifiable? | To be added during ORT planning | Completed